## Distribution Workflows
Module | Sub-Module / Step | Source URLs
Bid Process & Tender Management | Tender / NIT Identification – Monitor govt portals, receive NIT, document purchase | https://constructionfront.com/epc-contract/ | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents
| Bid / No-Bid Decision – Scope review, eligibility check, competition analysis, resource check, Go/No-Go | https://constructionfront.com/epc-contract/ | https://rkstrainings.com/what-is-project-management-in-epc/
| Pre-Bid Activities – Pre-bid meeting, site visit, queries submission, corrigendum review | https://constructionfront.com/epc-contract/ | https://www.projectmanager.com/blog/managing-construction-projects
| Scope & BOQ Analysis – BOQ review, technical spec study, quantity validation, ambiguous items | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process
| Cost Estimation – Material cost, civil cost, labour cost, equipment cost, overheads, taxes | https://rkstrainings.com/what-is-project-management-in-epc/ | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents
| Vendor & Subcontractor Quotations – RFQ to vendors, subcontractor quotes, rate comparison | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing
| Risk & Contingency Analysis – ROW risk, soil risk, monsoon risk, regulatory risk, consumer coordination risk | https://constructionfront.com/epc-contract/ | https://www.projectmanager.com/blog/managing-construction-projects
| Bid Price Finalization – Base cost consolidation, margin addition, management approval | https://rkstrainings.com/what-is-project-management-in-epc/ | https://constructionfront.com/epc-contract/
| Bid Preparation & Submission – Technical bid, commercial bid, EMD arrangement, submission, bid opening | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://constructionfront.com/epc-contract/
| Post-Bid Activities – Techno-commercial clarifications, price negotiation, LOA received | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://www.academia.edu/8347063/FIDIC_Conditions_of_Contract_for_EPC_Turnkey_Projects_doc
Contract Finalization | LOA Review & Acceptance – LOA terms review, scope confirmation, acceptance letter | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://rkstrainings.com/what-is-project-management-in-epc/
| Contract Drafting & Negotiation – Draft review, penalty/LD clause, variation clause, DLP terms, dispute resolution | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://www.academia.edu/8347063/FIDIC_Conditions_of_Contract_for_EPC_Turnkey_Projects_doc
| Contract Signing – Final execution, stamp duty, notarization | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://constructionfront.com/epc-contract/
| Bank Guarantee Submission – PBG submission (5-10%), Security Deposit, BG format approval | https://www.academia.edu/8347063/FIDIC_Conditions_of_Contract_for_EPC_Turnkey_Projects_doc | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/
| Insurance & Compliance – CAR insurance, Workmen Compensation, Third Party Liability, ESI/PF docs | https://www.projectmanager.com/blog/managing-construction-projects | https://rkstrainings.com/what-is-project-management-in-epc/
| Contract Effective & Project Kickoff – Contract effective date, project schedule (L1/L2), internal handover | https://rkstrainings.com/what-is-project-management-in-epc/ | https://www.projectmanager.com/blog/managing-construction-projects
Project Mobilization | Financial Mobilization – Mobilization advance claim, advance BG submission, fund allocation | https://www.academia.edu/8347063/FIDIC_Conditions_of_Contract_for_EPC_Turnkey_Projects_doc | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/
| Team Mobilization – PM deployment, site engineers/surveyors, billing engineer, safety officer, labour gangs | https://rkstrainings.com/what-is-project-management-in-epc/ | https://www.projectmanager.com/blog/managing-construction-projects
| Site Office Setup – Site office establishment, material store/yard, IT setup | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/
| Equipment & Vehicles Mobilization – Boring machines, JCB/excavator, crane/hydra, vehicles, safety equipment | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/
| HSE Setup – HSE plan preparation, safety induction, mock drills, incident reporting system | https://electrical4u.com/electrical-power-distribution-system-in-power-systems/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html
| Regulatory Compliances – Labour license, municipal registration, forest/highway/railway permissions | https://www.projectmanager.com/blog/managing-construction-projects | https://rkstrainings.com/what-is-project-management-in-epc/
Detailed Survey & Route Finalization | HT Line Route Survey – Walkover survey, GPS/GIS mapping, obstacle identification, crossing identification, span measurement, ROW verification, pole schedule | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process
| LT Line Route Survey – Consumer list verification, LT route marking, service connection point identification | https://electrical4u.com/electrical-power-distribution-system-in-power-systems/ | https://electricaltechnology.org/2014/03/electrical-power-distribution-system.html
| Soil Investigation – Soil type identification, foundation type selection, water table assessment | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process
| DTR Location Survey – Transformer site selection, civil pad feasibility, proximity to load center, access road availability | https://electrical4u.com/distribution-transformer/ | https://electrical-engineering-portal.com/distribution-substation
| Underground Cable Route Survey – Existing utility mapping, road crossing identification (HDD vs open cut), manhole/joint bay planning, route marker planning | https://electrical-engineering-portal.com/power-cable-laying-installation-methods | https://electrical4u.com/underground-cable-types-advantages-disadvantages/
| Survey Report & Client Approval – Survey report compilation, BOM revision, submission to client, IFC release | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process
Detailed Engineering & Drawing Preparation | HT Line Design – Conductor sag-tension calculations, pole schedule finalization, pole loading calculations, earthing design, DO fuse/AB switch locations, line drawing (plan & profile) | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://electrical4u.com/overhead-line-conductors/
| LT Network Design – Load calculation, conductor size selection (voltage drop), LT pole schedule, service connection schedule | https://electrical4u.com/electrical-power-distribution-system-in-power-systems/ | https://electricaltechnology.org/2014/03/electrical-power-distribution-system.html
| DTR Design – DTR capacity selection, HT connection scheme, LT panel design, earthing scheme, civil pad drawing | https://electrical4u.com/distribution-transformer/ | https://electrical-engineering-portal.com/transformer-factory-acceptance-tests-final-inspections
| Underground Cable Design – Cable sizing (current capacity/voltage drop), cable route drawing with chainage, joint bay/termination schedule, trench cross-section drawing | https://electrical-engineering-portal.com/power-cable-laying-installation-methods | https://electrical4u.com/underground-cable-types-advantages-disadvantages/
| Smart Meter / AMI Design – Meter type selection, communication technology selection (RF/GPRS/PLC), HES architecture, DCU location planning, MDM software configuration | https://electrical4u.com/energy-meter-types-of-energy-meter/ | https://instrumentationtools.com/scada-for-substation-automation/
| Distribution Automation Design – Auto Recloser location, sectionalizer/FRTU selection, FLISR logic design, communication network design, SCADA integration architecture | https://electrical-engineering-portal.com/distribution-automation-system | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-4-scada-and-comms-systems
| Drawing Submission & Approval – Submission to DISCOM/client, review comments incorporation, IFC drawings released | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process
Procurement & Material Management | Procurement Planning – MRP from IFC drawings, long lead item identification (DTRs/smart meters/cables), procurement schedule | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://rkstrainings.com/what-is-project-management-in-epc/
| Vendor Identification & RFQ – DISCOM-approved vendor list, RFQ issuance, technical bid evaluation, commercial comparison | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing
| Purchase Order Issuance – PO preparation with specs, delivery schedule, TPI inspection clause | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://rkstrainings.com/what-is-project-management-in-epc/
| Key Materials Procurement – Poles (PCC/steel/MS), conductors (ACSR/ABC), DTRs (25-250 kVA), insulators, hardware fittings, AB switches, dropout fuses, lightning arrestors, LT distribution boxes, XLPE cables, smart meters, RMU, auto reclosers, earthing materials | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://electrical4u.com/distribution-transformer/
| Vendor Inspection (TPI/FAT) – Factory inspection for DTRs (IS 2026 tests), type test certificate verification for poles/conductors, meter type approval/NABL certificates | https://electrical-engineering-portal.com/transformer-factory-acceptance-tests-final-inspections | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat
| Dispatch & Logistics – Dispatch clearance after inspection, route planning for oversized loads, transit insurance, staggered dispatch as per construction program | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://rkstrainings.com/what-is-project-management-in-epc/
Material Receipt & Store Management | Material Receipt at Site – Delivery challan verification against PO, physical quantity verification, visual inspection, GRN preparation | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://www.substationfaults.com/electrical-substation-construction/
| Incoming Material Inspection – Pole inspection (length/class/crack), conductor inspection (drum condition/length/dia), DTR inspection (nameplate/oil level/bushing/silica gel), hardware/insulator inspection, cable drum inspection, smart meter inspection | https://electrical-engineering-portal.com/transformer-factory-acceptance-tests-final-inspections | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat
| Short Supply / Damage Claim (SDR) – Shortage/damage report to vendor, replacement claim processing, insurance claim for transit damage | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/
| Store Management – Material segregation by type/location, pole yard stacking, conductor drum storage (upright/off ground), DTR storage (level ground/secured), FIFO management, daily material issue register | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://rkstrainings.com/what-is-project-management-in-epc/
| Issue to Field – Material indent from field engineer, issue as per approved drawings, material tracking (issue vs installation reconciliation) | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning
Civil Works | Pole Foundation (Overhead Lines) – Pole location marking per pole schedule, pit excavation by soil type (normal/rocky/waterlogged), PCC foundation base, backfilling and compaction, foundation concrete curing | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/
| Stay Foundation – Stay pit excavation (angle/section/dead end poles), stay block installation, stay rod and stay wire arrangement | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://electrical4u.com/overhead-line-conductors/
| DTR Civil Pad (Ground-Mounted) – Excavation and levelling, RCC pad construction with transformer rail channels, plinth protection, fence/compound wall, oil soak pit construction | https://electrical4u.com/distribution-transformer/ | https://www.substationfaults.com/electrical-substation-construction/
| Earth Pit Construction – Earth pit excavation (2-3m depth), GI pipe/plate electrode installation, salt and charcoal filling, earthing wire connection, earth resistance measurement | https://electrical4u.com/electrical-earthing/ | https://keentelengineering.com/ieee-compliant-ehv-hv-mv-substation-design-services-by-keentel-engineering
| Trench Excavation (UG Projects) – Trench marking per cable route drawing, excavation by location (JCB/HDD/manual), trench depth verification, sand bedding (150mm), route marker brick laying, backfilling in layers with compaction | https://electrical-engineering-portal.com/power-cable-laying-installation-methods | https://electrical4u.com/underground-cable-types-advantages-disadvantages/
| Joint Bay / Manhole Construction – Joint bay excavation, RCC structure construction, cable entry/exit duct sealing, cover slab with lifting provision | https://electrical-engineering-portal.com/power-cable-laying-installation-methods | https://electrical4u.com/underground-cable-types-advantages-disadvantages/
| Control Room / Panel Room (DA/SCADA) – Prefabricated/brick structure construction, cable entry conduits, earthing and lightning protection | https://electrical-engineering-portal.com/distribution-automation-system | https://instrumentationtools.com/scada-for-substation-automation/
Pole Erection & Overhead Line Construction | Pole Erection – Pole transport to location, pole erection using crane/hydra (vertical alignment/rake check), setting in foundation pit and backfilling, compaction and stability check, cross arm and insulator pin fixing | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/
| Cross Arm & Hardware Fitting – Cross arm fixing (11kV configuration), GOI/AB switch mounting, dropout fuse mounting, lightning arrestor mounting, stay wire fitting | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://electrical4u.com/overhead-line-conductors/
| Insulator Fitting – Pin insulator for tangent poles, strain/disc insulator assembly for dead-end/angle poles, visual inspection before fitting | https://electrical4u.com/overhead-line-conductors/ | https://electricaltechnology.org/2014/03/electrical-power-distribution-system.html
| HT Conductor Stringing (11/22/33kV) – Conductor drum placement, pilot wire/pulling rope laying, conductor pulling (manual/mechanical winch), sagging (sag board/dynamometer method), conductor binding/clamping at insulators, jumper connections | https://electrical4u.com/overhead-line-conductors/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning
| LT Conductor / ABC Cable Stringing (415V) – LT cross arm/bracket fixing, ABC cable stringing with messenger wire tensioning, strain/suspension clamp fitting, service connection tee-off joints | https://electrical4u.com/electrical-power-distribution-system-in-power-systems/ | https://electricaltechnology.org/2014/03/electrical-power-distribution-system.html
| Conductor Joints – Mid-span compression joints, parallel groove clamps for T-off connections, ferrule joints for small conductors | https://electrical4u.com/overhead-line-conductors/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning
DTR Installation | DTR Transportation to Site – Proper blocking on truck, tilt indicator check, site accessibility check | https://electrical4u.com/distribution-transformer/ | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents
| DTR Erection (Pole-Mounted) – Transformer brackets/cradle fitting on poles, lifting with hydra/crane, securing on brackets | https://electrical4u.com/distribution-transformer/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning
| DTR Erection (Ground-Mounted) – Placement on RCC pad with rollers, alignment with rail channels, securing with anchor bolts | https://electrical4u.com/distribution-transformer/ | https://www.substationfaults.com/electrical-substation-construction/
| HT Connections – HT AB switch/dropout fuse wiring from feeder line to HV bushing, lightning arrestor connection, HT cable/jumper termination at HV bushing | https://electrical4u.com/distribution-transformer/ | https://electrical4u.com/overhead-line-conductors/
| LT Connections – LT bus bar/link connection from LV bushing, LT distribution box/metering panel installation, LT outgoing feeder connections | https://electrical4u.com/distribution-transformer/ | https://electrical4u.com/electrical-power-distribution-system-in-power-systems/
| DTR Earthing – Body/tank earthing (GI flat to earth electrode), neutral earthing (LV neutral to earth), LA earthing (separate earth pit), earth resistance measurement | https://electrical4u.com/electrical-earthing/ | https://keentelengineering.com/ieee-compliant-ehv-hv-mv-substation-design-services-by-keentel-engineering
| Oil Treatment & Filling – Oil BDV testing (minimum 30 kV/2.5mm), oil filtration if BDV low, oil level check | https://electrical-engineering-portal.com/transformer-factory-acceptance-tests-final-inspections | https://electrical4u.com/distribution-transformer/
| DTR Pre-Commissioning – IR test (HV to LV/HV to earth/LV to earth), Turns Ratio Test (TTR), vector group verification, no-load losses measurement, continuity check | https://electrical-engineering-portal.com/transformer-factory-acceptance-tests-final-inspections | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat
Underground Cable Laying & Termination | Cable Pulling – Cable drum positioning, cable laying in trench (direct buried/in duct), cable bend radius compliance, route marker tiles laying, warning tape laying, cable length reconciliation | https://electrical-engineering-portal.com/power-cable-laying-installation-methods | https://electrical4u.com/underground-cable-types-advantages-disadvantages/
| Cable Jointing – Joint location identification, cold shrink/heat shrink joint kit installation (cable stripping/conductor connection/stress cone/heat shrink tube), joint bay sealing, joint record (GPS/depth/type) | https://electrical-engineering-portal.com/power-cable-laying-installation-methods | https://electrical4u.com/underground-cable-types-advantages-disadvantages/
| Cable Termination – Indoor/outdoor termination kit installation, cable glanding at RMU/panel, armour earthing at termination, stress cone installation, cable tag and phase identification | https://electrical-engineering-portal.com/power-cable-laying-installation-methods | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/
| High Voltage Testing of Cables – IR test before and after laying, VLF hipot test (0.1 Hz, 17kV for 60 min for 11kV cable), partial discharge test for critical circuits, sheath continuity and insulation test | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/
| RMU Installation – RMU positioning and levelling, cable termination at incoming/outgoing feeders, earthing of RMU enclosure, SF6 gas pressure check, functional test (open/close operations) | https://electrical4u.com/underground-cable-types-advantages-disadvantages/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/
Smart Meter / AMI Installation | Meter Hardware Installation – Existing meter removal, smart meter mounting on consumer meter board, CT installation (3-phase/HT consumers), tamper-evident sealing, consumer detail tagging | https://electrical4u.com/energy-meter-types-of-energy-meter/ | https://instrumentationtools.com/scada-for-substation-automation/
| Communication Module Setup – SIM card/RF module insertion and configuration, DCU installation at feeder pillar/DTR, communication test (meter to DCU), DCU to HES link verification | https://instrumentationtools.com/scada-for-substation-automation/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-4-scada-and-comms-systems
| HES / MDM Configuration – Meter registration in HES with consumer data, tariff loading in meter, time sync (meter clock synchronization), data pull test, alert configuration (tamper/power fail/reverse current) | https://instrumentationtools.com/scada-for-substation-automation/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-4-scada-and-comms-systems
| Consumer Onboarding – Consumer information update in DISCOM system, opening reading recording, consumer awareness/demo | https://electrical4u.com/energy-meter-types-of-energy-meter/ | https://electrical-engineering-portal.com/distribution-substation
Distribution Automation (DA) & SCADA Integration | Field Device Installation – Auto Recloser installation (pole mounting/HV cable connection/control cable to RTU), sectionalizer installation, FRTU installation in control box, CT/PT metering unit installation, solar panel/battery backup for FRTU | https://electrical-engineering-portal.com/distribution-automation-system | https://instrumentationtools.com/scada-for-substation-automation/
| Communication Network Setup – GPRS modem configuration in FRTU, optical fiber cable laying if applicable, RF mesh network setup, communication test (FRTU to SCADA connectivity) | https://instrumentationtools.com/scada-for-substation-automation/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-4-scada-and-comms-systems
| SCADA / DMS Configuration – Network topology loading in SCADA (feeder diagram/SLD/equipment tagging), RTU/FRTU protocol configuration (DNP3/IEC 60870-5-101/104), control function testing (remote open/close), FLISR logic testing, alarm and event configuration | https://electrical-engineering-portal.com/distribution-automation-system | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-4-scada-and-comms-systems
| Integration Testing – End-to-end test (field trip → SCADA alarm → auto isolation → restoration), communication redundancy test, SCADA data accuracy verification | https://instrumentationtools.com/scada-for-substation-automation/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-4-scada-and-comms-systems
Electrical Testing & Pre-Commissioning | HT Line Testing – IR test (phase to phase/phase to earth), continuity test, phase sequence verification, visual inspection (hardware tightness/sag/clearances), minimum ground clearance verification (6.1m over roads, railway norms) | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html
| LT Line Testing – IR test of LT network, phase identification at DTR LV terminals, LT feeder polarity check | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://electrical4u.com/electrical-power-distribution-system-in-power-systems/
| DTR Pre-Commissioning Tests – IR test (all combinations), Turns Ratio Test, no load test (no-load current), oil BDV test (minimum 30 kV), earth resistance measurement | https://electrical-engineering-portal.com/transformer-factory-acceptance-tests-final-inspections | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat
| AB Switch / DO Fuse Testing – Mechanical operation test (open/close 5 times), contact resistance measurement, insulation resistance test | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/
| Underground Cable Testing – IR test before and after laying, VLF hipot test, sheath continuity test, phase identification at both ends | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/ | https://electrical4u.com/underground-cable-types-advantages-disadvantages/
| Earthing System Verification – Earth resistance measurement at each DTR (per IE Rules), neutral earthing continuity check, body/equipment earthing continuity check | https://electrical4u.com/electrical-earthing/ | https://keentelengineering.com/ieee-compliant-ehv-hv-mv-substation-design-services-by-keentel-engineering
| Punch List Preparation – Pre-commissioning inspection punch list, closure of punch list items, pre-commissioning completion certificate | https://powersynchro.com/substation-commissioning-checklist/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/
Commissioning & Energization | External Clearances – Commissioning application to DISCOM/regulatory authority, Electrical Inspector (EI) inspection request, EI inspection and certificate issuance, DISCOM PTCC (Permission to Charge Certificate) | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html
| Pre-Energization Safety Check – Safety clearance (all workers off line), earthing clamps removed from all phases, all hardware secured, safety barriers/caution tape, switching scheme briefing | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html
| HT Line Energization – Step-by-step energization from source end, first charge observation (flashovers/tripping), voltage measurement at receiving end, phase sequence verification at all DTR HV terminations | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html
| DTR Energization – HT fuse/AB switch closing (DTR charging), no-load voltage measurement on LT side (415V ±5%), phase sequence check LT side, neutral voltage measurement | https://electrical4u.com/distribution-transformer/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/
| LT Network Energization – LT feeder links closing one by one, voltage measurement at feeder end (voltage drop check), load connection feeder by feeder, load current measurement at DTR LT terminals | https://electrical4u.com/electrical-power-distribution-system-in-power-systems/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/
| Smart Meter Commissioning – Meter power-on verification, real-time energy reading display check, communication link active status in HES, tamper seal verification | https://electrical4u.com/energy-meter-types-of-energy-meter/ | https://instrumentationtools.com/scada-for-substation-automation/
| DA / SCADA Live Commissioning – Auto Recloser live operation test, SCADA real-time data verification, remote switching test from SCADA | https://electrical-engineering-portal.com/distribution-automation-system | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-4-scada-and-comms-systems
Trial Run & Performance Monitoring | Trial Operation Period – System running under normal load (30 days), daily monitoring (voltage/load current/power factor), outage recording (fault type/location/restoration time), smart meter data collection | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html
| AT&C Loss Measurement – DTR metering (energy input at DTR), consumer metering (energy billed), AT&C loss calculation, loss report submission to client | https://electrical-engineering-portal.com/distribution-substation | https://electrical4u.com/transmission-line-in-power-system/
| Snag Rectification – Punch list from trial run, voltage problem rectification (tap change/conductor upgrade), loose connection tightening, earthing improvement | https://powersynchro.com/substation-commissioning-checklist/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/
| Performance Stabilization Certificate – Trial run completion report, performance stabilization confirmed by client | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://www.projectmanager.com/blog/managing-construction-projects
Project Handover & Closure | As-Built Documentation – As-built drawings (pole schedule/route map/GIS data), test certificates (IR/earth resistance/VLF/oil BDV), material reconciliation (issued vs installed vs balance), consumer list with meter numbers, O&M manuals | https://projectmanagement123.com/project-completion-and-handover-procedure/ | https://www.projectmanager.com/blog/managing-construction-projects
| Client Walk-Through & Acceptance – Joint inspection with client/DISCOM team, punch list review and closure confirmation, commissioning report acceptance | https://projectmanagement123.com/project-completion-and-handover-procedure/ | https://www.projectmanager.com/blog/managing-construction-projects
| Provisional Acceptance Certificate (PAC) – PAC issuance by client, retention money partial release | https://relgrow.com/resources/dlp-full-form-in-construction/ | https://www.mastt.com/blogs/defects-liability-period
| Financial Closure – Final bill preparation with all variation orders, measurement book reconciliation, final bill submission and approval, payment receipt | https://www.academia.edu/8347063/FIDIC_Conditions_of_Contract_for_EPC_Turnkey_Projects_doc | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf
| Regulatory Handover – Handover to DISCOM O&M team, line details in DISCOM GIS/asset management, consumer data transfer to DISCOM billing system | https://projectmanagement123.com/project-completion-and-handover-procedure/ | https://electrical-engineering-portal.com/distribution-substation
Defect Liability Period (DLP) | DLP Period Management – DLP period tracking (12-24 months from PAC), periodic site visits, defect register maintenance | https://www.mastt.com/blogs/defects-liability-period | https://relgrow.com/resources/dlp-full-form-in-construction/
| Defect Attendance – Defect notification from client, defect investigation (root cause analysis), repair/replacement execution (conductor snap/insulator failure/DTR failure/smart meter failure), defect closure confirmation | https://www.mastt.com/blogs/defects-liability-period | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/
| Warranty Claims Management – Back-to-back warranty claim to vendor, DTR warranty replacement (12-24 months), smart meter warranty replacement | https://www.mastt.com/blogs/defects-liability-period | https://www.academia.edu/8347063/FIDIC_Conditions_of_Contract_for_EPC_Turnkey_Projects_doc
Final Acceptance Certificate (FAC) & Contract Closeout | FAC Application – All DLP defects closed confirmation, FAC application submission | https://relgrow.com/resources/dlp-full-form-in-construction/ | https://www.mastt.com/blogs/defects-liability-period
| FAC Issuance – Final joint inspection, FAC issued by client | https://relgrow.com/resources/dlp-full-form-in-construction/ | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/
| Retention Release – PBG/BG return by client, retention money release, final payment receipt | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | https://www.academia.edu/8347063/FIDIC_Conditions_of_Contract_for_EPC_Turnkey_Projects_doc
| Contract Closure – Contract closure letter exchange, internal project closure (lessons learned document), project archive (all documents stored) | https://projectmanagement123.com/project-completion-and-handover-procedure/ | https://www.projectmanager.com/blog/managing-construction-projects