## Substation Workflows
Workflow No. | Workflow Name | Sub-Module / Step | Description | Source URL 1 | Source URL 2 | Source URL 3 | Covered in Document (PDF)
1 | Bid Process in Substation EPC Projects | Tender / NIT Received – Opportunity Identification | Company receives Tender or Notice Inviting Tender from client containing project requirements, specs, scope, timelines and eligibility criteria. | https://constructionfront.com/epc-contract/ | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://www.sora.ro/2026/05/31/epc-versus-fidic-contracts/ | Substation.docx; WBSETCL General Technical Specification (Turnkey); OEU White Substation RFP Exhibit A
1 | Bid Process in Substation EPC Projects | Bid / No-Bid Decision – Opportunity Evaluation | Management evaluates project opportunity against company capacity, financials, technical capability and strategic fit before deciding to bid. | https://www.procore.com/library/epc-contractors | https://rkstrainings.com/what-is-project-management-in-epc/ | https://prismecs.com/blog/understanding-the-lifecycle-of-epc-solutions-services | Substation.docx; OEU White Substation RFP Exhibit A
1 | Bid Process in Substation EPC Projects | Eligibility & Pre-Bid – Qualification Verification | Contractor verifies eligibility criteria, attends pre-bid meetings, submits queries, and confirms technical and financial qualifications. | https://www.euci.com/event_post/epc-contracts/ | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://dancumberlandlabs.com/blog/epc-engineering-procurement-construction/ | Substation.docx; OEU White Substation RFP Exhibit A (Pre-Bid Meeting Section)
1 | Bid Process in Substation EPC Projects | Scope Review & Quantity Take-Off – Understanding Project Scope | Engineering team reviews tender drawings and documents, performs quantity take-off for all civil, electrical and mechanical works. | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://electrical-engineering-portal.com/turnkey-substation-technical-documentation | Substation.docx; WBSETCL General Technical Specification (Turnkey); OEU White Substation RFP Exhibit A
1 | Bid Process in Substation EPC Projects | Vendor & Subcontractor Quotations – Market Cost Collection | Procurement team collects quotations from vendors, subcontractors and suppliers for all equipment, materials and services required. | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing | https://www.euci.com/event_post/epc-contracts-remote/ | Substation.docx; WBSETCL General Technical Specification (Turnkey)
1 | Bid Process in Substation EPC Projects | Parallel Cost Estimation – Detailed Cost Calculation | Estimating team calculates detailed project costs including civil, electrical, mechanical, manpower, overheads and logistics. | https://rkstrainings.com/what-is-project-management-in-epc/ | https://prismecs.com/blog/understanding-the-lifecycle-of-epc-solutions-services | https://constructionfront.com/epc-contract/ | Substation.docx
1 | Bid Process in Substation EPC Projects | Base Cost Estimation – Total Project Cost Consolidation | All cost elements are consolidated into a single base cost estimate representing total project execution cost. | https://rkstrainings.com/what-is-project-management-in-epc/ | https://www.pmi.org/learning/library/realizing-engineering-procurement-construction-projects-7173 | https://constructionfront.com/epc-contract/ | Substation.docx; OEU White Substation RFP Exhibit A (Budget: $3.8M)
1 | Bid Process in Substation EPC Projects | Risk & Contingency Analysis – Project Risk Assessment | Risk team identifies project risks, quantifies impact, and adds contingency provisions to the cost estimate. | https://www.mayerbrown.com/Files/Publication/35328234-d6f9-49c7-bbe8-964945bb9158/Presentation/PublicationAttachment/96527455-174f-4e1a-9a9c-9a1d66e9bde3/EPC_contracts_jan15_hosie.pdf | https://rkstrainings.com/what-is-project-management-in-epc/ | https://www.pmi.org/learning/library/realizing-engineering-procurement-construction-projects-7173 | Substation.docx
1 | Bid Process in Substation EPC Projects | Margin Finalization – Profit Strategy Definition | Management finalizes profit margin, commercial strategy and overall bid price based on market conditions and competition. | https://www.euci.com/event_post/epc-contracts/ | https://www.pillsburylaw.com/a/web/157254/EPC-Agreement-Provisions.pdf | https://prismecs.com/blog/understanding-the-lifecycle-of-epc-solutions-services | Substation.docx
1 | Bid Process in Substation EPC Projects | Technical & Commercial Bid Preparation – Proposal Creation | Bid team prepares complete technical proposal and commercial offer documents as per tender requirements for submission. | https://www.pillsburylaw.com/a/web/157254/EPC-Agreement-Provisions.pdf | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://www.euci.com/event_post/epc-contracts/ | Substation.docx; OEU White Substation RFP Exhibit A; WBSETCL General Technical Specification (Turnkey)
1 | Bid Process in Substation EPC Projects | Client Evaluation – Tender Assessment by Client | Client evaluates all received bids for technical compliance, commercial competitiveness and contractor qualifications. | https://www.procore.com/library/epc-contractors | https://www.sora.ro/2026/05/31/epc-versus-fidic-contracts/ | https://constructionfront.com/epc-contract/ | Substation.docx; OEU White Substation RFP Exhibit A
1 | Bid Process in Substation EPC Projects | Bid Award (LOA) – Project Successfully Won | Client issues Letter of Award (LOA) confirming contractor selection. This officially awards the project to the winning bidder. | https://relgrow.com/resources/dlp-full-form-in-construction/ | https://pmri.in/epccompletion/ | https://www.pillsburylaw.com/a/web/157254/EPC-Agreement-Provisions.pdf | Substation.docx; OEU White Substation RFP Exhibit A; WBSETCL General Technical Specification (Turnkey)
1 | Bid Process in Substation EPC Projects | Contract Finalization & PBG – Legal Agreement Completion | Contract terms are agreed and signed. Contractor submits Performance Bank Guarantee (PBG) as required by contract. | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://lauwtjunnji.weebly.com/uploads/1/0/1/7/10171621/fidic_-_conditions_of_contract_for_epc_(turnkey)_projects_(1999).pdf | https://www.pillsburylaw.com/a/web/157254/EPC-Agreement-Provisions.pdf | Substation.docx; OEU White Substation RFP Exhibit A
2 | Contract Finalization and Project Mobilization Process | LOA / LOI Received – Project Award Confirmation | Organization receives Letter of Award (LOA) or Letter of Intent (LOI) from client officially confirming project award. | https://pmri.in/epccompletion/ | https://relgrow.com/resources/dlp-full-form-in-construction/ | https://www.sora.ro/2026/05/31/epc-versus-fidic-contracts/ | Substation.docx; OEU White Substation RFP Exhibit A
2 | Contract Finalization and Project Mobilization Process | Draft and Review Contract – Contract Preparation | Legal and commercial teams draft the contract document covering scope, price, schedule, penalties, warranties and special conditions. | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://lauwtjunnji.weebly.com/uploads/1/0/1/7/10171621/fidic_-_conditions_of_contract_for_epc_(turnkey)_projects_(1999).pdf | https://www.pillsburylaw.com/a/web/157254/EPC-Agreement-Provisions.pdf | Substation.docx; OEU White Substation RFP Exhibit A (Deliverables Section)
2 | Contract Finalization and Project Mobilization Process | Negotiation and Finalization – Commercial and Legal Alignment | Both parties negotiate commercial terms, technical clarifications, payment schedules and risk allocation before signing. | https://petroedgeasia.net/training/engineering-procurement-construction-contracts-epc-training-course/ | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://www.euci.com/event_post/epc-contracts/ | Substation.docx
2 | Contract Finalization and Project Mobilization Process | Contract Signing – Legal Agreement Execution | Authorized representatives from both parties sign the final contract document making it legally binding and effective. | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://www.pillsburylaw.com/a/web/157254/EPC-Agreement-Provisions.pdf | https://constructionfront.com/epc-contract/ | Substation.docx; OEU White Substation RFP Exhibit A
2 | Contract Finalization and Project Mobilization Process | Parallel Compliance Activities – Financial and Regulatory Commitments | Contractor arranges advance bank guarantee (ABG), insurance policies, regulatory registrations and statutory compliance. | https://www.mastt.com/blogs/defects-liability-period | https://lauwtjunnji.weebly.com/uploads/1/0/1/7/10171621/fidic_-_conditions_of_contract_for_epc_(turnkey)_projects_(1999).pdf | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | Substation.docx; WBSETCL General Technical Specification (Turnkey)
2 | Contract Finalization and Project Mobilization Process | Contract Effective – Contract Activation | Contract becomes officially effective (Effective Date). Project clock starts. All teams are notified and project systems activated. | https://pmri.in/epccompletion/ | https://fidic.org/sites/default/files/The%20FIDIC%20Contracts%20Guide.pdf | https://rkstrainings.com/what-is-project-management-in-epc/ | Substation.docx
2 | Contract Finalization and Project Mobilization Process | Bid to Execution Handover – Ownership Transfer | Bid team formally hands over all project documentation, commitments and technical details to the execution project management team. | https://projectmanagement123.com/project-completion-and-handover-procedure/ | https://pmri.in/epccompletion/ | https://rkstrainings.com/what-is-project-management-in-epc/ | Substation.docx
2 | Contract Finalization and Project Mobilization Process | Project Planning Activities – Execution Preparation | Project Manager prepares detailed execution plan, work breakdown structure (WBS), resource plan, procurement schedule and baseline programme. | https://www.pmi.org/learning/library/realizing-engineering-procurement-construction-projects-7173 | https://rkstrainings.com/what-is-project-management-in-epc/ | https://prismecs.com/blog/understanding-the-lifecycle-of-epc-solutions-services | Substation.docx; WBSETCL General Technical Specification – L2 Networks Section
3 | Project Mobilization and Site Establishment Process | Mobilization Advance and Bank Guarantee | Contractor processes mobilization advance payment received from client and submits required Bank Guarantee (BG) as financial security. | https://lauwtjunnji.weebly.com/uploads/1/0/1/7/10171621/fidic_-_conditions_of_contract_for_epc_(turnkey)_projects_(1999).pdf | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | https://pmri.in/epccompletion/ | Substation.docx; WBSETCL General Technical Specification (Turnkey)
3 | Project Mobilization and Site Establishment Process | Site Possession – Physical Site Handover | Client formally hands over physical site to contractor. Contractor takes possession and begins site establishment activities. | https://www.substationfaults.com/electrical-substation-construction/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://rkstrainings.com/what-is-project-management-in-epc/ | Substation.docx; Eskom Dinaledi Civil SOW (DIN20P07-SE-E82); Valard – 10 Stages of Substation Construction
3 | Project Mobilization and Site Establishment Process | Resource Mobilization – Manpower and Equipment Deployment | Project team, skilled manpower, construction equipment, site office infrastructure and temporary facilities are mobilized to site. | https://www.substationfaults.com/electrical-substation-construction/ | https://prismecs.com/blog/understanding-the-lifecycle-of-epc-solutions-services | https://rkstrainings.com/what-is-project-management-in-epc/ | Substation.docx; Valard – 10 Stages (Brushing & Site Clearing)
3 | Project Mobilization and Site Establishment Process | Temporary Infrastructure Setup | Site office, labor camp, water supply, electricity connection, stores, laydown area, roads and fencing established for project operation. | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx; Eskom Dinaledi Civil SOW; OEU White Substation RFP (Site Housekeeping Section)
3 | Project Mobilization and Site Establishment Process | Health, Safety and Environment (HSE) Setup | Site safety plan, emergency response procedures, HSE documentation and safety inductions established before any work begins. | https://electra.cigre.org/311-august-2020/technical-brochures/guidelines-for-safe-work-methods-in-substations.html | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://rkstrainings.com/what-is-project-management-in-epc/ | Eskom Dinaledi Civil SOW (OHS Act Reference); OEU White Substation RFP (Working Hours & Housekeeping)
3 | Project Mobilization and Site Establishment Process | Site Established – Ready for Execution | Milestone confirming site is physically operational and all prerequisites for active work execution are in place. | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/ | https://prismecs.com/blog/understanding-the-lifecycle-of-epc-solutions-services | Substation.docx; Valard – 10 Stages of Substation Construction
4 | Survey, Geotechnical Investigation and Design Release Process | Benchmark Points and Grid Layout | Survey crews establish fixed benchmark reference points and GPS-based grid layout across the project site for measurement accuracy. | https://906a6d36-valard.com | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process | Substation.docx; Valard – 10 Stages (Survey & Geotechnical Studies); OEU White Substation RFP (Site Survey Item)
4 | Survey, Geotechnical Investigation and Design Release Process | Topographic Survey | Survey team conducts detailed topographic survey of the site capturing elevation, contours, existing structures and boundaries. | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://www.substationfaults.com/electrical-substation-construction/ | Substation.docx; OEU White Substation RFP (Site Survey / Utility Locates)
4 | Survey, Geotechnical Investigation and Design Release Process | Soil Investigation / Geotechnical Testing | Geotechnical team performs bore holes, soil sampling and laboratory tests to determine soil bearing capacity, permeability and properties. | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://www.substationfaults.com/electrical-substation-construction/ | Substation.docx; Valard – 10 Stages (Survey & Geotechnical Studies); OEU White Substation RFP (Geotechnical Report)
4 | Survey, Geotechnical Investigation and Design Release Process | Geotechnical Report Preparation | Engineering team prepares geotechnical investigation report with soil test results, bearing capacity, recommendations for foundation design. | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://electrical-engineering-portal.com/power-substation-design-engineering | https://rkstrainings.com/what-is-project-management-in-epc/ | Substation.docx; OEU White Substation RFP (Geotechnical Report – Contractor Responsibility Item 9)
4 | Survey, Geotechnical Investigation and Design Release Process | Technical Review and Client Approval | Draft geotechnical and survey reports submitted for internal review and client approval. Comments incorporated and final report issued. | https://electrical-engineering-portal.com/turnkey-substation-technical-documentation | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://www.pmi.org/learning/library/realizing-engineering-procurement-construction-projects-7173 | Substation.docx; WBSETCL General Technical Specification (Drawing Approval Process)
4 | Survey, Geotechnical Investigation and Design Release Process | Design Basis Finalized – Inputs for Engineering Released | All survey and geotechnical data formally released as engineering inputs. Design basis document finalized for use by engineering teams. | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://electrical-engineering-portal.com/turnkey-substation-technical-documentation | Substation.docx; WBSETCL General Technical Specification (Technical Particulars of System)
5 | Detailed Engineering and IFC Release Process | Design Basis and Engineering Inputs Collection | Engineers collect all technical requirements: tender specs, client needs, geotech reports, electrical loads, site survey data and grid requirements. | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://www.academia.edu/93132452/ElECTRIC_POWER_SUBSTATIONS_ENGINEERING | Substation.docx; WBSETCL General Technical Specification (Turnkey); OEU RFP – 30% Design Items
5 | Detailed Engineering and IFC Release Process | Single Line Diagram (SLD) Preparation | Electrical engineers develop switching SLD and metering/relaying SLD showing all equipment, connections and protection schemes. | https://electrical-engineering-portal.com/power-substation-design-engineering | https://www.academia.edu/93132452/ElECTRIC_POWER_SUBSTATIONS_ENGINEERING | https://keentelengineering.com/ieee-compliant-ehv-hv-mv-substation-design-services-by-keentel-engineering | Substation.docx; WBSETCL General Technical Specification; OEU RFP – SLD Deliverable at 30%
5 | Detailed Engineering and IFC Release Process | General Arrangement and Layout Design | Equipment layout, switchyard arrangement, control room position and general arrangement plans developed based on approved SLD. | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://www.academia.edu/93132452/ElECTRIC_POWER_SUBSTATIONS_ENGINEERING | Substation.docx; WBSETCL General Technical Specification (Land Utilisation Plan); OEU RFP – General Arrangement Plan
5 | Detailed Engineering and IFC Release Process | Civil and Structural Design | Civil engineers design foundations, grading, drainage, cable trenches, structural steel supports, earthmat and control room building. | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://www.academia.edu/93132452/ElECTRIC_POWER_SUBSTATIONS_ENGINEERING | Substation.docx; Eskom Dinaledi Civil SOW; OEU RFP – Civil Design at 60%; WBSETCL (Foundation Design)
5 | Detailed Engineering and IFC Release Process | Protection, Control and SCADA Design | Protection engineers design relay schemes, control panel layouts, AC/DC schematics, SCADA integration and communication block diagrams. | https://electrical-engineering-portal.com/power-substation-design-engineering | https://seclab.illinois.edu/wp-content/uploads/2011/03/iec61850-intro.pdf | https://library.e.abb.com/public/5ea2620c3dec4376a1540fc2b07a18b7/IEC%2061850%20Overview_Self.pdf | Substation.docx; WBSETCL General Technical Specification (Control & Protection Schemes); OEU RFP – Relay/Control Panel Specs
5 | Detailed Engineering and IFC Release Process | Grounding and Earthing Design | Earth mat layout, ground grid design, lightning protection design and earthing calculations prepared per IEEE Std. 80. | https://keentelengineering.com/ieee-compliant-ehv-hv-mv-substation-design-services-by-keentel-engineering | https://www.academia.edu/93132452/ElECTRIC_POWER_SUBSTATIONS_ENGINEERING | https://electrical-engineering-portal.com/power-substation-design-engineering | Substation.docx; WBSETCL General Technical Specification (Earth Mat Layout); OEU RFP – IEEE Std 80 Reference; Eskom Dinaledi SOW (Earthing Standard Ref)
5 | Detailed Engineering and IFC Release Process | Cable and Raceway Design | Underground raceway plans, conduit schedules, cable pulling schedules and cable trench layouts designed for all power and control cables. | https://electrical-engineering-portal.com/power-substation-design-engineering | https://keentelengineering.com/ieee-compliant-ehv-hv-mv-substation-design-services-by-keentel-engineering | https://www.academia.edu/93132452/ElECTRIC_POWER_SUBSTATIONS_ENGINEERING | Substation.docx; OEU RFP – Underground Raceway Plan at 60%; WBSETCL (Cable Supply Scope)
5 | Detailed Engineering and IFC Release Process | Engineering Calculations (Fault, Battery, Lightning, Grounding) | Engineering team performs fault current analysis, battery sizing, lightning protection and grounding calculations to validate design. | https://keentelengineering.com/ieee-compliant-ehv-hv-mv-substation-design-services-by-keentel-engineering | https://www.academia.edu/93132452/ElECTRIC_POWER_SUBSTATIONS_ENGINEERING | https://electrical-engineering-portal.com/power-substation-design-engineering | Substation.docx; OEU White Substation RFP (Calculations at 60% – Fault, Battery, Lightning)
6 | Submit for Approval – Client Submission Process | Drawing and Document Submission to Client | All engineering drawings, calculations and specifications submitted to client for review in sequential order as per approval schedule. | https://electrical-engineering-portal.com/turnkey-substation-technical-documentation | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://www.academia.edu/93132452/ElECTRIC_POWER_SUBSTATIONS_ENGINEERING | Substation.docx; WBSETCL General Technical Specification (Drawings to be Furnished Section); OEU RFP – 30/60/90% Review Gates
6 | Submit for Approval – Client Submission Process | Client Technical Review and Comments | Client engineering team reviews submitted documents for technical compliance, design methodology, safety standards and project requirements. | https://electrical-engineering-portal.com/turnkey-substation-technical-documentation | https://rkstrainings.com/what-is-project-management-in-epc/ | https://www.pmi.org/learning/library/realizing-engineering-procurement-construction-projects-7173 | Substation.docx; OEU RFP – 30/60/90% Review Process; WBSETCL (Modification by WBSETCL Section)
6 | Submit for Approval – Client Submission Process | Revision Incorporation and Resubmission | Contractor incorporates client comments into drawings, updates calculations and resubmits revised documents for final approval. | https://electrical-engineering-portal.com/turnkey-substation-technical-documentation | https://rkstrainings.com/what-is-project-management-in-epc/ | https://keentelengineering.com/a-guide-to-the-substation-design-process | Substation.docx; WBSETCL (Any modification shall be incorporated and resubmitted)
6 | Submit for Approval – Client Submission Process | Approved – IFC (Issued for Construction) Release | Client grants final approval. Drawings are stamped IFC (Issued for Construction) and released to construction and procurement teams. | https://electrical-engineering-portal.com/turnkey-substation-technical-documentation | https://keentelengineering.com/a-guide-to-the-substation-design-process | https://www.academia.edu/93132452/ElECTRIC_POWER_SUBSTATIONS_ENGINEERING | Substation.docx; OEU RFP – Record Drawing Section; WBSETCL (Approval Clause)
7 | Procurement, Vendor Approval and Manufacturing Process | Procurement Plan Preparation | Procurement team identifies all materials and equipment required, prioritizes long-lead items, defines vendor strategy and aligns with project schedule. | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://rkstrainings.com/what-is-project-management-in-epc/ | https://www.procore.com/library/epc-contractors | Substation.docx; OEU RFP – Procurement Specifications Section; WBSETCL (Supply and Delivery Scope Items)
7 | Procurement, Vendor Approval and Manufacturing Process | Request for Quotation (RFQ) and Vendor Identification | RFQs issued to approved vendors for all equipment. Technical specifications and commercial terms shared with potential suppliers. | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing | https://www.euci.com/event_post/epc-contracts-remote/ | Substation.docx; WBSETCL (Makers List of Equipment); OEU RFP (OEU will provide Transformers & Breakers)
7 | Procurement, Vendor Approval and Manufacturing Process | Bid Evaluation and Techno-Commercial Comparison | Procurement team evaluates vendor quotations technically and commercially, prepares comparative statements and recommends preferred vendor. | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://rkstrainings.com/what-is-project-management-in-epc/ | https://www.euci.com/event_post/epc-contracts/ | Substation.docx; WBSETCL General Technical Specification (Workmanship – Bid Conformity Section)
7 | Procurement, Vendor Approval and Manufacturing Process | Purchase Order (PO) Issuance and Vendor Approval | Purchase Order issued to selected vendors. Vendor drawings and technical submittals reviewed and approved before manufacturing begins. | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat | Substation.docx; WBSETCL (Equipment Drawings for Approval Section); OEU RFP – Procurement Specifications
7 | Procurement, Vendor Approval and Manufacturing Process | Advance Payment and Bank Guarantee Processing | Financial transactions completed per purchase order terms. Vendor submits bank guarantee against advance payment before production starts. | https://lauwtjunnji.weebly.com/uploads/1/0/1/7/10171621/fidic_-_conditions_of_contract_for_epc_(turnkey)_projects_(1999).pdf | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | https://pmri.in/epccompletion/ | Substation.docx; WBSETCL General Technical Specification (Turnkey)
8 | Manufacturing Execution, FAT Testing and Dispatch Process | Manufacturing Kickoff – Production Planning | Approved vendors begin production planning, allocate manufacturing resources, schedule production timelines and initiate fabrication. | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat | https://electrical-engineering-portal.com/substation-equipment-type-testing-factory-site-acceptance-testing-fat-sat | Substation.docx; WBSETCL General Technical Specification (Design, Engineering, Testing at Manufacturer)
8 | Manufacturing Execution, FAT Testing and Dispatch Process | In Production – Equipment Manufacturing Process | Vendors manufacture transformers, switchgear, panels, breakers, control systems and structures per approved drawings and purchase orders. | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing | https://electrical-engineering-portal.com/substation-equipment-type-testing-factory-site-acceptance-testing-fat-sat | https://electrical-engineering-portal.com/transformer-factory-acceptance-tests-final-inspections | Substation.docx; WBSETCL General Technical Specification (Fabrication, Galvanizing, Testing, Supply)
8 | Manufacturing Execution, FAT Testing and Dispatch Process | Stage Inspection – In-Process Quality Verification | Client and contractor inspectors visit manufacturing facility during production to verify quality at key manufacturing milestones. | https://electrical-engineering-portal.com/substation-equipment-type-testing-factory-site-acceptance-testing-fat-sat | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing | Substation.docx; WBSETCL General Technical Specification (Inspection Call 15 Days Prior)
8 | Manufacturing Execution, FAT Testing and Dispatch Process | Factory Acceptance Testing (FAT) | Final testing at manufacturer facility verifying electrical performance, operational functionality, safety compliance and design conformity before dispatch. | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat | https://electrical-engineering-portal.com/res3/FAT-SAT-OF-electrical-and-automation-systems.pdf | Substation.docx; WBSETCL General Technical Specification (FAT Testing Scope); OEU RFP – Commissioning and Testing Item
8 | Manufacturing Execution, FAT Testing and Dispatch Process | Dispatch Clearance and Packing | After FAT completion and client dispatch approval, equipment is packed, preserved and prepared for transport to project site. | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | Substation.docx; WBSETCL (Supply and Delivery to Site Scope)
9 | Logistics, Transportation and Material Receipt Process | Transport Planning and Route Survey | Logistics teams plan transport routes, identify dimensional restrictions, obtain special transport permits and coordinate with authorities. | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://rkstrainings.com/what-is-project-management-in-epc/ | https://prismecs.com/blog/understanding-the-lifecycle-of-epc-solutions-services | Substation.docx; OEU RFP (Access Road Design – Contractor Responsibility Item 8)
9 | Logistics, Transportation and Material Receipt Process | Equipment Dispatch from Vendor Facility | Equipment dispatched from manufacturing facility with complete documentation including test reports, packing list and dispatch advices. | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://rkstrainings.com/what-is-project-management-in-epc/ | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat | Substation.docx; WBSETCL General Technical Specification (Supply and Delivery of Cables/Equipment)
9 | Logistics, Transportation and Material Receipt Process | In-Transit Monitoring and Tracking | Logistics team monitors equipment movement from vendor to site, tracks shipment status and coordinates with transporters. | https://rkstrainings.com/what-is-project-management-in-epc/ | https://prismecs.com/blog/understanding-the-lifecycle-of-epc-solutions-services | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | Substation.docx
9 | Logistics, Transportation and Material Receipt Process | Site Unloading and Placement | Heavy equipment unloaded at site using cranes, placed in designated storage or directly on foundations as per erection sequence. | https://www.substationfaults.com/electrical-substation-construction/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://rkstrainings.com/what-is-project-management-in-epc/ | Substation.docx; Valard – 10 Stages (Electrical Equipment installation via cranes); WBSETCL (Transformer unloading at site)
10 | Material Receipt, Inspection and Installation Release Process | Site Preparation for Material Receipt | Site teams verify storage space, unloading equipment readiness, manpower and material handling arrangements before delivery. | https://www.substationfaults.com/electrical-substation-construction/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://projectmanagement123.com/project-completion-and-handover-procedure/ | Substation.docx; Valard – 10 Stages of Substation Construction
10 | Material Receipt, Inspection and Installation Release Process | Material Unloading and Receipt | Materials unloaded at site, verified against dispatch documents, packing lists and purchase orders for quantity and identity. | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/ | Substation.docx
10 | Material Receipt, Inspection and Installation Release Process | Incoming Inspection and Quality Verification | Quality team inspects received equipment for physical damage, completeness, documentation correctness and conformance to specifications. | https://electrical-engineering-portal.com/substation-equipment-type-testing-factory-site-acceptance-testing-fat-sat | https://keentelengineering.com/substation-testing-lifecycle-fat-vs-sat | https://electrical-engineering-portal.com/checks-for-successful-substation-factory-acceptance-testing | Substation.docx; WBSETCL General Technical Specification (Equipment Workmanship Standards)
10 | Material Receipt, Inspection and Installation Release Process | SDR / Claim Management – Discrepancy Resolution | If discrepancies found (damage, shortage, wrong material), SDR (Site Discrepancy Report) raised and claim initiated with vendor/insurer. | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | https://www.pillsburylaw.com/a/web/157254/EPC-Agreement-Provisions.pdf | Substation.docx
10 | Material Receipt, Inspection and Installation Release Process | Storage and Inventory Management | Accepted materials stored properly in designated areas, inventory records updated and materials preserved as per manufacturer requirements. | https://blog.projectmaterials.com/category/epc-projects/procurement-logistics/project-procurement-documents | https://rkstrainings.com/what-is-project-management-in-epc/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | Substation.docx
10 | Material Receipt, Inspection and Installation Release Process | Released for Installation | Materials formally released from inventory to field teams for installation after passing inspection and quality verification. | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/ | https://rkstrainings.com/what-is-project-management-in-epc/ | Substation.docx
11 | Civil Construction and Structural Readiness Process | Site Clearing, Grading and Levelling | Construction teams perform land clearing, grubbing, grading and levelling to prepare site to required elevation per civil drawings. | https://www.substationfaults.com/electrical-substation-construction/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx; Valard – 10 Stages (Brushing & Site Clearing; Substation Pad Construction)
11 | Civil Construction and Structural Readiness Process | Below Grade Works – Cable Trenches, Conduits, Ground Grid | Underground conduits, cable trenches, draw boxes and earth mat conductors installed below ground level per approved drawings. | https://www.substationfaults.com/electrical-substation-construction/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://electra.cigre.org/311-august-2020/technical-brochures/guidelines-for-safe-work-methods-in-substations.html | Substation.docx; Valard – 10 Stages (Below Grade Facilities); OEU RFP – Underground Raceway; WBSETCL (Earth Mat)
11 | Civil Construction and Structural Readiness Process | Foundation Construction | Concrete foundations for equipment, structural steel, control room and buildings constructed per approved foundation drawings. | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/ | https://electra.cigre.org/311-august-2020/technical-brochures/guidelines-for-safe-work-methods-in-substations.html | Substation.docx; Valard – 10 Stages (Foundations); OEU RFP – Foundation Design; WBSETCL (Foundation of Substation Structure)
11 | Civil Construction and Structural Readiness Process | Control Room and Buildings Construction | Control room building, store shed, DG shed, pump house and other civil structures constructed as per architectural drawings. | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/ | https://electra.cigre.org/311-august-2020/technical-brochures/guidelines-for-safe-work-methods-in-substations.html | Substation.docx; Eskom Dinaledi Civil SOW (New Access Control Building); WBSETCL (Control Room Building Design)
11 | Civil Construction and Structural Readiness Process | Drainage, Fencing and Stone Verge | Stormwater drainage system, security fencing, stone verge (HV yard stone) and site perimeter works completed as per civil drawings. | https://www.substationfaults.com/electrical-substation-construction/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://electra.cigre.org/311-august-2020/technical-brochures/guidelines-for-safe-work-methods-in-substations.html | Substation.docx; Eskom Dinaledi Civil SOW (Outer Fence; Stone Verge; Refurbishment of Drainage); OEU RFP – Screen Wall
11 | Civil Construction and Structural Readiness Process | Civil Readiness Check – Structural Work Complete | Formal inspection confirms all civil and structural works are complete and ready for equipment erection to begin. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx
12 | Equipment Erection, Mechanical Installation and Cabling Readiness Process | Prerequisite Verification – Civil and Materials Ready | Confirm all civil foundations complete and all required equipment and materials inspected, accepted and released from inventory. | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | Substation.docx; Valard – 10 Stages (Electrical Equipment)
12 | Equipment Erection, Mechanical Installation and Cabling Readiness Process | Structural Steel Erection | Structural support steel (lattice, H-beam or tubular) erected and secured to foundations to support switchyard equipment. | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/ | https://electra.cigre.org/311-august-2020/technical-brochures/guidelines-for-safe-work-methods-in-substations.html | Substation.docx; Valard – 10 Stages (Structural Support Steel); WBSETCL (Fabrication, Galvanizing, Erection of Structures)
12 | Equipment Erection, Mechanical Installation and Cabling Readiness Process | Power Transformer and Major Equipment Installation | Power transformers, circuit breakers, reactors, CTs, PTs and other major equipment installed on foundations using cranes. | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/ | https://electrical-engineering-portal.com/transformer-factory-acceptance-tests-final-inspections | Substation.docx; Valard – 10 Stages (Electrical Equipment); WBSETCL (Power Transformer Erection & Commissioning); OEU RFP (OEU provides Transformers & Breakers)
12 | Equipment Erection, Mechanical Installation and Cabling Readiness Process | Bus Bar and Conductor Installation | Flexible and rigid bus bars, conductors, insulators, clamps and connectors installed to connect all switchyard equipment. | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://www.substationfaults.com/electrical-substation-construction/ | https://keentelengineering.com/ieee-compliant-ehv-hv-mv-substation-design-services-by-keentel-engineering | Substation.docx; Valard – 10 Stages (Electrical Bus Work); WBSETCL (Clamps, Connectors, Hardware Fittings)
12 | Equipment Erection, Mechanical Installation and Cabling Readiness Process | Mechanical Completion Check | Formal inspection confirms all equipment erection and mechanical installation is complete per drawings before cabling begins. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx
13 | Cabling, Termination, Testing and SAS Readiness Process | Power and Control Cable Laying | Power cables and control cables pulled through conduits and cable trays from control building to all switchyard equipment. | https://www.substationfaults.com/electrical-substation-construction/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx; Valard – 10 Stages (Cable Pulling & Terminating); WBSETCL (Power Cable, Control Cable Supply & Laying)
13 | Cabling, Termination, Testing and SAS Readiness Process | Cable Termination at Equipment and Panels | All cables terminated at equipment terminals, control panels, relay panels and marshalling boxes per approved wiring diagrams. | https://www.substationfaults.com/electrical-substation-construction/ | https://electrical-engineering-portal.com/power-substation-project-design-construction-erection-commissioning | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx; Valard – 10 Stages (Cable Pulling & Terminating); OEU RFP (Point-to-point panel wiring diagrams)
13 | Cabling, Termination, Testing and SAS Readiness Process | Point-to-Point Continuity Testing | Technicians test every cable connection end-to-end for continuity, correct routing, labeling and correct termination against wiring diagrams. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx; OEU RFP (Point-to-point panel wiring diagrams at 90%)
13 | Cabling, Termination, Testing and SAS Readiness Process | SAS Panel Installation and Configuration | Substation Automation System (SAS) panels, IEDs (Intelligent Electronic Devices) and communication equipment installed and configured. | https://instrumentationtools.com/scada-for-substation-automation/ | https://seclab.illinois.edu/wp-content/uploads/2011/03/iec61850-intro.pdf | https://library.e.abb.com/public/5ea2620c3dec4376a1540fc2b07a18b7/IEC%2061850%20Overview_Self.pdf | Substation.docx; WBSETCL (Control & Relay Panel – Supply, Erection, Testing & Commissioning); OEU RFP (Relay & Control Panels)
13 | Cabling, Termination, Testing and SAS Readiness Process | SAS Readiness Check | Formal confirmation that all cabling, terminations and SAS panel installations are complete and ready for functional testing. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-4-scada-and-comms-systems | https://instrumentationtools.com/scada-for-substation-automation/ | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx
14 | SAS / SCADA Integration, Functional Testing and Pre-Commissioning Readiness Process | IED Configuration and Logic Programming | Protection and automation engineers configure IEDs, program protection logic, set relay parameters per coordination study. | https://seclab.illinois.edu/wp-content/uploads/2011/03/iec61850-intro.pdf | https://library.e.abb.com/public/5ea2620c3dec4376a1540fc2b07a18b7/IEC%2061850%20Overview_Self.pdf | https://instrumentationtools.com/scada-for-substation-automation/ | Substation.docx; OEU RFP (Relay settings in AcSELerator format; Relay Coordination Study using ETAP)
14 | SAS / SCADA Integration, Functional Testing and Pre-Commissioning Readiness Process | SCADA Integration and Communication Testing | SCADA system integration tested to verify all signals, alarms, controls and measurements communicate correctly between field and control centre. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-4-scada-and-comms-systems | https://instrumentationtools.com/scada-for-substation-automation/ | https://seclab.illinois.edu/wp-content/uploads/2011/03/iec61850-intro.pdf | Substation.docx; WBSETCL (PLCC/Microwave Teleprotection Commissioning); OEU RFP (Communications Block Diagram)
14 | SAS / SCADA Integration, Functional Testing and Pre-Commissioning Readiness Process | Functional Testing of Protection Schemes | All protection schemes (differential, overcurrent, earth fault, busbar, breaker failure) tested functionally by secondary injection. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx; OEU RFP (Relay Coordination Study using ETAP)
14 | SAS / SCADA Integration, Functional Testing and Pre-Commissioning Readiness Process | HMI and Local Control Testing | Local control panel HMI, mimic display, annunciator, alarm system and local/remote switching tested for correct operation. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-4-scada-and-comms-systems | https://instrumentationtools.com/scada-for-substation-automation/ | https://mbcontrol.com/understanding-substation-automation-systems/ | Substation.docx; WBSETCL (Control & Relay Panel Commissioning)
14 | SAS / SCADA Integration, Functional Testing and Pre-Commissioning Readiness Process | Pre-Commissioning Readiness Declaration | All SAS and functional test results reviewed. Pre-commissioning readiness certificate issued confirming system ready for energization tests. | https://powersynchro.com/substation-commissioning-checklist/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx
15 | Pre-Commissioning Testing, System Validation and Commissioning Readiness Process | Insulation Resistance (IR) Testing | Insulation resistance tested on all cables, transformers, switchgear and equipment to verify insulation integrity before energization. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx; OEU RFP (Equipment Tested in Presence of City Representative)
15 | Pre-Commissioning Testing, System Validation and Commissioning Readiness Process | CT / PT Ratio, Polarity and Burden Testing | Current transformers and voltage transformers tested for ratio accuracy, polarity correctness, excitation and burden compliance. | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx
15 | Pre-Commissioning Testing, System Validation and Commissioning Readiness Process | Protection Relay Secondary Injection Testing | All protection relays tested using secondary injection equipment to verify pickup settings, timing, tripping and relay coordination. | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://elliotengineeringinc.com/testing-and-commissioning/ | Substation.docx; OEU RFP (Relay Settings in AcSELerator; Relay Coordination using ETAP)
15 | Pre-Commissioning Testing, System Validation and Commissioning Readiness Process | Circuit Breaker Timing and Mechanical Testing | Circuit breaker operations tested for timing, contact resistance, mechanical operation, coil profiling and gas/vacuum checks. | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx
15 | Pre-Commissioning Testing, System Validation and Commissioning Readiness Process | Transformer Differential and REF Stability Testing | Transformer differential protection and restricted earth fault (REF) protection tested for stability and correct operation before energization. | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx
15 | Pre-Commissioning Testing, System Validation and Commissioning Readiness Process | Ground Grid Continuity and Earthing Verification | Earth mat continuity tested with low-ohm injection. All equipment earthing connections verified as per IEEE Std. 80/81. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-2-pre-commissioning-inspections/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx; OEU RFP (IEEE Std. 80 – Grounding Reference); WBSETCL (Earthing System Commissioning)
15 | Pre-Commissioning Testing, System Validation and Commissioning Readiness Process | Punch List Identification and Rectification | All outstanding deficiencies from testing identified, punch list prepared, and all items rectified before commissioning readiness declared. | https://powersynchro.com/substation-commissioning-checklist/ | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://pmri.in/epccompletion/ | Substation.docx; OEU RFP (Substantial Completion – List of Items to be Corrected)
15 | Pre-Commissioning Testing, System Validation and Commissioning Readiness Process | Commissioning Readiness Certificate Issued | All pre-commissioning tests completed and documented. Commissioning readiness certificate signed off by client and contractor teams. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://powersynchro.com/substation-commissioning-checklist/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx; OEU RFP (Final Inspection – Written Certification); WBSETCL (Commissioning Plan)
16 | Final Commissioning, Initial Charging and Energization Readiness Process | Pre-Commissioning Completion Verification | Commissioning team confirms all pre-commissioning tests passed, all punch list items cleared and all systems validated before live work begins. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://powersynchro.com/substation-commissioning-checklist/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx; OEU RFP – Final Inspection Section
16 | Final Commissioning, Initial Charging and Energization Readiness Process | External Clearances – Grid / SLDC / Regulatory Approvals | Coordination with Grid/SLDC for synchronization approval, regulatory body clearances and all external operational authorizations obtained. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx
16 | Final Commissioning, Initial Charging and Energization Readiness Process | Initial Charging of Equipment – Step-by-Step Energization | Controlled step-by-step energization starting from low voltage components progressively to high voltage equipment per energization sequence. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx; Valard – 10 Stages (Testing & Commissioning); OEU RFP (Commissioning and Testing)
16 | Final Commissioning, Initial Charging and Energization Readiness Process | Protection Selectivity Verification Under Live Conditions | Protection relay operation verified under live energized conditions. Inrush monitoring, load behavior and protection selectivity confirmed. | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/ | https://elliotengineeringinc.com/testing-and-commissioning/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx
16 | Final Commissioning, Initial Charging and Energization Readiness Process | Energization Readiness Confirmed | All commissioning checks completed. Substation declared energization ready. Full voltage applied across all equipment. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://powersynchro.com/substation-commissioning-checklist/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | Substation.docx; OEU RFP (Equipment Systems Tested and Operational)
17 | Final Energization and Grid Synchronization Process | Grid Authorization Received | Grid operator (SLDC/utility) issues formal authorization for permanent connection and synchronization with the live power grid. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx
17 | Final Energization and Grid Synchronization Process | Charge and Synchronize – Permanent Grid Connection | Substation charged and synchronized with live grid. Electrical connection between new substation and power grid officially established. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx; Valard – 10 Stages (Testing & Commissioning – Substation turned on)
17 | Final Energization and Grid Synchronization Process | Load Flow Verification | Engineers verify correct power flow through transformers, busbars, feeders and outgoing lines. Load distribution and system balance confirmed. | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx
17 | Final Energization and Grid Synchronization Process | Metering and Billing Meter Verification | Energy meters, billing meters, measurement systems, CTs and VTs validated for accurate operational measurement and revenue metering. | https://eepower.com/technical-articles/substation-commissioning-and-testing-part-3-field-testing/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx
18 | Trial Run and Performance Stabilization Process | Trial Operation Period | Substation operated under normal and varying load conditions for a defined period to verify sustained performance and reliability. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://electrical4learning.blogspot.com/2024/11/method-statement-for-testing-and-commissioning-of-substation-equipments.html | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx
18 | Trial Run and Performance Stabilization Process | Performance Monitoring – Live Data Collection | All operational parameters monitored: voltage stability, current flow, transformer loading, protection operation, alarms, SCADA data. | https://www.ncbi.nlm.nih.gov/pmc/articles/PMC12431182/ | https://instrumentationtools.com/scada-for-substation-automation/ | https://mbcontrol.com/understanding-substation-automation-systems/ | Substation.docx; WBSETCL (DGA Test Before Commissioning)
18 | Trial Run and Performance Stabilization Process | Defect Identification and Correction During Trial Run | Any defects or anomalies identified during trial run are recorded, investigated and corrected before handover. | https://relgrow.com/resources/dlp-full-form-in-construction/ | https://www.mastt.com/blogs/defects-liability-period | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | Substation.docx
18 | Trial Run and Performance Stabilization Process | Performance Stabilization Confirmed | System declared stable after successful trial operation. All performance benchmarks met. Substation ready for formal handover. | https://eepower.com/technical-articles/substation-commissioning-and-testingpart-1-scope-and-workflow/ | https://pmri.in/epccompletion/ | https://powersynchro.com/substation-commissioning-checklist/ | Substation.docx
19 | Project Closure, Client Acceptance and Final Handover Process | Punch List Final Completion | All outstanding items from commissioning and trial run identified on final punch list are completely resolved before handover. | https://pmri.in/epccompletion/ | https://projectmanagement123.com/project-completion-and-handover-procedure/ | https://relgrow.com/resources/dlp-full-form-in-construction/ | Substation.docx; OEU RFP (Substantial Completion – Items to be Completed or Corrected)
19 | Project Closure, Client Acceptance and Final Handover Process | Client Walk-through and Acceptance Inspection | Client and contractor jointly inspect all works. Client verifies compliance with contract scope, specifications and quality standards. | https://pmri.in/epccompletion/ | https://projectmanagement123.com/project-completion-and-handover-procedure/ | https://relgrow.com/resources/dlp-full-form-in-construction/ | Substation.docx; OEU RFP (Final Inspection – City conducts inspection to verify completion status)
19 | Project Closure, Client Acceptance and Final Handover Process | As-Built Documentation Handover | Final as-built drawings, test reports, manuals, warranties and operation documentation formally handed over to client. | https://projectmanagement123.com/project-completion-and-handover-procedure/ | https://pmri.in/epccompletion/ | https://relgrow.com/resources/dlp-full-form-in-construction/ | Substation.docx; OEU RFP (Record Drawing in AutoCAD 2018 + Hard Copy; Warranties & Operational Manuals); WBSETCL (Commissioning Plan)
19 | Project Closure, Client Acceptance and Final Handover Process | Certificate of Completion / Provisional Acceptance Certificate (PAC) | Client issues Completion Certificate or PAC (Provisional Acceptance Certificate) marking official project handover and start of DLP. | https://relgrow.com/resources/dlp-full-form-in-construction/ | https://www.mastt.com/blogs/defects-liability-period | https://pmri.in/epccompletion/ | Substation.docx; OEU RFP (Certificate of Substantial Completion); FIDIC Silver Book Reference
19 | Project Closure, Client Acceptance and Final Handover Process | Contractor Closeout Submittals | Contractor submits closeout package: completed submittals, evidence of subcontractor payments, warranties and operation manuals. | https://projectmanagement123.com/project-completion-and-handover-procedure/ | https://pmri.in/epccompletion/ | https://relgrow.com/resources/dlp-full-form-in-construction/ | OEU White Substation RFP – Contractor's Closeout Submittals Section (Page 7-8)
20 | Defect Liability Period (DLP), Warranty Support and Final Acceptance Process | DLP Period Commencement | DLP begins from date of Completion Certificate/PAC. Contractor remains responsible for rectifying defects for DLP duration (typically 12-24 months). | https://www.mastt.com/blogs/defects-liability-period | https://relgrow.com/resources/dlp-full-form-in-construction/ | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | Substation.docx; FIDIC Silver Book – Clause 11
20 | Defect Liability Period (DLP), Warranty Support and Final Acceptance Process | Defect Attendance – Identification and Repair | Client notifies contractor of defects in writing. Contractor attends, investigates and rectifies defects at no extra cost within agreed timeframe. | https://www.mastt.com/blogs/defects-liability-period | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | https://www.turtons.com/blog/what-is-the-defects-liability-period | Substation.docx; OEU RFP (Work Incomplete or Defective – City Notifies Contractor in Writing)
20 | Defect Liability Period (DLP), Warranty Support and Final Acceptance Process | Recurring Defect Investigation and Permanent Resolution | Recurring defects investigated for root cause. Design modifications, material replacements or procedural changes implemented for permanent resolution. | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | https://www.mastt.com/blogs/defects-liability-period | https://www.turtons.com/blog/what-is-the-defects-liability-period | Substation.docx
20 | Defect Liability Period (DLP), Warranty Support and Final Acceptance Process | Warranty Claims Management | Equipment warranty claims raised with manufacturers for defective components. Replacement or repair managed within warranty period. | https://www.mastt.com/blogs/defects-liability-period | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | https://lauwtjunnji.weebly.com/uploads/1/0/1/7/10171621/fidic_-_conditions_of_contract_for_epc_(turnkey)_projects_(1999).pdf | Substation.docx; OEU RFP (Warranties and Operational Manuals – 2 Copies at Closeout)
21 | Final Acceptance Certificate (FAC), Contract Closure and Project Closeout Process | All DLP Defects Rectified – Final Inspection Request | Contractor confirms all DLP defects rectified and requests final inspection from client for issuance of Final Acceptance Certificate (FAC). | https://relgrow.com/resources/dlp-full-form-in-construction/ | https://www.mastt.com/blogs/defects-liability-period | https://pmri.in/epccompletion/ | Substation.docx; OEU RFP (Final Inspection Section – Contractor submits written certification)
21 | Final Acceptance Certificate (FAC), Contract Closure and Project Closeout Process | Final Acceptance Certificate (FAC) Issuance | Client issues FAC after confirming all defects resolved and project performed satisfactorily throughout DLP. Contractor released from further liability. | https://relgrow.com/resources/dlp-full-form-in-construction/ | https://www.mastt.com/blogs/defects-liability-period | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | Substation.docx; FIDIC Silver Book – Clause 11.9 (Performance Certificate)
21 | Final Acceptance Certificate (FAC), Contract Closure and Project Closeout Process | Final Payment and Retention Release | Final payment processed. Retention amounts held during DLP released to contractor. Performance bonds and bank guarantees returned. | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | https://lauwtjunnji.weebly.com/uploads/1/0/1/7/10171621/fidic_-_conditions_of_contract_for_epc_(turnkey)_projects_(1999).pdf | https://www.mastt.com/blogs/defects-liability-period | Substation.docx; OEU RFP (Evidence of Payment to Subcontractors); FIDIC Silver Book – Final Payment Clause
21 | Final Acceptance Certificate (FAC), Contract Closure and Project Closeout Process | Contract Closure and Project Closeout | All contractual obligations fulfilled. Project closed in management systems. Lessons learned documented. Project formally archived. | https://projectmanagement123.com/project-completion-and-handover-procedure/ | https://pmri.in/epccompletion/ | https://www.pmi.org/learning/library/realizing-engineering-procurement-construction-projects-7173 | Substation.docx; OEU RFP – Full Deliverables Section
21 | Final Acceptance Certificate (FAC), Contract Closure and Project Closeout Process | Rework Loop – Unresolved Issues Resolution | If FAC not granted due to remaining issues, rework loop activated. Issues re-investigated, corrected and final inspection repeated. | https://constructionlawmadeeasy.com/construction-law/chapter-10/defects-liability-period/ | https://www.mastt.com/blogs/defects-liability-period | https://projectmanagement123.com/project-completion-and-handover-procedure/ | Substation.docx; OEU RFP (Contractor shall remedy deficiencies – Second Written Notice of Substantial Completion)