## 132 KV Transmission WBS
Level1_Name | Level1_Desc | Level2_Name | Level2_Desc | Level3_Name | Level3_Desc | Level4_Name | Level4_Desc | Level5_Name | Level5_Desc | Assign_To | Timeline | Weight | Tower_Tagging | Leaf_Node_Progress_Type
Level1_Name | Level1_Desc | Level2_Name | Level2_Desc | Level3_Name | Level3_Desc | Level4_Name | Level4_Desc | Level5_Name | Level5_Desc | Assign_To | Timeline | Weight | Tower_Tagging | Leaf_Node_Progress_Type
Project Initial Activity | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Finalization of Sub-Contractor | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Establishment of Store cum office setup | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Mobilization of Site Team | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Statutory approval | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Proposal Making | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Gazzett Notification | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Forest | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | PTCC | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | NHAI | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Railway | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Power live crossing | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Proposal Submission | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Gazzett Notification | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Forest | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | PTCC | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | NHAI | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Railway | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Power live crossing | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Review by Authority | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Gazzett Notification | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Forest | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | PTCC | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | NHAI | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Railway | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Power live crossing | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Approval | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Gazzett Notification | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Forest | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | PTCC | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | NHAI | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Railway | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Power live crossing | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Survey | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Route Survey | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Data gathering/field survey | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Proposal Submission to client | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | approval | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Detail Survey | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Data collection from the filed | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Submission of profile to client | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Profile Approval | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Check Survey | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Data gathering/field survey | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | GTY 132 kV GSS RVPNL NOKHA-CHANDAWAT-AP-01 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-01 - AP-02 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-02 - AP-03 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-03 - AP-04 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-04 - AP-05 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-05 - AP-06 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-06 - AP-07 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-07 - AP-08 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-08 - AP-09 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-09 - AP-10 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-10 - AP-11 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-11 - AP-12 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-12 - AP-13 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-13 - AP-14 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-14 - AP-15 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-15 - AP-16 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-16 - AP-17 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-17 - AP-18 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-18 - AP-19 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-19 - AP-20 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-20 - AP-21 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-21 - AP-22 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-22 - AP-23 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-23 - AP-24 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-24 - AP-25 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-25 - AP-26 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-26 - AP-27 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-27 - AP-28 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-28 - AP-29 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-29 - AP-30 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-30 - AP-31 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-31-GTY 132 kV GSS GOTAN | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Proposal Submission to client | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | GTY 132 kV GSS RVPNL NOKHA-CHANDAWAT-AP-01 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-01 - AP-02 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-02 - AP-03 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-03 - AP-04 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-04 - AP-05 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-05 - AP-06 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-06 - AP-07 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-07 - AP-08 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-08 - AP-09 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-09 - AP-10 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-10 - AP-11 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-11 - AP-12 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-12 - AP-13 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-13 - AP-14 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-14 - AP-15 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-15 - AP-16 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-16 - AP-17 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-17 - AP-18 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-18 - AP-19 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-19 - AP-20 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-20 - AP-21 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-21 - AP-22 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-22 - AP-23 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-23 - AP-24 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-24 - AP-25 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-25 - AP-26 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-26 - AP-27 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-27 - AP-28 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-28 - AP-29 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-29 - AP-30 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-30 - AP-31 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-31-GTY 132 kV GSS GOTAN | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Approval to client | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | GTY 132 kV GSS RVPNL NOKHA-CHANDAWAT-AP-01 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-01 - AP-02 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-02 - AP-03 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-03 - AP-04 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-04 - AP-05 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-05 - AP-06 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-06 - AP-07 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-07 - AP-08 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-08 - AP-09 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-09 - AP-10 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-10 - AP-11 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-11 - AP-12 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-12 - AP-13 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-13 - AP-14 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-14 - AP-15 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-15 - AP-16 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-16 - AP-17 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-17 - AP-18 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-18 - AP-19 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-19 - AP-20 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-20 - AP-21 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-21 - AP-22 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-22 - AP-23 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-23 - AP-24 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-24 - AP-25 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-25 - AP-26 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-26 - AP-27 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-27 - AP-28 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-28 - AP-29 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-29 - AP-30 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-30 - AP-31 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-31-GTY 132 kV GSS GOTAN | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Engineering | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Documentation | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Requisition of Inputs | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Receipt of Drawings | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | All type foundation drawing | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Tower structure | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Earthing drawing | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Sag Chart approval | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Vibration damper placement chart | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Performance of Supply Contract | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Order | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Tower | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | High Tensile Steel |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mild Steel |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Sub Station Structures All type - Mild Steel | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Supply of Bolts & Nuts for towers and stubs (including step bolts & nuts and anti theft bolts & nuts, Spring Washers Etc. ) | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Earthing | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Pipe Type Set |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Counter Poise Earthing set |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Supply of following Tower Accessories | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Danger Plate |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Number Plate |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Phase Plate (Set of three) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Insulator | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | (i) Disc Insulators-70KN |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | (i) Disc Insulators-120KN |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | HTLS Conductor equivalent to ACSR Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Hardware Fittings for HTLS equivalent to Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Single Suspension H/W fittings with Preformed Armour Rod for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Suspension H/W fittings with Preformed Armour Rod for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Tension H/W fittings for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Suspension H/W fittings for pilot string HTLS equivalent to Zebra Conductor (Complete Set with Preformed Armour Rod) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Hardware Fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Suspension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Suspension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Tension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Preformed Armour Rod for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Hardware Fittings for ACSR Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Single Suspension H/W fittings for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Preformed Armour Rod for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | OPGW Cable | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | 48 Fibre (DWSM) OPGW fibre optic cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | 24 Fibre (DWSM) OPGW fibre optic cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | OPGW Hardware Fitting & Accessories | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Installation Hardware set for 48 Fibre OPGW Fibre Optic cabling including all cable fittings & accessories except joint box |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Installation Hardware set for 24 Fibre OPGW Fibre Optic cabling including all cable fittings & accessories except joint box |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | JOINT BOX | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Joint box (48 Fibre) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Joint box (24 Fibre) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | FODP | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | FODP 48F: Indoor Type, rack mounted with FCPC coupling and pigtails |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | FODP 96F: Indoor Type, rack mounted with FCPC coupling and pigtails |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Fiber Optic Approach Cable | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | 48 Fibre (DWSM) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | 24 Fibre (DWSM) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Fiber Optic Approach Cable Hardware Fitting | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Installation Hardware set for above 48 Fibre, Fibre Optic Approach Cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Installation Hardware set for above 24 Fibre, Fibre Optic Approach Cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | G.I. Earth Wire 7/4 MM | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Accessories for Earth Wire | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Strain Assembly for Earth Wire 7/4 mm WITH COPPER Earth Bond |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Suspension Assembly for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration damper for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid span compression joint for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair sleeve for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | G.I. Earth Wire 7/3.15 MM | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Accessories for Earth Wire | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Strain Assembly for Earth Wire 7/3.15 mm WITH COPPER Earth Bond |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Suspension Assembly for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration damper for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid span compression joint for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair sleeve for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Bus Post Insulator | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Post Insulator 145 KV |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Bus PI Clamp for Panther |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | HDPE Pipe | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | HDPE PLB Duct Pipe DN40/33 mm, Rope Feed, Blue Colour with White Strip |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Approval | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Tower | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | High Tensile Steel |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mild Steel |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Sub Station Structures All type - Mild Steel | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Supply of Bolts & Nuts for towers and stubs (including step bolts & nuts and anti theft bolts & nuts, Spring Washers Etc. ) | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Earthing | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Pipe Type Set |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Counter Poise Earthing set |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Supply of following Tower Accessories | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Danger Plate |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Number Plate |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Phase Plate (Set of three) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Insulator | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | (i) Disc Insulators-70KN |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | (i) Disc Insulators-120KN |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | HTLS Conductor equivalent to ACSR Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Hardware Fittings for HTLS equivalent to Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Single Suspension H/W fittings with Preformed Armour Rod for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Suspension H/W fittings with Preformed Armour Rod for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Tension H/W fittings for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Suspension H/W fittings for pilot string HTLS equivalent to Zebra Conductor (Complete Set with Preformed Armour Rod) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Hardware Fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Suspension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Suspension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Tension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Preformed Armour Rod for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Hardware Fittings for ACSR Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Single Suspension H/W fittings for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Preformed Armour Rod for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | OPGW Cable | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | 48 Fibre (DWSM) OPGW fibre optic cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | 24 Fibre (DWSM) OPGW fibre optic cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | OPGW Hardware Fitting & Accessories | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Installation Hardware set for 48 Fibre OPGW Fibre Optic cabling including all cable fittings & accessories except joint box |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Installation Hardware set for 24 Fibre OPGW Fibre Optic cabling including all cable fittings & accessories except joint box |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | JOINT BOX | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Joint box (48 Fibre) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Joint box (24 Fibre) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | FODP | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | FODP 48F: Indoor Type, rack mounted with FCPC coupling and pigtails |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | FODP 96F: Indoor Type, rack mounted with FCPC coupling and pigtails |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Fiber Optic Approach Cable | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | 48 Fibre (DWSM) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | 24 Fibre (DWSM) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Fiber Optic Approach Cable Hardware Fitting | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Installation Hardware set for above 48 Fibre, Fibre Optic Approach Cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Installation Hardware set for above 24 Fibre, Fibre Optic Approach Cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | G.I. Earth Wire 7/4 MM | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Accessories for Earth Wire | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Strain Assembly for Earth Wire 7/4 mm WITH COPPER Earth Bond |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Suspension Assembly for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration damper for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid span compression joint for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair sleeve for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | G.I. Earth Wire 7/3.15 MM | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Accessories for Earth Wire | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Strain Assembly for Earth Wire 7/3.15 mm WITH COPPER Earth Bond |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Suspension Assembly for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration damper for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid span compression joint for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair sleeve for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Bus Post Insulator | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Post Insulator 145 KV |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Bus PI Clamp for Panther |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | HDPE Pipe | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | HDPE PLB Duct Pipe DN40/33 mm, Rope Feed, Blue Colour with White Strip |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Manufacturing | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Tower | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | High Tensile Steel |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mild Steel |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Sub Station Structures All type - Mild Steel | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Supply of Bolts & Nuts for towers and stubs (including step bolts & nuts and anti theft bolts & nuts, Spring Washers Etc. ) | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Earthing | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Pipe Type Set |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Counter Poise Earthing set |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Supply of following Tower Accessories | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Danger Plate |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Number Plate |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Phase Plate (Set of three) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Insulator | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | (i) Disc Insulators-70KN |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | (i) Disc Insulators-120KN |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | HTLS Conductor equivalent to ACSR Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Hardware Fittings for HTLS equivalent to Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Single Suspension H/W fittings with Preformed Armour Rod for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Suspension H/W fittings with Preformed Armour Rod for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Tension H/W fittings for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Suspension H/W fittings for pilot string HTLS equivalent to Zebra Conductor (Complete Set with Preformed Armour Rod) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Hardware Fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Suspension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Suspension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Tension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Preformed Armour Rod for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Hardware Fittings for ACSR Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Single Suspension H/W fittings for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Preformed Armour Rod for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | OPGW Cable | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | 48 Fibre (DWSM) OPGW fibre optic cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | 24 Fibre (DWSM) OPGW fibre optic cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | OPGW Hardware Fitting & Accessories | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Installation Hardware set for 48 Fibre OPGW Fibre Optic cabling including all cable fittings & accessories except joint box |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Installation Hardware set for 24 Fibre OPGW Fibre Optic cabling including all cable fittings & accessories except joint box |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | JOINT BOX | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Joint box (48 Fibre) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Joint box (24 Fibre) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | FODP | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | FODP 48F: Indoor Type, rack mounted with FCPC coupling and pigtails |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | FODP 96F: Indoor Type, rack mounted with FCPC coupling and pigtails |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Fiber Optic Approach Cable | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | 48 Fibre (DWSM) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | 24 Fibre (DWSM) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Fiber Optic Approach Cable Hardware Fitting | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Installation Hardware set for above 48 Fibre, Fibre Optic Approach Cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Installation Hardware set for above 24 Fibre, Fibre Optic Approach Cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | G.I. Earth Wire 7/4 MM | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Accessories for Earth Wire | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Strain Assembly for Earth Wire 7/4 mm WITH COPPER Earth Bond |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Suspension Assembly for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration damper for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid span compression joint for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair sleeve for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | G.I. Earth Wire 7/3.15 MM | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Accessories for Earth Wire | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Strain Assembly for Earth Wire 7/3.15 mm WITH COPPER Earth Bond |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Suspension Assembly for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration damper for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid span compression joint for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair sleeve for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Bus Post Insulator | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Post Insulator 145 KV |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Bus PI Clamp for Panther |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | HDPE Pipe | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | HDPE PLB Duct Pipe DN40/33 mm, Rope Feed, Blue Colour with White Strip |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Supply | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Tower | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | High Tensile Steel |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mild Steel |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Sub Station Structures All type - Mild Steel | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Supply of Bolts & Nuts for towers and stubs (including step bolts & nuts and anti theft bolts & nuts, Spring Washers Etc. ) | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Earthing | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Pipe Type Set |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Counter Poise Earthing set |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Supply of following Tower Accessories | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Danger Plate |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Number Plate |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Phase Plate (Set of three) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Insulator | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | (i) Disc Insulators-70KN |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | (i) Disc Insulators-120KN |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | HTLS Conductor equivalent to ACSR Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Hardware Fittings for HTLS equivalent to Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Single Suspension H/W fittings with Preformed Armour Rod for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Suspension H/W fittings with Preformed Armour Rod for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Tension H/W fittings for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Suspension H/W fittings for pilot string HTLS equivalent to Zebra Conductor (Complete Set with Preformed Armour Rod) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for HTLS equivalent to Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Hardware Fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Suspension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Suspension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Double Tension H/W fittings for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Preformed Armour Rod for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for ACSR Panther Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Hardware Fittings for ACSR Zebra Conductor | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Single Suspension H/W fittings for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Single Tension H/W fittings for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid Span Compression Joint for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair Sleeve for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Preformed Armour Rod for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration Damper for ACSR Zebra Conductor |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | OPGW Cable | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | 48 Fibre (DWSM) OPGW fibre optic cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | 24 Fibre (DWSM) OPGW fibre optic cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | OPGW Hardware Fitting & Accessories | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Installation Hardware set for 48 Fibre OPGW Fibre Optic cabling including all cable fittings & accessories except joint box |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Installation Hardware set for 24 Fibre OPGW Fibre Optic cabling including all cable fittings & accessories except joint box |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | JOINT BOX | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Joint box (48 Fibre) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Joint box (24 Fibre) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | FODP | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | FODP 48F: Indoor Type, rack mounted with FCPC coupling and pigtails |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | FODP 96F: Indoor Type, rack mounted with FCPC coupling and pigtails |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Fiber Optic Approach Cable | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | 48 Fibre (DWSM) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | 24 Fibre (DWSM) |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Fiber Optic Approach Cable Hardware Fitting | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Installation Hardware set for above 48 Fibre, Fibre Optic Approach Cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Installation Hardware set for above 24 Fibre, Fibre Optic Approach Cable |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | G.I. Earth Wire 7/4 MM | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Accessories for Earth Wire | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Strain Assembly for Earth Wire 7/4 mm WITH COPPER Earth Bond |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Suspension Assembly for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration damper for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid span compression joint for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair sleeve for Earth Wire 7/4 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | G.I. Earth Wire 7/3.15 MM | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Accessories for Earth Wire | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Strain Assembly for Earth Wire 7/3.15 mm WITH COPPER Earth Bond |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Suspension Assembly for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Vibration damper for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Mid span compression joint for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Repair sleeve for Earth Wire 7/3.15 mm |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Bus Post Insulator | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | Post Insulator 145 KV |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
[6 empty] | Bus PI Clamp for Panther |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | HDPE Pipe | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
[6 empty] | HDPE PLB Duct Pipe DN40/33 mm, Rope Feed, Blue Colour with White Strip |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Tower Foundation | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Civil Work | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 29/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Earthing | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Tower Erection | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Leg assembly | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 29/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Body panel erection | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 29/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Cross-arm erection | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 29/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Boom erection | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 29/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Bolt tightening & torquing | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 29/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Nut bolt Punching | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 29/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Tack welding | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Location No. 1/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 2/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 2/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 3/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 3/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 4/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 5/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 5/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 6/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 6/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 6/2 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 6/3 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 6/4 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 7/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 7/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 7/2 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 7/3 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 8/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 8/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 8/2 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 8/3 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 8/4 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 9/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 10/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 11/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 12/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 12/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 12/2 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 12/3 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 12/4 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 13/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 13/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 13/2 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 13/3 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 13/4 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 14/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 14/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 14/2 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 15/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 16/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 17/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 18/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 18/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 18/2 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 18/3 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 18/4 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 19/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 20/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 20/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 20/2 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 20/3 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 21/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 21/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 21/2 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 21/3 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 22/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 23/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 23/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 24/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 25/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 26/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 27/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 27/1 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 28/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 29/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 30/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Location No. 31/0 | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Conducter Stringing | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Insulator hosting | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | GTY 132 kV GSS RVPNL NOKHA-CHANDAWAT-AP-01 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-01 - AP-02 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-02 - AP-03 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-03 - AP-04 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-04 - AP-05 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-05 - AP-06 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-06 - AP-07 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-07 - AP-08 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-08 - AP-09 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-09 - AP-10 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-10 - AP-11 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-11 - AP-12 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-12 - AP-13 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-13 - AP-14 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-14 - AP-15 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-15 - AP-16 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-16 - AP-17 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-17 - AP-18 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-18 - AP-19 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-19 - AP-20 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-20 - AP-21 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-21 - AP-22 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-22 - AP-23 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-23 - AP-24 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-24 - AP-25 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-25 - AP-26 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-26 - AP-27 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-27 - AP-28 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-28 - AP-29 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-29 - AP-30 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-30 - AP-31 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-31-GTY 132 kV GSS GOTAN | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Payout of Conducter | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | GTY 132 kV GSS RVPNL NOKHA-CHANDAWAT-AP-01 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-01 - AP-02 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-02 - AP-03 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-03 - AP-04 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-04 - AP-05 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-05 - AP-06 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-06 - AP-07 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-07 - AP-08 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-08 - AP-09 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-09 - AP-10 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-10 - AP-11 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-11 - AP-12 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-12 - AP-13 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-13 - AP-14 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-14 - AP-15 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-15 - AP-16 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-16 - AP-17 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-17 - AP-18 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-18 - AP-19 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-19 - AP-20 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-20 - AP-21 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-21 - AP-22 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-22 - AP-23 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-23 - AP-24 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-24 - AP-25 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-25 - AP-26 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-26 - AP-27 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-27 - AP-28 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-28 - AP-29 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-29 - AP-30 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-30 - AP-31 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-31-GTY 132 kV GSS GOTAN | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Final Sag | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | GTY 132 kV GSS RVPNL NOKHA-CHANDAWAT-AP-01 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-01 - AP-02 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-02 - AP-03 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-03 - AP-04 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-04 - AP-05 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-05 - AP-06 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-06 - AP-07 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-07 - AP-08 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-08 - AP-09 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-09 - AP-10 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-10 - AP-11 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-11 - AP-12 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-12 - AP-13 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-13 - AP-14 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-14 - AP-15 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-15 - AP-16 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-16 - AP-17 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-17 - AP-18 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-18 - AP-19 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-19 - AP-20 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-20 - AP-21 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-21 - AP-22 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-22 - AP-23 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-23 - AP-24 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-24 - AP-25 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-25 - AP-26 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-26 - AP-27 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-27 - AP-28 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-28 - AP-29 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-29 - AP-30 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-30 - AP-31 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-31-GTY 132 kV GSS GOTAN | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Intallation Conducter accessories | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | GTY 132 kV GSS RVPNL NOKHA-CHANDAWAT-AP-01 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-01 - AP-02 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-02 - AP-03 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-03 - AP-04 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-04 - AP-05 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-05 - AP-06 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-06 - AP-07 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-07 - AP-08 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-08 - AP-09 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-09 - AP-10 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-10 - AP-11 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-11 - AP-12 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-12 - AP-13 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-13 - AP-14 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-14 - AP-15 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-15 - AP-16 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-16 - AP-17 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-17 - AP-18 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-18 - AP-19 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-19 - AP-20 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-20 - AP-21 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-21 - AP-22 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-22 - AP-23 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-23 - AP-24 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-24 - AP-25 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-25 - AP-26 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-26 - AP-27 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-27 - AP-28 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-28 - AP-29 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-29 - AP-30 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-30 - AP-31 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-31-GTY 132 kV GSS GOTAN | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Earth wire/OPGW Stringing | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Payout of OPGW | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | GTY 132 kV GSS RVPNL NOKHA-CHANDAWAT-AP-01 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-01-AP-02 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-02-AP-03 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-03-AP-04 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-04-AP-05 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-05-AP-06 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-06-AP-07 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-07-AP-08 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-08-AP-09 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-09-AP-10 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-10-AP-11 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-11-AP-12 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-12-AP-13 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-13-AP-14 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-14-AP-15 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-15-AP-16 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-16-AP-17 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-17-AP-18 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-18-AP-19 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-19-AP-20 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-20-AP-21 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-21-AP-22 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-22-AP-23 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-23-AP-24 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-24-AP-25 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-25-AP-26 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-26-AP-27 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-27-AP-28 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-28-AP-29 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-29-AP-30 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-30-AP-31 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-31-GTY 132 kV GSS GOTAN | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Final Sag | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | GTY 132 kV GSS RVPNL NOKHA-CHANDAWAT-AP-01 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-01-AP-02 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-02-AP-03 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-03-AP-04 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-04-AP-05 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-05-AP-06 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-06-AP-07 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-07-AP-08 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-08-AP-09 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-09-AP-10 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-10-AP-11 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-11-AP-12 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-12-AP-13 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-13-AP-14 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-14-AP-15 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-15-AP-16 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-16-AP-17 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-17-AP-18 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-18-AP-19 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-19-AP-20 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-20-AP-21 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-21-AP-22 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-22-AP-23 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-23-AP-24 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-24-AP-25 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-25-AP-26 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-26-AP-27 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-27-AP-28 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-28-AP-29 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-29-AP-30 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-30-AP-31 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | AP-31-GTY 132 kV GSS GOTAN | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Tower Accessories | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Danger plate | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Phase plate | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Circuit plate | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  | Number plate | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  |  |  | Location No. 1/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 2/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 3/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 4/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 5/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 6/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 7/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 8/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 9/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 10/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 11/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 12/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 13/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 14/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 15/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 16/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 17/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 18/4 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 19/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 20/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/2 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 21/3 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 22/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 23/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 24/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 25/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 26/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 27/1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 28/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 30/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
|  |  |  | Location No. 31/0 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No | Binary
Testing & Commisioning | [9 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026 |  | No
|  | Test | [7 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026
|  |  |  | Test 1 | [5 empty] | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026
[6 empty] | Test 2 |  |  |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026
[8 empty] | Test 3 |  | Harsh,Shruti | 25-Dec-2025¦07-Jun-2026