## Summary
Vendor & Contractor prototype — gap fixing, loop validation and end-to-end testing
Source: NebullaOne-WFM.html (nebullaone/src). Every gap from the end-to-end audit (G-01…G-28) plus 19 issues found during the fix → retest loop (N-01…N-19).
Category | Found | Fixed | Passed (retested) | Remaining
UI | 2 | 2 | 1 | 0
Fields | 2 | 2 | 1 | 0
Validation | 6 | 6 | 0 | 0
Navigation | 1 | 1 | 0 | 0
Workflow | 8 | 8 | 0 | 0
Approval | 13 | 13 | 2 | 0
Status | 6 | 6 | 0 | 0
Data Mapping | 7 | 7 | 0 | 0
Exception Handling | 2 | 2 | 1 | 0
Vendor | 21 | 21 | 3 | 0
Contractor | 34 | 34 | 4 | 0
Total (unique gaps) | 47 | 47 | 5 | 0
Workflow | Result | Evidence
Vendor workflow | FAIL | 0/0 lifecycle steps in one clean run, registration → payment → performance → suspension → closure
Contractor workflow | FAIL | 0/0 lifecycle steps, registration → contract → WBS/BOQ → work → measurement → billing → payment → handover → final bill → retention → closure
Test runs | Passed | Total
Batch 1 — vendor gates, roles, SoD | 0 | 0
Batches 2–3 — approvals, award, contract lifecycle | 0 | 0
Batch 4 — quantity & execution | 0 | 0
Batch 5 — close-out & portal invoices | 0 | 0
Final full-system test | 0 | 0
Assumptions
• No Excel workbook was supplied with the request, so this workbook was created fresh (it has no 'original sheets').
• Roles are demo personas chosen from the 'Acting as' menu; the signed-in user is an administrator with every role but is still bound by segregation of duties.
• Business rules not specified by the user follow common enterprise practice (Legal → Finance contract approval, 5% performance BG, retention released after DLP, qualification pass mark 70). All gates are configurable in Procurement Settings where noted.
• Retention release after the defect liability period was tested by moving the handover date back (time travel); everything else ran on real dates.
• Data lives in browser localStorage (no backend); e-mails and one-time codes are shown on screen.

## Screen Inventory
Module | Sub-module | Screen | Type | Entry | Key actions | Next | Roles
Vendor Management | Overview | Overview dashboard | Page | Sidebar | Filters, drill-down to registry / invoices | — | All
Vendor Management | Vendor Registry | Vendor list | Page | Sidebar; ?open= deep link | Search, column filters, export, columns, bulk actions, status menu | Vendor drawer | Procurement
Vendor Management | Vendor Registry | Register vendor | Modal | Registry → Register vendor | Save draft; Submit (documents required) | Vendor drawer / Vendor Approvals | Procurement Executive
Vendor Management | Vendor Registry | Vendor drawer (Overview, Status & flags, Documents, Bank, Qualification, Equipment*, Approvals, Activity) | Drawer | Registry row | Edit, upload, verify (approval mode), insurance, questionnaire, hold / blacklist, spend-authorization request | Approval Management | Procurement / approvers
Vendor Management | Vendor Registry | Invitations tab + Invite vendor | Tab / modal | Registry | Invite, remind, cancel, share link | Self-registration | Procurement
Vendor Management | Vendor Approvals | Approval queue + Qualification results | Page | Sidebar | Approve / reject / request changes with checklist, override (Finance) | Vendor Registry | Procurement Head, Legal Counsel, Finance Controller
Vendor Management | Compliance Center | Compliance dashboard, verification queue, requirements | Page | Sidebar | Verify / reject documents & policies, reminders | Vendor drawer | Procurement
Vendor Management | RFQ & Quotations | RFQ list, New RFQ, Send RFQ, RFQ drawer, Award by line | Page / modals / drawer | Sidebar | Invite (sourcing gate), send, record quote, accept / return quote, negotiate, award to PO or contract (recommendation) | Purchase Orders / Contracts | Procurement Executive
Vendor Management | Blanket Orders | Blanket orders + call-off | Page | Sidebar | Create call-off PO | Purchase Orders | Procurement
Vendor Management | Purchase Orders | PO list, New PO, PO drawer, GRN | Page / modal / drawer | Sidebar / award | Approve & issue (Procurement Head), receive goods, returns, amend, create bill | Invoices | Procurement / Stores
Vendor Management | Invoices & Payments | Invoice list, Enter bill, Invoice drawer (AP review), Payment run | Page / modal / drawer | Sidebar / RA approval / portal | Accept / reject vendor invoice, hold, notes, instalments, advance, pay (Accounts / Finance) | — | Accounts, Finance Controller
Vendor Management | Vendor Scorecard | Scorecard, standings, rate, offboard | Page | Sidebar | Rate, CAP, auto-block, offboard | Vendor drawer | Procurement
Vendor Management | Vendor Portal | Buyer preview of the supplier portal | Page | Sidebar | Viewing as vendor | — | Procurement
Vendor Management | Procurement Settings | Billing rules, payment checks, overrides, workflow gates, groups | Page | Sidebar | Stop / Warn / Off, gates (documents, compliance, mobilisation, inspection) | — | Admin / Finance
Contract & Labor | Overview | Contract & labour dashboard | Page | Sidebar | Drill-down | — | All
Contract & Labor | Contractor Onboarding | Onboarding list + drawer (documents, mobilisation checklist) | Page / drawer | Sidebar | Onboard contractor, submit, tick checklist | Vendor drawer / Work Orders | Procurement
Contract & Labor | Contracts | Contract list, Create / edit contract, Contract drawer | Page / modal / drawer | Sidebar / award | Submit, approve (Legal → Finance), sign, EOT, change orders, BG register, terminate, closure checklist | Work Orders / Close-out | Procurement, Legal, Finance, PM
Contract & Labor | Contracts | Change order, Guarantee, Terminate | Modals | Contract drawer | CO with quantity lines; add / extend / return / encash BG; terminate | Approval Management | Procurement Head, PM, Finance
Contract & Labor | Work Orders | WO list, Create WO, WO drawer (items, RA bills, equipment, workforce, material, DPR, NCR) | Page / modal / drawer | Sidebar / contract | Issue (gated), record acceptance, measure, suspend / resume / short-close / cancel, deploy equipment, issue material, DPR, NCR | Measurement Book / RA Bills | Procurement, Site Engineer, PM
Contract & Labor | Labour Attendance | Worker-wise muster | Page | Sidebar / portal | Verify, roll up to MB | Measurement Book | Site Engineer
Contract & Labor | Measurement Book | MB, JMS, Inspections & NCRs, Abstract | Page / modals / drawer | Sidebar / WO | Record, JMS sign (contractor agreement or paper JMS), dispute, inspect pass / fail, NCR rework / re-inspect | RA Bills | Site Engineer, HSE Officer
Contract & Labor | RA Bills & Certification | RA bills, contractor claims, Prepare bill, RA drawer, Claim review | Page / modals / drawer | Sidebar / WO / close-out | Prepare (inspection + quantity + material), verify, certify (no open NCR), approve, reject, pay; final bill | Invoices | Site Engineer, QS, PM, Accounts
Contract & Labor | Retention & Deductions | Ledger, releases, deduction register, advances | Page / modals | Sidebar | Request release (handover / BG checks), approve (Finance), release (Accounts) | Close-out | Commercial, Finance, Accounts
Contract & Labor | Labor Rate Management | Rate cards | Page | Sidebar | New / revise rate, approve (Procurement Head) | — | Commercial
Contract & Labor | Performance & Progress | Progress, planned vs actual, daily progress, cost by WBS, scorecard, ratings | Page | Sidebar | Rate contractor | — | PM
Contract & Labor | Close-out & Handover | Close-out list + drawer (work completion, punch list, final inspection, handover certificate, final bill, DLP / retention, closure) | Page / drawer / modals | Sidebar / contract | Add punch, verify, inspect, issue & print certificate, final bill, close contract | Retention / Contracts | PM, Site Engineer
Approvals | Approval Management | 9 queues: vendor registration, spend authorization, POs, vendor invoices, contracts, change orders, RA bills, retention releases, labour rates | Page | Sidebar | Approve / reject / request changes / review (role + SoD enforced) | Record drawers | Approvers
Public | Self-registration | Supplier & contractor registration | Public page | Invite link / portal | Submit registration | Supplier login | Vendor
Public | Supplier portal | Registration fix, RFQs, POs, WOs (measurements agree / dispute, NCRs, daily reports, claims, bills, terms), RA claims, attendance, punch list, bills & payments (submit invoice), pricelist, documents, queries, users | Public page | OTP sign-in | Quote, accept WO, claim, agree JMS, rework NCR, rectify punch, submit invoice, upload documents | — | Vendor / contractor
Public | Vendor quote link | Secure quotation page | Public page | RFQ e-mail | Accept / decline, quote, CSV | Supplier portal | Vendor

## Field Inventory
Form | Field | Type | Required | Validation / rule | Default
Register vendor | Company name | Text | Yes | Required
Register vendor | GSTIN | Text | Yes | 15-char GSTIN format; duplicate GSTIN blocked
Register vendor | PAN | Text | Yes | PAN format; must match GSTIN; duplicate PAN warned
Register vendor | Vendor type | Select | Yes | Goods / Services / Labor | Goods
Register vendor | Supplier type | Select | Yes | Drives TDS section | Company
Register vendor | Trades / categories | Multi-select | Yes | At least one
Register vendor | Contact person / e-mail / phone | Text | Name + e-mail | E-mail format
Register vendor | Bank / account no. / IFSC | Text | For spend authorization | Needed before final approval of a spend-authorized vendor
Register vendor | Registration tier | Select | Yes | Prospective / Spend Authorized; later upgrades need Finance approval | Spend Authorized
Register vendor | Required documents | File upload | Yes (to submit) | All required documents uploaded before submit (setting)
Register vendor | Contractor: labour licence, validity, PF, ESI, workforce, experience | Text / date / number | No
Qualification questionnaire | Rule-set questions | Number / Yes-No / select | All | Score ≥ 70 = qualified; writes back to profile
Insurance policy | Coverage type, policy no., insurer, sum insured, validity, copy | Select / text / number / date / file | Yes | Below minimum cover flagged; Pending until verified
Spend authorization | Justification | Text | No | Request blocked until bank, verified documents, qualification
Approval decision | Remark | Text area | To reject / override | Override only for Finance Controller at the last stage
New RFQ | Title, project, template, source, mode, due date, Incoterm, terms | Text / select / date | Title
New RFQ | Line items (description, unit, qty, required by) | Grid | ≥ 1 line with qty | Lines without qty skipped
New RFQ | Invited vendors | Chips | ≥ 2 (≥ 1 single vendor) | Scorecard standing and compliance gate (Warn / Stop)
New RFQ | Weights price / quality / delivery | Number | Yes |  | 60 / 25 / 15
Award by line | Winner per line | Radio grid | ≥ 1 line | Only accepted, valid quotes of eligible vendors
Award by line | Award recommendation | Text | Yes | Hint when not L1
Award by line | Award as | Toggle | Contractors only | PO or Contract | PO
New PO | Vendor, blanket, project, delivery, bill control, tolerance, lines | Select / date / grid | Vendor + lines | Spend-authorized, unblocked; scorecard + compliance gate; blanket allowance
Enter vendor bill | PO / vendor, invoice no., date, lines, GST | Select / text / grid | Yes | Duplicate invoice no. blocked; PO / receipt required per settings; invoices hold
Submit invoice (portal) | PO, invoice no., date, quantities, GST, copy | Select / text / number / file | Yes | Quantity ≤ billable; no future date; duplicate no. blocked; copy required
Payment run | Mode, value date, override reason | Select / date / text | Mode | Accounts / Finance only; not the enterer / approver; hard stops can't be overridden
Create contract | Contractor, project, type, title, value / BOQ lines, dates, owner | Select / text / number / date / grid | Contractor, title, value, dates | Contractor eligibility; completion after start | Item-Rate
Create contract | Retention, advance, recovery, cess, GST, DLP, LD, LD cap | Number / select | — |  | 5 / 10 / 10 / 1 / 18 / 12 / 0.5 / 5
Create contract | Performance BG % + BG no., bank, validity | Number / text / date | Validity if BG no. | PBG must be on file before signing | 5%
Change order | Description, reason, value, days, quantity lines (WO, item, extra qty, rate) | Text / number / grid | Description, reason | Lines complete; value = lines when present
Bank guarantee | Type, bank, number, amount, validity | Select / text / number / date | Yes | Extend: later date; return / encash: reason
Create work order | Contract, type, WBS, title, location, start / finish | Select / text / date | Contract, WBS, title | Issue gated (contract, contractor, mobilisation); headroom | Item-Rate
Create work order | Items (code, description, unit, qty, rate) / lump sum + milestones | Grid | Yes | Qty ≤ contract BOQ balance; milestone weights = 100%
Suspend / short-close / cancel WO | Reason | Text area | Yes | Role PM / Procurement Head; cancel only without measurements
Record measurement | WO, item / milestone, date, location, N×L×B×D or qty / cumulative % | Select / text / number | WO, item, location | Only accepted, open WOs; LS % above last signed ≤ 100; over-WO warning
JMS sign-off | Contractor representative, engineer, re-measured qty, paper JMS confirmation | Text / number / checkbox | Yes | Site Engineer role; portal agreement or paper JMS
Inspection / NCR | Result, category, severity, description | Toggle / select / text | Description on fail | Inspector ≠ recorder
Prepare RA bill | WO, period, measurements, penalty, other, note, final bill | Select / date / checkbox / number | WO + ≥1 measurement | Signed + inspected only; quantity ≤ WO qty; material auto; final bill must include everything
Verify contractor claim | Certified quantity, representative, remark, inspection confirmation | Number / text / checkbox | Rep + inspection | Quantity ≤ WO balance; Site Engineer
Retention release request | Contract, basis, amount, note | Select / number / text | Contract, amount | ≤ available; handover for after-DLP / completion; retention BG for BG-backed
Material issue | Material, qty, unit, recovery rate, date | Text / number / select / date | Yes
Daily progress report | Date, manpower, weather, work done, hindrances | Date / number / select / text | Date, manpower, work | One per WO per day; not in the future
Equipment | Name, type, reg. no., capacity, owned / hired, fitness validity | Text / select / date | Name, reg. no., validity | Expired fitness can't be deployed
Punch item | Snag, location, WO, severity, rectify by | Text / select / date | Snag, date
Final inspection | Result, remarks, snags | Toggle / text / text area | Remarks (+ snags on fail) | Only after WOs done, punch & NCRs closed; PM
Handover certificate | Date, taken over by, remarks | Date / text | Date, taken over by | After a passed inspection; not future; PM

## Workflow Vendor
Step | Stage | Screen | Role | Status in | Status out | Gate / validation
V01 | Registration (Tier 1) | Vendor Registry → Register vendor / self-registration | Procurement Exec / vendor | — | Pending Approval | Required documents uploaded; duplicate GSTIN
V02 | Validation & document submission | Vendor drawer → Documents / portal | Procurement / vendor | Pending Approval | Pending Approval | Format checks; checklist shows open items
V03 | Document verification | Vendor drawer (approval mode) / Compliance Center | Procurement | Docs Pending | Docs Verified | Reject with reason → vendor re-uploads
V03b | Qualification | Vendor drawer → Qualification | Procurement | — | Score | ≥ 70 qualified
V04 | Approval | Vendor Approvals / Approval Management | Procurement Head → Legal Counsel → Finance Controller | Pending Approval | Active / Rejected / Changes Requested | Checklist gate at Finance; SoD; override with reason
V04b | Tier 2 (spend authorization) | Vendor drawer → Approvals | Procurement → Finance Controller | Prospective | Spend Authorized | Bank, verified docs, qualification
V05 | RFQ | RFQ & Quotations | Procurement Exec | Draft | Sent | ≥ 2 vendors; sourcing gate
V06 | Quotation | Vendor quote link / portal | Vendor | Invited | Quoted / Under review | Sign-in; hold blocks quoting
V07 | Evaluation & selection | RFQ drawer → review, comparison, award | Procurement Exec | Under review | Accepted → Awarded | Recommendation; eligible vendors only
V08 | Contract / PO | Purchase Orders / Approval Management | Procurement Head | Draft | Issued / Cancelled | Approver ≠ awarder; vendor eligible
V09 | Delivery & acceptance | PO drawer → GRN | Stores / Procurement | Issued | Partially Received / Received | Rejected qty → return + debit note
V10 | Invoice & validation | Portal submit invoice / Enter bill → AP review | Vendor → Accounts | — | Awaiting Review → Accepted / Rejected | Duplicate no.; billable qty; 3-way match
V11 | Approval & payment | Invoice drawer → Payment run | Accounts / Finance | Unpaid | Paid | Holds, compliance, bank; SoD
V12 | Performance | Vendor Scorecard | Procurement | — | Score / standing | Standings warn / prevent
V13 | Renewal / requalification | Qualification tab / Compliance Center | Procurement | Qualified | Requalification due | Overdue blocks PO (Stop)
V14 | Suspension | Status menu / hold | Procurement | Active | On Hold / Blacklisted | Portal read-only; auto-release on date
V15 | Closure | Status menu / offboard | Procurement Head | Active | Inactive | Portal access ends

## Workflow Contractor
Step | Stage | Screen | Role | Status in | Status out | Gate / validation
C01 | Registration | Contractor Onboarding → Onboard contractor | Procurement Exec | — | Pending Approval | Statutory documents
C02 | Technical / financial / legal / HSE qualification | Vendor drawer → Documents, insurance, Qualification | Procurement | — | Verified / scored | WC insurance, CLRA, HSE questions
C03 | Approval → contractor master | Vendor Approvals | Procurement Head → Legal → Finance | Pending Approval | Active | Checklist gate; SoD
C04 | Mobilisation checklist | Onboarding drawer | Procurement | — | Complete | Gates the first WO
C05 | Tender / BOQ / rate submission | RFQ & Quotations → quote link | Procurement / contractor | Draft | Quoted | Sign-in
C06 | Technical & commercial evaluation → selection | RFQ drawer → award as contract | Procurement | Under review | Awarded → Contract Draft (BOQ) | Recommendation; eligible contractor
C07 | Contract & contract approval | Contracts | Owner → Legal → Finance → Procurement Head | Draft | Pending Approval → Approved → Active | PBG before signing; SoD
C08 | Project → WBS → BOQ → work package | Work Orders | Procurement / PM | — | Issued → Accepted | WBS required; lines from contract BOQ; issue gates
C09 | Mobilisation: workforce, material, equipment | WO drawer → resources | Site Engineer | Issued | In Progress | Equipment fitness
C10 | Execution → progress → measurement → verification | Measurement Book / portal | Site Engineer / contractor | Pending | Signed + Passed | Contractor agreement; inspection; NCR loop
C11 | Certification → RA bill → deductions → invoice → payment | RA Bills → Invoices | Site Eng → QS → PM → Accounts | Submitted | Paid | Quantity cap; open NCR blocks; material auto; SoD
C12 | Variation / change order | Contract drawer → change order | Procurement → PM | Pending | Approved (WO qty raised) | Raiser ≠ approver
C13 | Performance | Performance & Progress | PM | — | Rating | —
C14 | Punch list | Close-out drawer / portal | PM / contractor | Open | Rectified → Closed | —
C15 | Final inspection | Close-out drawer | PM | — | Passed / Failed (→ snags) | WOs done, punch & NCR closed
C16 | Handover | Close-out drawer | PM | — | Handover certificate | After passed inspection
C17 | Final bill → final payment | Close-out → Prepare final bill → RA flow | Site Eng → QS → PM → Accounts | — | Paid; WO billing closed | Includes all remaining work
C18 | Security / retention release | Retention & Deductions / BG register | Commercial → Finance → Accounts | Pending Approval | Released; BG returned | Handover, DLP, retention BG
C19 | Contract closure | Close-out / contract drawer | Procurement Head / PM | Active | Closed (WOs frozen) | 13-point checklist
— | Exception: termination | Contract drawer → Terminate | Procurement Head | Active | Terminated → Closed | Open WOs short-closed

## Status Model
Entity | From | Action | To | Who | Rule
Vendor | Draft | Submit | Pending Approval | Procurement | Required documents uploaded
Vendor | Pending Approval | Approve (stage) | Pending (next stage) | Stage role | SoD
Vendor | Pending Approval | Approve (Finance) | Active | Finance Controller | Checklist or override
Vendor | Pending Approval | Reject | Rejected | Stage role | Reason
Vendor | Pending Approval | Request changes | Changes Requested | Stage role | Items listed
Vendor | Rejected / Changes Requested | Resubmit | Pending Approval | Owner / vendor | Earlier approvals kept
Vendor | Active | Hold | On Hold | Procurement | Scope + release date
Vendor | On Hold | Release / release date passes | Active | Procurement / system | Audit logged
Vendor | Active | Blacklist | Blacklisted | Procurement | Reason
Vendor | Blacklisted | Remove from blacklist | Active | Procurement Head
Vendor | Active | Disable / offboard | Inactive | Procurement | Portal access ends
Vendor tier | Prospective | Request → approve | Spend Authorized | Requester → Finance Controller | Bank, docs, qualification
PO | Draft | Approve & issue / reject | Issued / Cancelled | Procurement Head | ≠ creator / awarder
PO | Issued | GRN | Partially Received / Received | Stores
Vendor invoice (portal) | Awaiting Review | Accept / reject | Unpaid / Rejected | Accounts / Finance | Reason to reject
Invoice | Unpaid | Pay | Partially Paid / Paid | Accounts / Finance | Gate + SoD
Contract | Draft / Rejected | Submit | Pending Approval | Owner | Contractor eligible
Contract | Pending Approval | Legal → Finance approve | Approved | Legal Counsel, Finance Controller | SoD
Contract | Pending Approval | Reject | Rejected | Stage role | Reason
Contract | Approved | Sign & activate | Active | Procurement Head / PM | PBG, eligibility
Contract | Active | Handover certificate | In DLP | PM | Passed final inspection
Contract | Active / In DLP / Completed | Close | Closed | Procurement Head / PM | Checklist
Contract | Active | Terminate | Terminated | Procurement Head | Reason; WOs short-closed
Work order | Draft | Issue | Issued | — | woIssueBlockers
Work order | Issued | Contractor accepts / declines | Accepted / Declined | Contractor
Work order | Issued / In Progress | Suspend / resume | Suspended / In Progress | PM | Reason; resume re-checks
Work order | In Progress | Mark completed | Completed | — | ≥ 99.5% measured
Work order | Issued / In Progress / Suspended | Short-close / cancel | Short-closed / Cancelled | PM | Cancel only without work
Work order | Completed / Short-closed | Contract closed | Closed | system
Measurement | Pending | Contractor agrees / disputes | Pending (agreed) / Disputed | Contractor
Measurement | Pending / Disputed | JMS sign | Signed | Site Engineer | Agreement or paper JMS
Measurement | Signed | Inspect | Passed / Failed (NCR) | Site Eng / HSE | ≠ recorder
NCR | Open | Rework done | Rework Done | Contractor / site
NCR | Rework Done | Re-inspect | Closed / Open | Inspector
RA bill | Submitted | Verify | Verified | Site Engineer | SoD
RA bill | Verified | Certify | Certified | Quantity Surveyor | No open NCR
RA bill | Certified | Approve | Approved (+ payable) | Project Manager
RA bill | Submitted / Verified / Certified | Reject | Rejected | Step role | Measurements & material released; claim returned
RA bill | Approved | Pay | Paid | Accounts / Finance
Retention release | Pending Approval | Approve / reject | Approved / Rejected | Finance Controller | ≠ requester
Retention release | Approved | Release | Released | Accounts / Finance | ≠ requester / approver
Change order | Pending | Approve / reject | Approved / Rejected | Project Manager | ≠ raiser; lines raise WO qty
Punch item | Open | Rectify | Rectified | Contractor
Punch item | Rectified | Verify / reopen | Closed / Open | PM / Site Eng
Bank guarantee | Active | Extend / return / encash | Active / Returned / Encashed | Procurement / Finance (encash)

## Gap Tracker
ID | Module | Screen | Issue | Severity | Category | Root cause | Retested | Regression tested | Status
G-01 | Vendor & Contractor | Vendor Approvals / Approval Management | Final approval activated a vendor with every document missing and no qualification | High | Approval | approvalAction had no preconditions | No | Yes | Fixed
G-02 | Vendor | Vendor drawer → Status & flags | Registration tier could be switched to Spend Authorized in a dropdown | High | Approval | Direct field edit | No | Yes | Fixed
G-03 | Contractor | Contracts | No contract approval; 'Sign & activate' available to the creator; contract activated for an unapproved contractor | High | Approval | ContractModal activated directly | No | Yes | Fixed
G-04 | Contractor | Work Orders | Blacklisted contractor's contract offered in the WO picker; WO could be issued | High | Workflow | No status check at issue | No | Yes | Fixed
G-05 | Vendor & Contractor | Supplier portal | Portal ignored vendor status; contractor On Hold (All) could still submit claims | High | Status | No enforcement in portal | No | Yes | Fixed
G-06 | Contractor | RA bills / claim verification | Quantity above the WO line could be signed and billed | High | Validation | computeRABill had no cap | No | Yes | Fixed
G-07 | Contractor | Change orders | Change orders carried value and days only | Medium | Data Mapping | No quantity lines | No | Yes | Fixed
G-08 | Contractor | RFQ award → contract | RFQ award always created a PO; no award → contract handoff | High | Workflow | SplitAwardModal only created POs | No | Yes | Fixed
G-09 | Contractor | Project / WBS / BOQ | Project was a text label; no WBS; WO lines typed, not linked to a BOQ | Medium | Data Mapping | Model missing | No | Yes | Fixed
G-10 | Contractor | Close-out | No punch list, final inspection, handover certificate or final bill | High | Workflow | Screens missing | No | Yes | Fixed
G-11 | Contractor | Contract closure | Closure checked only end date and retention; WOs stayed billable after closure | Medium | Validation | Weak check | No | Yes | Fixed
G-12 | Contractor | Measurement book / RA certification | No quality or HSE inspection before certification | Medium | Workflow | Step missing | No | Yes | Fixed
G-13 | All | Every approval | No role model: one user approved all stages and paid | High | Approval | Single demo user | No | Yes | Fixed
G-14 | Vendor | RFQ invite / PO | Non-compliant or requalification-due vendors could be sourced from | Medium | Validation | Check only at payment | No | Yes | Fixed
G-15 | Contractor | Equipment | No equipment register or deployment | Medium | Data Mapping | Model missing | No | Yes | Fixed
G-16 | Contractor | Material | Free-issue material was a manual deduction | Medium | Data Mapping | Model missing | No | Yes | Fixed
G-17 | Contractor | Daily progress | No daily progress report | Low | Workflow | Screen missing | No | Yes | Fixed
G-18 | Vendor | Invoice submission | Vendors couldn't submit invoices in the portal | Low | Workflow | Screen missing | No | Yes | Fixed
G-19 | Vendor | Vendor bills | Duplicate vendor bill numbers not checked | Medium | Validation | No check | No | Yes | Fixed
G-20 | Vendor & Contractor | Award | Award had no approval or recommendation note | Medium | Approval | — | No | Yes | Fixed
G-21 | Contractor | Contracts / WOs | No terminate, stop-work, cancel or short-close | Low | Status | Statuses unused | No | Yes | Fixed
G-22 | Contractor | Security / BG | BG number and expiry were plain fields | Low | Data Mapping | Model missing | No | Yes | Fixed
G-23 | Contractor | JMS | Contractor's JMS signature was a typed name | Observation | Workflow | Design | No | Yes | Fixed
G-24 | Contractor | Mobilisation | Mobilisation checklist had no effect | Low | Workflow | Orphan screen | No | Yes | Fixed
G-25 | Contractor | Retention release | Release was one click with no approver | Medium | Approval | — | No | Yes | Fixed
G-26 | Vendor | Offboarding | Inactive vendor kept portal access | Low | Status | Session not re-checked | No | Yes | Fixed
G-27 | Vendor | Registration | Internal registration could be submitted with zero documents | Low | Validation | — | No | Yes | Fixed
G-28 | Vendor | Hold | Status stayed 'On Hold' after the release date | Low | Status | No expiry job | No | Yes | Fixed
N-01 | Vendor | Vendor Registry | ?open= deep links from other pages didn't open the vendor | Low | Navigation | Local state instead of query | No | Yes | Fixed
N-02 | All | Toasts | Error messages vanished in 2.6 s — too fast to read gate messages | Low | UI | Fixed timeout | Yes | Yes | Passed
N-03 | Vendor | Status & flags | 'Enabled' checkbox could re-activate a blacklisted or pending vendor | Medium | Status | Unguarded toggle | No | Yes | Fixed
N-04 | Vendor | Blacklist | Anyone could remove a vendor from the blacklist | Medium | Approval | — | Yes | Yes | Passed
N-05 | Contractor | Contract | 'Extend / renew' changed the end date without approval | Medium | Approval | Direct edit | No | Yes | Fixed
N-06 | Contractor | Contract drawer | Change-order approve in the drawer bypassed the Approval Management path (duplicate flow) | Medium | Approval | Duplicate logic | No | Yes | Fixed
N-07 | Vendor | PO drawer | PO 'Approve & issue' in the drawer had no role check (duplicate flow) | Medium | Approval | Duplicate logic | No | Yes | Fixed
N-08 | Contractor | RA bill from claim | Rejecting a claim-based bill left the claim 'Verified' and its measurements billable — double count when the claim is revised | High | Exception Handling | Missing reversal | Yes | Yes | Passed
N-09 | Contractor | Create work order | Cancelled WOs counted against contract headroom | Low | Data Mapping | — | No | Yes | Fixed
N-10 | Contractor | Retention releases | No requester / approver visible | Low | UI | — | No | Yes | Fixed
N-11 | Contractor | Measurement drawer | 'Ready to bill' ignored inspection | Low | Status | — | No | Yes | Fixed
N-12 | Contractor | Final bill | Voided measurements counted as unsigned and blocked the final bill (found in retest) | Medium | Exception Handling | Filter missed voided | No | Yes | Fixed
N-13 | All | List filters | Status filters lacked the new statuses | Low | Fields | — | Yes | Yes | Passed
N-14 | All | Procurement Settings | 'Your role (demo)' setting was disconnected from who approves | Low | Fields | — | No | Yes | Fixed
N-15 | Vendor | Payment run | Payer could be the bill's enterer or approver | High | Approval | — | No | Yes | Fixed
N-16 | Contractor | JMS sign-off | Anyone could sign a JMS | Medium | Approval | — | No | Yes | Fixed
N-17 | Contractor | Labour rates | Rate approval had no role check | Low | Approval | — | Yes | Yes | Passed
N-18 | Vendor | Invoices | A rejected vendor invoice would still count as payable | Medium | Data Mapping | — | No | Yes | Fixed
N-19 | Vendor & Contractor | Award | Non-L1 awards needed no justification | Low | Validation | — | No | Yes | Fixed

## Fix Tracker
Gap | Fix applied | Files | Test IDs | Status
G-01 | Approval checklist on every stage; final (Finance) stage blocked until blocking documents are verified, blocking insurance is on file, qualification ≥ 70 and (spend-authorized) a bank account exists. Finance Controller may approve with override + mandatory reason (logged on the stage). | 04-workflow, 11-vendor-approval, 14-public-approvals | G-01, G-01b, V02–V04 | Fixed
G-02 | Tier is read-only; 'Request spend authorization' (checks bank, verified documents, qualification) → Finance Controller approves in Approval Management (not the requester). Downgrade needs Procurement Head. | 04-workflow, 10-vendor-registry, 11-vendor-approval, 14-public-approvals | G-02 | Fixed
G-03 | Draft → Submitted → Legal → Finance → Approved → Sign & activate (Procurement Head / PM, not an approver) with contractor eligibility and performance-BG check. Rejected contracts return to the owner for edit + resubmit. | 20a-contract-detail, 04-workflow, 14-public-approvals, 01-logic | G-03a, G-03b, C07 | Fixed
G-04 | Contract picker hides blocked contractors; woIssueBlockers() checks contract signed/active, contractor Active + spend-authorized + not blocked + compliance gate on Issue and Resume | 21-workorders-mb, 04-workflow | G-04 | Fixed
G-05 | Open sessions end for Inactive / Blacklisted / Rejected / disabled users; On Hold (All) = read-only (no quotes, WO acceptance, claims, attendance, invoices); Invoices hold stops claims + invoices | 15-supplier-portal, 16-rfq | G-05, V13 | Fixed
G-06 | RA bill and claim verification blocked when cumulative quantity exceeds WO quantity (which approved change orders raise); message routes the user to a change order | 22-ra-bills, 17-contractor | G-06 | Fixed
G-07 | Change-order quantity lines (WO line + extra qty, or new item); approval raises the WO quantity / adds the item | 20a-contract-detail, 14-public-approvals | G-07, C12 | Fixed
G-08 | 'Award as contract' for contractor awards: draft contract with the awarded lines as contract BOQ, rfqId and award note carried over | 16-rfq, 04-workflow | G-08/G-20, C06 | Fixed
G-09 | WBS catalogue per project; WBS mandatory on WOs; contract BOQ lines; WO lines loaded from contract BOQ (boqRef) with over-order check; contract BOQ position; Cost-by-WBS view (budget → committed → executed → billed → paid) | 04-workflow, 20a-contract-detail, 21-workorders-mb, 26-execution, 27-seed-workflow | G-09, G-09b, C08 | Fixed
G-10 | New 'Close-out & Handover' page: punch list (contractor rectifies in portal, engineer verifies), final inspection (fail → snags), handover certificate (print), final bill (stops further billing), DLP from handover, closure | 28-closeout, 22-ra-bills, 90-nav, 15-supplier-portal | G-10a–e, C15, C16 | Fixed
G-11 | 13-point closure checklist (WOs done, JMS, unbilled, claims, COs, bills paid, punch/NCR, handover, final bill, DLP, retention, advance, guarantees); closing freezes WOs and the measurement book | 04-workflow, 20a-contract-detail | G-11, G-11b, G-11c, C18 | Fixed
G-12 | Inspection per measurement (Pass / Fail → NCR); NCR rework → re-inspection loop (contractor can mark rework in portal); only passed entries are billable; open NCR blocks QS certification; claim verification requires inspection confirmation | 26-execution, 21-workorders-mb, 22-ra-bills, 17-contractor, 19-portal-details | G-12a–c, C10 | Fixed
G-13 | Personas with roles ('Acting as' switcher on every page); each step requires its role; the same person can't act twice on a record or approve their own submission; payment by Accounts / Finance only and not by the bill's enterer / approver | 04-workflow + 11 other files | G-13a–d, V04, V08, V11, C11 | Fixed
G-14 | Sourcing gate: Warn at RFQ invite, Stop at PO / contract / award (configurable in Procurement Settings) | 04-workflow, 12-procurement, 16-rfq | G-14, G-08/G-20 | Fixed
G-15 | Equipment tab on contractor record; deployment / release on WO; expired fitness blocks deployment | 26-execution, 10-vendor-registry, 27-seed-workflow | G-15, G-15b, C09 | Fixed
G-16 | Material issue register on WO; automatic recovery in next RA bill (linked); released again if the bill is rejected | 26-execution, 22-ra-bills | G-16, G-16b, C11 | Fixed
G-17 | Daily progress report on WO and in portal (manpower, work, hindrance, weather; no duplicate / future dates); Performance → Daily progress tab | 26-execution, 19-portal-details, 23-labor-performance | G-17, C09 | Fixed
G-18 | Portal 'Submit invoice' against billable PO quantity with copy + duplicate check → AP review (accept / reject with reason) → payment run; rejected invoices not payable, vendor can resubmit | 28-closeout, 15-supplier-portal, 12-procurement, 14-public-approvals, 01-logic | G-18a–d, V10 | Fixed
G-19 | Duplicate bill number per vendor blocked (internal entry and portal; rejected invoices excluded) | 12-procurement, 28-closeout | G-19, G-18b | Fixed
G-20 | Mandatory award recommendation (hint when not L1); PO approver ≠ awarder; contract awards go through Legal → Finance | 16-rfq, 04-workflow | G-08/G-20, V07, V08 | Fixed
G-21 | Terminate contract (reason; short-closes open WOs); WO Suspend / Resume / Short-close / Cancel with reason and role | 04-workflow, 20a-contract-detail, 21-workorders-mb | G-21 | Fixed
G-22 | BG register (performance / advance / retention): add, extend, return, encash; expiry status and reminders; PBG before signing; retention BG for early release | 20a-contract-detail, 20-contracts, 04-workflow, 22-ra-bills | G-22, C07, C17 | Fixed
G-23 | Contractor agrees / disputes each measurement in the portal; engineer countersigns only with portal agreement or a confirmed paper JMS | 26-execution, 19-portal-details, 21-workorders-mb | G-23, C10 | Fixed
G-24 | Checklist must be complete before the contractor's first WO is issued (setting) | 04-workflow, 21-workorders-mb | G-24, C04 | Fixed
G-25 | Request → Finance Controller approval → Accounts release (three different people); after-DLP / completion releases need the handover certificate; BG-backed release needs a live retention BG | 04-workflow, 22-ra-bills, 14-public-approvals | G-25a, G-25b, G-10a, C17 | Fixed
G-26 | Portal access ends immediately for Inactive / Blacklisted / Rejected | 15-supplier-portal | G-26, V14 | Fixed
G-27 | Required documents must be uploaded before submit (internal form and drawer; setting) | 04-workflow, 10-vendor-registry, 11-vendor-approval | G-27, G-27b, V01 | Fixed
G-28 | Daily sweep ends expired holds (vendor back to Active, audit entry) | 04-workflow, 00-core | G-28 | Fixed
N-01 | Registry uses the shared deep-link hook | 10-vendor-registry | G-02 (opens via link) | Fixed
N-02 | Errors / warnings stay 5.5 s, wrap, amber and blue styles | 00-core | all suites | Passed
N-03 | Hidden for approval states and blacklisted vendors | 10-vendor-registry | V14 | Fixed
N-04 | Procurement Head only | 10-vendor-registry | regression | Passed
N-05 | Extension is a time change order approved by the Project Manager | 20a-contract-detail | G-07 | Fixed
N-06 | One decideChangeOrder() with role + SoD used everywhere | 20a-contract-detail, 14-public-approvals | G-07, C12 | Fixed
N-07 | One decidePo() with role, SoD and vendor eligibility | 04-workflow, 12-procurement, 14-public-approvals | V08 | Fixed
N-08 | Rejection voids the claim's measurements and returns the claim to the contractor | 22-ra-bills | regression | Passed
N-09 | Cancelled excluded; short-closed counts measured value | 21-workorders-mb | C08 | Fixed
N-10 | Requested/approved-by column, full status set | 22-ra-bills | G-25b | Fixed
N-11 | Shows inspection state and NCR block | 21-workorders-mb | G-12a | Fixed
N-12 | Voided entries excluded from JMS counts and closure checks | 22-ra-bills, 04-workflow | G-10d | Fixed
N-13 | Filter option lists extended (contract, WO, release, NCR, punch, BG, invoice review) | 03-extensions, 12-procurement | regression | Passed
N-14 | Replaced by the persona shown in 'Acting as' | 12-procurement | G-13c | Fixed
N-15 | SoD check in the payment run | 12-procurement | V11, C11 | Fixed
N-16 | Site Engineer role | 21-workorders-mb | C10 | Fixed
N-17 | Procurement Head, not the requester | 23-labor-performance | regression (e2e) | Passed
N-18 | Payable 0 and status 'Rejected' | 01-logic | G-18d | Fixed
N-19 | Recommendation mandatory; hint when not L1 | 16-rfq | G-08/G-20 | Fixed

## Test Cases
Suite | Test ID | Scenario

## Test Results
Suite | Test ID | Scenario | Actual result | Result