## Summary
NebullaOne — Vendor & Contract module UAT
795 checks · 756 pass · 0 fail · 0 warn · 39 info · 0 issues found and fixed during UAT
Every page of both modules, the supplier portal (contractor and goods supplier) and the public pages; then a 1280 px laptop layout pass.
Module | Page / area | Checks | Pass | Fail | Warn | Info | Result
Navigation | Sidebar | 30 | 30 | 0 | 0 | 0 | PASS
Vendor Management | Overview | 5 | 4 | 0 | 0 | 1 | PASS
Vendor Management | Vendor Registry | 38 | 37 | 0 | 0 | 1 | PASS
Vendor Management | Vendor Approvals | 38 | 37 | 0 | 0 | 1 | PASS
Vendor Management | Compliance Center | 62 | 61 | 0 | 0 | 1 | PASS
Vendor Management | Purchase Requisitions | 16 | 15 | 0 | 0 | 1 | PASS
Vendor Management | RFQ & Quotations | 16 | 15 | 0 | 0 | 1 | PASS
Vendor Management | Blanket Orders | 16 | 15 | 0 | 0 | 1 | PASS
Vendor Management | Purchase Orders | 17 | 16 | 0 | 0 | 1 | PASS
Vendor Management | Invoices & Payments | 32 | 30 | 0 | 0 | 2 | PASS
Vendor Management | Requalification | 6 | 5 | 0 | 0 | 1 | PASS
Vendor Management | Vendor Scorecard | 36 | 34 | 0 | 0 | 2 | PASS
Vendor Management | Vendor Portal | 48 | 47 | 0 | 0 | 1 | PASS
Vendor Management | Procurement Settings | 9 | 8 | 0 | 0 | 1 | PASS
Contract & Labor | Overview | 5 | 4 | 0 | 0 | 1 | PASS
Contract & Labor | Contractor Onboarding | 16 | 15 | 0 | 0 | 1 | PASS
Contract & Labor | Contracts | 16 | 15 | 0 | 0 | 1 | PASS
Contract & Labor | Work Orders | 17 | 16 | 0 | 0 | 1 | PASS
Contract & Labor | Labour Attendance | 21 | 18 | 0 | 0 | 3 | PASS
Contract & Labor | Measurement Book | 39 | 37 | 0 | 0 | 2 | PASS
Contract & Labor | RA Bills & Certification | 27 | 26 | 0 | 0 | 1 | PASS
Contract & Labor | Retention & Deductions | 40 | 39 | 0 | 0 | 1 | PASS
Contract & Labor | Labor Rate Management | 50 | 48 | 0 | 0 | 2 | PASS
Contract & Labor | Performance & Progress | 38 | 35 | 0 | 0 | 3 | PASS
Contract & Labor | Close-out & Handover | 13 | 12 | 0 | 0 | 1 | PASS
Contract & Labor | Final Settlement | 13 | 12 | 0 | 0 | 1 | PASS
Contract & Labor | DLP & Warranty | 12 | 11 | 0 | 0 | 1 | PASS
Contract & Labor | Contractor Release | 4 | 3 | 0 | 0 | 1 | PASS
Contract & Labor | Termination & Final Account | 7 | 6 | 0 | 0 | 1 | PASS
Administration | Audit Log | 13 | 11 | 0 | 0 | 2 | PASS
Approvals | Approval Management | 22 | 21 | 0 | 0 | 1 | PASS
Supplier portal | Contractor (Shree Balaji) | 20 | 20 | 0 | 0 | 0 | PASS
Supplier portal | Goods supplier (Deccan Steel) | 19 | 19 | 0 | 0 | 0 | PASS
Public pages | No sign-in | 4 | 4 | 0 | 0 | 0 | PASS
Layout | Laptop 1280 × 720 | 30 | 30 | 0 | 0 | 0 | PASS

## Issues
Page | Area | Check | Status | What was seen | Action

## All checks
Module | Page | Area | Check | Result | Detail
Navigation | Sidebar | Menu | Vendor Management → Overview | PASS | page title is "Vendor Overview"
Navigation | Sidebar | Menu | Vendor Management → Vendor Registry | PASS
Navigation | Sidebar | Menu | Vendor Management → Vendor Approvals | PASS
Navigation | Sidebar | Menu | Vendor Management → Compliance Center | PASS
Navigation | Sidebar | Menu | Vendor Management → Purchase Requisitions | PASS
Navigation | Sidebar | Menu | Vendor Management → RFQ & Quotations | PASS
Navigation | Sidebar | Menu | Vendor Management → Blanket Orders | PASS
Navigation | Sidebar | Menu | Vendor Management → Purchase Orders | PASS
Navigation | Sidebar | Menu | Vendor Management → Invoices & Payments | PASS
Navigation | Sidebar | Menu | Vendor Management → Requalification | PASS
Navigation | Sidebar | Menu | Vendor Management → Vendor Scorecard | PASS
Navigation | Sidebar | Menu | Vendor Management → Vendor Portal | PASS
Navigation | Sidebar | Menu | Vendor Management → Procurement Settings | PASS
Navigation | Sidebar | Menu | Contract & Labor → Overview | PASS | page title is "Contract & Labour Overview"
Navigation | Sidebar | Menu | Contract & Labor → Contractor Onboarding | PASS
Navigation | Sidebar | Menu | Contract & Labor → Contracts | PASS
Navigation | Sidebar | Menu | Contract & Labor → Work Orders | PASS
Navigation | Sidebar | Menu | Contract & Labor → Labour Attendance | PASS
Navigation | Sidebar | Menu | Contract & Labor → Measurement Book | PASS
Navigation | Sidebar | Menu | Contract & Labor → RA Bills & Certification | PASS
Navigation | Sidebar | Menu | Contract & Labor → Retention & Deductions | PASS | page title is "Retention, Deductions & Advances"
Navigation | Sidebar | Menu | Contract & Labor → Labor Rate Management | PASS | page title is "Labour Rate Management"
Navigation | Sidebar | Menu | Contract & Labor → Performance & Progress | PASS
Navigation | Sidebar | Menu | Contract & Labor → Close-out & Handover | PASS
Navigation | Sidebar | Menu | Contract & Labor → Final Settlement | PASS
Navigation | Sidebar | Menu | Contract & Labor → DLP & Warranty | PASS
Navigation | Sidebar | Menu | Contract & Labor → Contractor Release | PASS
Navigation | Sidebar | Menu | Contract & Labor → Termination & Final Account | PASS
Navigation | Sidebar | Menu | Administration → Audit Log | PASS
Navigation | Sidebar | Menu | Approvals → Approval Management | PASS
Vendor Management | Overview | Page | loads without script errors | PASS | 733 ms
Vendor Management | Overview | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Overview | Page | no sideways scroll of the page | PASS
Vendor Management | Overview | Header | button "Last 90 days" | PASS | menu / action
Vendor Management | Overview | Page | summary | INFO | 6 cards, 0 tabs, 1 header buttons, loaded in 733 ms
Vendor Management | Vendor Registry | Page | loads without script errors | PASS | 746 ms
Vendor Management | Vendor Registry | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Vendor Registry | Page | no sideways scroll of the page | PASS
Vendor Management | Vendor Registry | Form | button "Invite vendor" → "Invite vendor to register" opens | PASS
Vendor Management | Vendor Registry | Form | "Invite vendor to register" — Send invitation disabled until the form is complete | PASS | 5 fields, 2 required
Vendor Management | Vendor Registry | Form | "Invite vendor to register" closes with Esc | PASS
Vendor Management | Vendor Registry | Form | button "Register vendor" → "Register vendor" opens | PASS
Vendor Management | Vendor Registry | Form | "Register vendor" — Submit for approval on the untouched form | PASS | Blocked: validation message shown
Vendor Management | Vendor Registry | Form | "Register vendor" closes with Esc | PASS
Vendor Management | Vendor Registry | Tab | tab "Vendors" opens | PASS
Vendor Management | Vendor Registry | List | tab "Vendors": footer count matches the rows | PASS | footer 13 vendors, rows 13
Vendor Management | Vendor Registry | List | tab "Vendors": sort on all 8 columns | PASS
Vendor Management | Vendor Registry | List | tab "Vendors": search "Shree" finds rows | PASS | 1 rows
Vendor Management | Vendor Registry | List | tab "Vendors": search with no match shows "No matches" | PASS
Vendor Management | Vendor Registry | Filters | tab "Vendors": panel opens (4 sections, 17 chips) | PASS
Vendor Management | Vendor Registry | Filters | tab "Vendors": apply one chip | PASS | 13 → 3 rows
Vendor Management | Vendor Registry | Filters | tab "Vendors": Reset restores all rows | PASS | 13 of 13
Vendor Management | Vendor Registry | List | tab "Vendors": export to CSV | PASS | vendor-master-2026-10-03.csv · 13 rows
Vendor Management | Vendor Registry | List | tab "Vendors": Customize columns opens | PASS
Vendor Management | Vendor Registry | Record | tab "Vendors": drawer "Shree Balaji Infra Contractors" opens | PASS
Vendor Management | Vendor Registry | Record | tab "Vendors": drawer tab "Overview" | PASS
Vendor Management | Vendor Registry | Record | tab "Vendors": drawer tab "Status & flags" | PASS
Vendor Management | Vendor Registry | Record | tab "Vendors": drawer tab "Documents 9/9" | PASS
Vendor Management | Vendor Registry | Record | tab "Vendors": drawer tab "Bank 2" | PASS
Vendor Management | Vendor Registry | Record | tab "Vendors": drawer tab "Qualification" | PASS
Vendor Management | Vendor Registry | Record | tab "Vendors": drawer tab "Equipment 3" | PASS
Vendor Management | Vendor Registry | Record | tab "Vendors": drawer tab "Approvals" | PASS
Vendor Management | Vendor Registry | Tab | tab "Invitations" opens | PASS
Vendor Management | Vendor Registry | List | tab "Invitations": footer count matches the rows | PASS | footer 2 invitations, rows 2
Vendor Management | Vendor Registry | List | tab "Invitations": sort on all 6 columns | PASS
Vendor Management | Vendor Registry | List | tab "Invitations": search "info@bharatformwork.in" finds rows | PASS | 1 rows
Vendor Management | Vendor Registry | List | tab "Invitations": search with no match shows "No matches" | PASS
Vendor Management | Vendor Registry | Filters | tab "Invitations": panel opens (2 sections, 3 chips) | PASS
Vendor Management | Vendor Registry | Filters | tab "Invitations": apply one chip | PASS | 2 → 1 rows
Vendor Management | Vendor Registry | Filters | tab "Invitations": Reset restores all rows | PASS | 2 of 2
Vendor Management | Vendor Registry | List | tab "Invitations": export to CSV | PASS | invitations-2026-10-03.csv · 2 rows
Vendor Management | Vendor Registry | Record | tab "Invitations": drawer "Bharat Formwork Systems" opens | PASS
Vendor Management | Vendor Registry | Page | summary | INFO | 0 cards, 2 tabs, 2 header buttons, loaded in 746 ms
Vendor Management | Vendor Approvals | Page | loads without script errors | PASS | 720 ms
Vendor Management | Vendor Approvals | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Vendor Approvals | Page | no sideways scroll of the page | PASS
Vendor Management | Vendor Approvals | Tab | tab "Approval queue" opens | PASS
Vendor Management | Vendor Approvals | List | tab "Approval queue": footer count matches the rows | PASS | footer 2 vendors, rows 2
Vendor Management | Vendor Approvals | List | tab "Approval queue": sort on all 4 columns | PASS
Vendor Management | Vendor Approvals | List | tab "Approval queue": search "Services" finds rows | PASS | 1 rows
Vendor Management | Vendor Approvals | List | tab "Approval queue": search with no match shows "No matches" | PASS
Vendor Management | Vendor Approvals | Filters | tab "Approval queue": panel opens (3 sections, 15 chips) | PASS
Vendor Management | Vendor Approvals | Filters | tab "Approval queue": apply one chip | PASS | 2 → 0 rows
Vendor Management | Vendor Approvals | Filters | tab "Approval queue": Reset restores all rows | PASS | 2 of 2
Vendor Management | Vendor Approvals | List | tab "Approval queue": export to CSV | PASS | vendors-2026-10-03.csv · 2 rows
Vendor Management | Vendor Approvals | Record | tab "Approval queue": drawer "Greenline Solar EPC" opens | PASS
Vendor Management | Vendor Approvals | Record | tab "Approval queue": drawer tab "Overview" | PASS
Vendor Management | Vendor Approvals | Record | tab "Approval queue": drawer tab "Status & flags" | PASS
Vendor Management | Vendor Approvals | Record | tab "Approval queue": drawer tab "Documents 8/9" | PASS
Vendor Management | Vendor Approvals | Record | tab "Approval queue": drawer tab "Bank 1" | PASS
Vendor Management | Vendor Approvals | Record | tab "Approval queue": drawer tab "Qualification" | PASS
Vendor Management | Vendor Approvals | Record | tab "Approval queue": drawer tab "Equipment" | PASS
Vendor Management | Vendor Approvals | Record | tab "Approval queue": drawer tab "Approvals" | PASS
Vendor Management | Vendor Approvals | Tab | tab "Qualification results" opens | PASS
Vendor Management | Vendor Approvals | List | tab "Qualification results": footer count matches the rows | PASS | footer 6 vendors, rows 6
Vendor Management | Vendor Approvals | List | tab "Qualification results": sort on all 5 columns | PASS
Vendor Management | Vendor Approvals | List | tab "Qualification results": search "Contractor" finds rows | PASS | 6 rows
Vendor Management | Vendor Approvals | List | tab "Qualification results": search with no match shows "No matches" | PASS
Vendor Management | Vendor Approvals | Filters | tab "Qualification results": panel opens (3 sections, 11 chips) | PASS
Vendor Management | Vendor Approvals | Filters | tab "Qualification results": apply one chip | PASS | 6 → 3 rows
Vendor Management | Vendor Approvals | Filters | tab "Qualification results": Reset restores all rows | PASS | 6 of 6
Vendor Management | Vendor Approvals | List | tab "Qualification results": export to CSV | PASS | vendors-2026-10-03.csv · 6 rows
Vendor Management | Vendor Approvals | Record | tab "Qualification results": drawer "Shree Balaji Infra Contractors" opens | PASS
Vendor Management | Vendor Approvals | Record | tab "Qualification results": drawer tab "Overview" | PASS
Vendor Management | Vendor Approvals | Record | tab "Qualification results": drawer tab "Status & flags" | PASS
Vendor Management | Vendor Approvals | Record | tab "Qualification results": drawer tab "Documents 9/9" | PASS
Vendor Management | Vendor Approvals | Record | tab "Qualification results": drawer tab "Bank 2" | PASS
Vendor Management | Vendor Approvals | Record | tab "Qualification results": drawer tab "Qualification" | PASS
Vendor Management | Vendor Approvals | Record | tab "Qualification results": drawer tab "Equipment 3" | PASS
Vendor Management | Vendor Approvals | Record | tab "Qualification results": drawer tab "Approvals" | PASS
Vendor Management | Vendor Approvals | Page | summary | INFO | 0 cards, 2 tabs, 0 header buttons, loaded in 720 ms
Vendor Management | Compliance Center | Page | loads without script errors | PASS | 752 ms
Vendor Management | Compliance Center | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Compliance Center | Page | no sideways scroll of the page | PASS
Vendor Management | Compliance Center | Header | button "Send due reminders" | PASS | 7 reminders e-mailed
Vendor Management | Compliance Center | Tab | tab "Vendors" opens | PASS
Vendor Management | Compliance Center | List | tab "Vendors": footer count matches the rows | PASS | footer 13 vendors, rows 13
Vendor Management | Compliance Center | List | tab "Vendors": sort on all 2 columns | PASS
Vendor Management | Compliance Center | List | tab "Vendors": search "Compliant" finds rows | PASS | 12 rows
Vendor Management | Compliance Center | List | tab "Vendors": search with no match shows "No matches" | PASS
Vendor Management | Compliance Center | Filters | tab "Vendors": panel opens (3 sections, 12 chips) | PASS
Vendor Management | Compliance Center | Filters | tab "Vendors": apply one chip | PASS | 13 → 2 rows
Vendor Management | Compliance Center | Filters | tab "Vendors": Reset restores all rows | PASS | 13 of 13
Vendor Management | Compliance Center | List | tab "Vendors": export to CSV | PASS | vendors-2026-10-03.csv · 13 rows
Vendor Management | Compliance Center | Record | tab "Vendors": drawer "Shree Balaji Infra Contractors" opens | PASS
Vendor Management | Compliance Center | Record | tab "Vendors": drawer tab "Checklist" | PASS
Vendor Management | Compliance Center | Record | tab "Vendors": drawer tab "Documents" | PASS
Vendor Management | Compliance Center | Record | tab "Vendors": drawer tab "Insurance" | PASS
Vendor Management | Compliance Center | Record | tab "Vendors": drawer tab "Reminders & history" | PASS
Vendor Management | Compliance Center | Tab | tab "Expiring & expired" opens | PASS
Vendor Management | Compliance Center | List | tab "Expiring & expired": footer count matches the rows | PASS | footer 4 items, rows 4
Vendor Management | Compliance Center | List | tab "Expiring & expired": sort on all 3 columns | PASS
Vendor Management | Compliance Center | List | tab "Expiring & expired": search "Workmen" finds rows | PASS | 4 rows
Vendor Management | Compliance Center | List | tab "Expiring & expired": search with no match shows "No matches" | PASS
Vendor Management | Compliance Center | Filters | tab "Expiring & expired": panel opens (3 sections, 4 chips) | PASS
Vendor Management | Compliance Center | Filters | tab "Expiring & expired": apply one chip | PASS | 4 → 2 rows
Vendor Management | Compliance Center | Filters | tab "Expiring & expired": Reset restores all rows | PASS | 4 of 4
Vendor Management | Compliance Center | List | tab "Expiring & expired": export to CSV | PASS | items-2026-10-03.csv · 4 rows
Vendor Management | Compliance Center | Record | tab "Expiring & expired": drawer "Sai Earthmovers" opens | PASS
Vendor Management | Compliance Center | Record | tab "Expiring & expired": drawer tab "Checklist" | PASS
Vendor Management | Compliance Center | Record | tab "Expiring & expired": drawer tab "Documents" | PASS
Vendor Management | Compliance Center | Record | tab "Expiring & expired": drawer tab "Insurance" | PASS
Vendor Management | Compliance Center | Record | tab "Expiring & expired": drawer tab "Reminders & history 2" | PASS
Vendor Management | Compliance Center | Tab | tab "Verification queue" opens | PASS
Vendor Management | Compliance Center | List | tab "Verification queue": footer count matches the rows | PASS | footer 2 uploads, rows 2
Vendor Management | Compliance Center | List | tab "Verification queue": sort on all 2 columns | PASS
Vendor Management | Compliance Center | List | tab "Verification queue": search "Safety" finds rows | PASS | 1 rows
Vendor Management | Compliance Center | List | tab "Verification queue": search with no match shows "No matches" | PASS
Vendor Management | Compliance Center | Filters | tab "Verification queue": panel opens (2 sections, 2 chips) | PASS
Vendor Management | Compliance Center | Filters | tab "Verification queue": apply one chip | PASS | 2 → 2 rows
Vendor Management | Compliance Center | Filters | tab "Verification queue": Reset restores all rows | PASS | 2 of 2
Vendor Management | Compliance Center | List | tab "Verification queue": export to CSV | PASS | uploads-2026-10-03.csv · 2 rows
Vendor Management | Compliance Center | Record | tab "Verification queue": drawer "Greenline Solar EPC" opens | PASS
Vendor Management | Compliance Center | Record | tab "Verification queue": drawer tab "Checklist" | PASS
Vendor Management | Compliance Center | Record | tab "Verification queue": drawer tab "Documents" | PASS
Vendor Management | Compliance Center | Record | tab "Verification queue": drawer tab "Insurance" | PASS
Vendor Management | Compliance Center | Record | tab "Verification queue": drawer tab "Reminders & history 2" | PASS
Vendor Management | Compliance Center | Tab | tab "Insurance" opens | PASS
Vendor Management | Compliance Center | List | tab "Insurance": footer count matches the rows | PASS | footer 9 requirements, rows 9
Vendor Management | Compliance Center | List | tab "Insurance": sort on all 3 columns | PASS
Vendor Management | Compliance Center | List | tab "Insurance": search "Workmen" finds rows | PASS | 7 rows
Vendor Management | Compliance Center | List | tab "Insurance": search with no match shows "No matches" | PASS
Vendor Management | Compliance Center | Filters | tab "Insurance": panel opens (3 sections, 12 chips) | PASS
Vendor Management | Compliance Center | Filters | tab "Insurance": apply one chip | PASS | 9 → 7 rows
Vendor Management | Compliance Center | Filters | tab "Insurance": Reset restores all rows | PASS | 9 of 9
Vendor Management | Compliance Center | List | tab "Insurance": export to CSV | PASS | requirements-2026-10-03.csv · 9 rows
Vendor Management | Compliance Center | Record | tab "Insurance": drawer "Shree Balaji Infra Contractors" opens | PASS
Vendor Management | Compliance Center | Record | tab "Insurance": drawer tab "Checklist" | PASS
Vendor Management | Compliance Center | Record | tab "Insurance": drawer tab "Documents" | PASS
Vendor Management | Compliance Center | Record | tab "Insurance": drawer tab "Insurance" | PASS
Vendor Management | Compliance Center | Record | tab "Insurance": drawer tab "Reminders & history" | PASS
Vendor Management | Compliance Center | Tab | tab "Requirements" opens | PASS
Vendor Management | Compliance Center | Page | summary | INFO | 0 cards, 5 tabs, 1 header buttons, loaded in 752 ms
Vendor Management | Purchase Requisitions | Page | loads without script errors | PASS | 775 ms
Vendor Management | Purchase Requisitions | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Purchase Requisitions | Page | no sideways scroll of the page | PASS
Vendor Management | Purchase Requisitions | Form | button "New requisition" → "New purchase requisition" opens | PASS
Vendor Management | Purchase Requisitions | Form | "New purchase requisition" — Submit disabled until the form is complete | PASS | 11 fields, 3 required
Vendor Management | Purchase Requisitions | Form | "New purchase requisition" closes with Esc | PASS
Vendor Management | Purchase Requisitions | List | list: footer count matches the rows | PASS | footer 2 requisitions, rows 2
Vendor Management | Purchase Requisitions | List | list: sort on all 5 columns | PASS
Vendor Management | Purchase Requisitions | List | list: search "Purchase" finds rows | PASS | 1 rows
Vendor Management | Purchase Requisitions | List | list: search with no match shows "No matches" | PASS
Vendor Management | Purchase Requisitions | Filters | list: panel opens (3 sections, 21 chips) | PASS
Vendor Management | Purchase Requisitions | Filters | list: apply one chip | PASS | 2 → 1 rows
Vendor Management | Purchase Requisitions | Filters | list: Reset restores all rows | PASS | 2 of 2
Vendor Management | Purchase Requisitions | List | list: export to CSV | PASS | requisitions-2026-10-03.csv · 2 rows
Vendor Management | Purchase Requisitions | Record | list: drawer "MR-001 — Purchase" opens | PASS
Vendor Management | Purchase Requisitions | Page | summary | INFO | 0 cards, 0 tabs, 1 header buttons, loaded in 775 ms
Vendor Management | RFQ & Quotations | Page | loads without script errors | PASS | 756 ms
Vendor Management | RFQ & Quotations | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | RFQ & Quotations | Page | no sideways scroll of the page | PASS
Vendor Management | RFQ & Quotations | Form | button "New RFQ" → "New request for quotation" opens | PASS
Vendor Management | RFQ & Quotations | Form | "New request for quotation" — Save & compose e-mail disabled until the form is complete | PASS | 16 fields, 1 required
Vendor Management | RFQ & Quotations | Form | "New request for quotation" closes with Esc | PASS
Vendor Management | RFQ & Quotations | List | list: footer count matches the rows | PASS | footer 3 RFQs, rows 3
Vendor Management | RFQ & Quotations | List | list: sort on all 5 columns | PASS
Vendor Management | RFQ & Quotations | List | list: search "steel" finds rows | PASS | 1 rows
Vendor Management | RFQ & Quotations | List | list: search with no match shows "No matches" | PASS
Vendor Management | RFQ & Quotations | Filters | list: panel opens (4 sections, 17 chips) | PASS
Vendor Management | RFQ & Quotations | Filters | list: apply one chip | PASS | 3 → 1 rows
Vendor Management | RFQ & Quotations | Filters | list: Reset restores all rows | PASS | 3 of 3
Vendor Management | RFQ & Quotations | List | list: export to CSV | PASS | RFQs-2026-10-03.csv · 3 rows
Vendor Management | RFQ & Quotations | Record | list: drawer "TMT steel Fe500D — 120 MT" opens | PASS
Vendor Management | RFQ & Quotations | Page | summary | INFO | 0 cards, 0 tabs, 1 header buttons, loaded in 756 ms
Vendor Management | Blanket Orders | Page | loads without script errors | PASS | 767 ms
Vendor Management | Blanket Orders | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Blanket Orders | Page | no sideways scroll of the page | PASS
Vendor Management | Blanket Orders | Form | button "New blanket order" → "New blanket order" opens | PASS
Vendor Management | Blanket Orders | Form | "New blanket order" — Save agreement disabled until the form is complete | PASS | 12 fields, 2 required
Vendor Management | Blanket Orders | Form | "New blanket order" closes with Esc | PASS
Vendor Management | Blanket Orders | List | list: footer count matches the rows | PASS | footer 1 agreements, rows 1
Vendor Management | Blanket Orders | List | list: sort on all 3 columns | PASS
Vendor Management | Blanket Orders | List | list: search "UltraBuild" finds rows | PASS | 1 rows
Vendor Management | Blanket Orders | List | list: search with no match shows "No matches" | PASS
Vendor Management | Blanket Orders | Filters | list: panel opens (2 sections, 6 chips) | PASS
Vendor Management | Blanket Orders | Filters | list: apply one chip | PASS | 1 → 0 rows
Vendor Management | Blanket Orders | Filters | list: Reset restores all rows | PASS | 1 of 1
Vendor Management | Blanket Orders | List | list: export to CSV | PASS | agreements-2026-10-03.csv · 1 rows
Vendor Management | Blanket Orders | Record | list: drawer "OPC 53 cement — annual rate agreement FY 26-27" opens | PASS
Vendor Management | Blanket Orders | Page | summary | INFO | 0 cards, 0 tabs, 1 header buttons, loaded in 767 ms
Vendor Management | Purchase Orders | Page | loads without script errors | PASS | 759 ms
Vendor Management | Purchase Orders | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Purchase Orders | Page | no sideways scroll of the page | PASS
Vendor Management | Purchase Orders | Form | button "New PO" → "New purchase order" opens | PASS
Vendor Management | Purchase Orders | Form | "New purchase order" — Create & issue disabled until the form is complete | PASS | 6 fields, 1 required
Vendor Management | Purchase Orders | Form | "New purchase order" closes with Esc | PASS
Vendor Management | Purchase Orders | List | list: footer count matches the rows | PASS | footer 3 purchase orders, rows 3
Vendor Management | Purchase Orders | List | list: sort on all 5 columns | PASS
Vendor Management | Purchase Orders | List | list: search "Partially" finds rows | PASS | 1 rows
Vendor Management | Purchase Orders | List | list: search with no match shows "No matches" | PASS
Vendor Management | Purchase Orders | Filters | list: panel opens (4 sections, 18 chips) | PASS
Vendor Management | Purchase Orders | Filters | list: apply one chip | PASS | 3 → 0 rows
Vendor Management | Purchase Orders | Filters | list: Reset restores all rows | PASS | 3 of 3
Vendor Management | Purchase Orders | List | list: export to CSV | PASS | purchase-orders-2026-10-03.csv · 3 rows
Vendor Management | Purchase Orders | List | list: Customize columns opens | PASS
Vendor Management | Purchase Orders | Record | list: drawer "PO-001 · Deccan Steel Traders" opens | PASS
Vendor Management | Purchase Orders | Page | summary | INFO | 0 cards, 0 tabs, 1 header buttons, loaded in 759 ms
Vendor Management | Invoices & Payments | Page | loads without script errors | PASS | 757 ms
Vendor Management | Invoices & Payments | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Invoices & Payments | Page | no sideways scroll of the page | PASS
Vendor Management | Invoices & Payments | Form | button "Record advance" → "Record advance paid to vendor" opens | PASS
Vendor Management | Invoices & Payments | Form | "Record advance paid to vendor" — Save disabled until the form is complete | PASS | 5 fields, 3 required
Vendor Management | Invoices & Payments | Form | "Record advance paid to vendor" closes with Esc | PASS
Vendor Management | Invoices & Payments | Form | button "Enter vendor bill" → "Enter vendor bill" opens | PASS
Vendor Management | Invoices & Payments | Form | "Enter vendor bill" — Save bill disabled until the form is complete | PASS | 5 fields, 1 required
Vendor Management | Invoices & Payments | Form | "Enter vendor bill" closes with Esc | PASS
Vendor Management | Invoices & Payments | Header | button "Select payable" | PASS | 1 bill(s) due within 7 days and clear of payment checks selected
Vendor Management | Invoices & Payments | Tab | tab "Bills" opens | PASS
Vendor Management | Invoices & Payments | List | tab "Bills": footer count matches the rows | PASS | footer 9 bills, rows 9
Vendor Management | Invoices & Payments | List | tab "Bills": sort on all 5 columns | PASS
Vendor Management | Invoices & Payments | List | tab "Bills": search "INV-001" finds rows | PASS | 1 rows
Vendor Management | Invoices & Payments | List | tab "Bills": search with no match shows "No matches" | PASS
Vendor Management | Invoices & Payments | Filters | tab "Bills": panel opens (3 sections, 14 chips) | PASS
Vendor Management | Invoices & Payments | Filters | tab "Bills": apply one chip | PASS | 9 → 7 rows
Vendor Management | Invoices & Payments | Filters | tab "Bills": Reset restores all rows | PASS | 9 of 9
Vendor Management | Invoices & Payments | List | tab "Bills": export to CSV | PASS | bills-2026-10-03.csv · 9 rows
Vendor Management | Invoices & Payments | List | tab "Bills": Customize columns opens | PASS
Vendor Management | Invoices & Payments | Record | tab "Bills": drawer "INV-001 · Shree Balaji Infra Contractors" opens | PASS
Vendor Management | Invoices & Payments | Tab | tab "Accruals" opens | PASS
Vendor Management | Invoices & Payments | List | tab "Accruals": footer count matches the rows | PASS | footer 2 accrual lines, rows 2
Vendor Management | Invoices & Payments | List | tab "Accruals": sort on all 7 columns | PASS
Vendor Management | Invoices & Payments | List | tab "Accruals": search "MB-026" finds rows | PASS | 1 rows
Vendor Management | Invoices & Payments | List | tab "Accruals": search with no match shows "No matches" | PASS
Vendor Management | Invoices & Payments | Filters | tab "Accruals": panel opens (3 sections, 7 chips) | PASS
Vendor Management | Invoices & Payments | Filters | tab "Accruals": apply one chip | PASS | 2 → 0 rows
Vendor Management | Invoices & Payments | Filters | tab "Accruals": Reset restores all rows | PASS | 2 of 2
Vendor Management | Invoices & Payments | List | tab "Accruals": export to CSV | PASS | accruals-2026-10-03.csv · 2 rows
Vendor Management | Invoices & Payments | Record | tab "Accruals": row click | INFO | no drawer (row is not clickable)
Vendor Management | Invoices & Payments | Page | summary | INFO | 0 cards, 2 tabs, 4 header buttons, loaded in 757 ms
Vendor Management | Requalification | Page | loads without script errors | PASS | 777 ms
Vendor Management | Requalification | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Requalification | Page | no sideways scroll of the page | PASS
Vendor Management | Requalification | Tab | tab "To requalify" opens | PASS
Vendor Management | Requalification | Tab | tab "History" opens | PASS
Vendor Management | Requalification | Page | summary | INFO | 0 cards, 2 tabs, 0 header buttons, loaded in 777 ms
Vendor Management | Vendor Scorecard | Page | loads without script errors | PASS | 754 ms
Vendor Management | Vendor Scorecard | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Vendor Scorecard | Page | no sideways scroll of the page | PASS
Vendor Management | Vendor Scorecard | Form | button "Rate performance" → "Rate contractor performance" opens | PASS
Vendor Management | Vendor Scorecard | Form | "Rate contractor performance" — Save rating disabled until the form is complete | PASS | 8 fields, 0 required
Vendor Management | Vendor Scorecard | Form | "Rate contractor performance" closes with Esc | PASS
Vendor Management | Vendor Scorecard | Header | button "Run auto-block check" | PASS | No vendor below threshold
Vendor Management | Vendor Scorecard | Tab | tab "Scorecard" opens | PASS
Vendor Management | Vendor Scorecard | List | tab "Scorecard": footer count matches the rows | PASS | footer 13 vendors, rows 13
Vendor Management | Vendor Scorecard | List | tab "Scorecard": sort on all 4 columns | PASS
Vendor Management | Vendor Scorecard | List | tab "Scorecard": search "Cement" finds rows | PASS | 2 rows
Vendor Management | Vendor Scorecard | List | tab "Scorecard": search with no match shows "No matches" | PASS
Vendor Management | Vendor Scorecard | Filters | tab "Scorecard": panel opens (3 sections, 12 chips) | PASS
Vendor Management | Vendor Scorecard | Filters | tab "Scorecard": apply one chip | PASS | 13 → 2 rows
Vendor Management | Vendor Scorecard | Filters | tab "Scorecard": Reset restores all rows | PASS | 13 of 13
Vendor Management | Vendor Scorecard | List | tab "Scorecard": export to CSV | PASS | vendors-2026-10-03.csv · 13 rows
Vendor Management | Vendor Scorecard | List | tab "Scorecard": Customize columns opens | PASS
Vendor Management | Vendor Scorecard | Record | tab "Scorecard": drawer "UltraBuild Cement Distributors" opens | PASS
Vendor Management | Vendor Scorecard | Record | tab "Scorecard": drawer tab "Overview" | PASS
Vendor Management | Vendor Scorecard | Record | tab "Scorecard": drawer tab "Status & flags" | PASS
Vendor Management | Vendor Scorecard | Record | tab "Scorecard": drawer tab "Documents 5/5" | PASS
Vendor Management | Vendor Scorecard | Record | tab "Scorecard": drawer tab "Bank 1" | PASS
Vendor Management | Vendor Scorecard | Record | tab "Scorecard": drawer tab "Qualification" | PASS
Vendor Management | Vendor Scorecard | Record | tab "Scorecard": drawer tab "Approvals" | PASS
Vendor Management | Vendor Scorecard | Tab | tab "Corrective actions" opens | PASS
Vendor Management | Vendor Scorecard | List | tab "Corrective actions": footer count matches the rows | PASS | footer 2 corrective actions, rows 2
Vendor Management | Vendor Scorecard | List | tab "Corrective actions": sort on all 6 columns | PASS
Vendor Management | Vendor Scorecard | List | tab "Corrective actions": search "Rapid" finds rows | PASS | 1 rows
Vendor Management | Vendor Scorecard | List | tab "Corrective actions": search with no match shows "No matches" | PASS
Vendor Management | Vendor Scorecard | Filters | tab "Corrective actions": panel opens (3 sections, 5 chips) | PASS
Vendor Management | Vendor Scorecard | Filters | tab "Corrective actions": apply one chip | PASS | 2 → 1 rows
Vendor Management | Vendor Scorecard | Filters | tab "Corrective actions": Reset restores all rows | PASS | 2 of 2
Vendor Management | Vendor Scorecard | List | tab "Corrective actions": export to CSV | PASS | corrective-actions-2026-10-03.csv · 2 rows
Vendor Management | Vendor Scorecard | Record | tab "Corrective actions": row click | INFO | no drawer (row is not clickable)
Vendor Management | Vendor Scorecard | Tab | tab "Metric model" opens | PASS
Vendor Management | Vendor Scorecard | Page | summary | INFO | 0 cards, 3 tabs, 2 header buttons, loaded in 754 ms
Vendor Management | Vendor Portal | Page | loads without script errors | PASS | 756 ms
Vendor Management | Vendor Portal | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Vendor Portal | Page | no sideways scroll of the page | PASS
Vendor Management | Vendor Portal | Header | button "Open supplier sign-in" | PASS | menu / action
Vendor Management | Vendor Portal | Header | button "Shree Balaji Infra Contractors" | PASS | menu / action
Vendor Management | Vendor Portal | Tab | tab "RFQs" opens | PASS
Vendor Management | Vendor Portal | Tab | tab "Purchase orders" opens | PASS
Vendor Management | Vendor Portal | Tab | tab "Work orders" opens | PASS
Vendor Management | Vendor Portal | List | tab "Work orders": footer count matches the rows | PASS | footer 2 records, rows 2
Vendor Management | Vendor Portal | List | tab "Work orders": sort on all 4 columns | PASS
Vendor Management | Vendor Portal | List | tab "Work orders": search "Tower" finds rows | PASS | 2 rows
Vendor Management | Vendor Portal | List | tab "Work orders": search with no match shows "No matches" | PASS
Vendor Management | Vendor Portal | Filters | tab "Work orders": panel opens (2 sections, 6 chips) | PASS
Vendor Management | Vendor Portal | Filters | tab "Work orders": apply one chip | PASS | 2 → 2 rows
Vendor Management | Vendor Portal | Filters | tab "Work orders": Reset restores all rows | PASS | 2 of 2
Vendor Management | Vendor Portal | List | tab "Work orders": export to CSV | PASS | records-2026-10-03.csv · 2 rows
Vendor Management | Vendor Portal | Record | tab "Work orders": drawer "Tower A — substructure & superstructure up to L5" opens | PASS
Vendor Management | Vendor Portal | Record | tab "Work orders": drawer tab "BOQ items" | PASS
Vendor Management | Vendor Portal | Record | tab "Work orders": drawer tab "Measurements 2 to agree" | PASS
Vendor Management | Vendor Portal | Record | tab "Work orders": drawer tab "NCRs" | PASS
Vendor Management | Vendor Portal | Record | tab "Work orders": drawer tab "Daily reports 2" | PASS
Vendor Management | Vendor Portal | Record | tab "Work orders": drawer tab "Claims 0" | PASS
Vendor Management | Vendor Portal | Record | tab "Work orders": drawer tab "RA bills 3" | PASS
Vendor Management | Vendor Portal | Record | tab "Work orders": drawer tab "Contract terms" | PASS
Vendor Management | Vendor Portal | Tab | tab "RA claims" opens | PASS
Vendor Management | Vendor Portal | Tab | tab "Bills & payments" opens | PASS
Vendor Management | Vendor Portal | List | tab "Bills & payments": footer count matches the rows | PASS | footer 3 records, rows 3
Vendor Management | Vendor Portal | List | tab "Bills & payments": sort on all 6 columns | PASS
Vendor Management | Vendor Portal | List | tab "Bills & payments": search "RA-001" finds rows | PASS | 1 rows
Vendor Management | Vendor Portal | List | tab "Bills & payments": search with no match shows "No matches" | PASS
Vendor Management | Vendor Portal | Filters | tab "Bills & payments": panel opens (1 sections, 2 chips) | PASS
Vendor Management | Vendor Portal | Filters | tab "Bills & payments": apply one chip | PASS | 3 → 2 rows
Vendor Management | Vendor Portal | Filters | tab "Bills & payments": Reset restores all rows | PASS | 3 of 3
Vendor Management | Vendor Portal | List | tab "Bills & payments": export to CSV | PASS | records-2026-10-03.csv · 3 rows
Vendor Management | Vendor Portal | Record | tab "Bills & payments": drawer "Bill RA-001/WO-001" opens | PASS
Vendor Management | Vendor Portal | Tab | tab "Pricelist" opens | PASS
Vendor Management | Vendor Portal | Tab | tab "Documents" opens | PASS
Vendor Management | Vendor Portal | List | tab "Documents": footer count matches the rows | PASS | footer 9 documents, rows 9
Vendor Management | Vendor Portal | List | tab "Documents": sort on all 2 columns | PASS
Vendor Management | Vendor Portal | List | tab "Documents": search with no match shows "No matches" | PASS
Vendor Management | Vendor Portal | Filters | tab "Documents": panel opens (1 sections, 6 chips) | PASS
Vendor Management | Vendor Portal | Filters | tab "Documents": apply one chip | PASS | 9 → 9 rows
Vendor Management | Vendor Portal | Filters | tab "Documents": Reset restores all rows | PASS | 9 of 9
Vendor Management | Vendor Portal | List | tab "Documents": export to CSV | PASS | documents-2026-10-03.csv · 9 rows
Vendor Management | Vendor Portal | Record | tab "Documents": drawer "PAN Card" opens | PASS
Vendor Management | Vendor Portal | Tab | tab "Queries" opens | PASS
Vendor Management | Vendor Portal | Tab | tab "Users" opens | PASS
Vendor Management | Vendor Portal | Page | summary | INFO | 4 cards, 9 tabs, 2 header buttons, loaded in 756 ms
Vendor Management | Procurement Settings | Page | loads without script errors | PASS | 766 ms
Vendor Management | Procurement Settings | Page | no undefined / NaN / Invalid Date on screen | PASS
Vendor Management | Procurement Settings | Page | no sideways scroll of the page | PASS
Vendor Management | Procurement Settings | Header | button "Save settings" | PASS | Settings saved
Vendor Management | Procurement Settings | Tab | tab "Rules" opens | PASS
Vendor Management | Procurement Settings | Tab | tab "Gates & approvals" opens | PASS
Vendor Management | Procurement Settings | Tab | tab "Masters" opens | PASS
Vendor Management | Procurement Settings | Tab | tab "Templates" opens | PASS
Vendor Management | Procurement Settings | Page | summary | INFO | 0 cards, 4 tabs, 1 header buttons, loaded in 766 ms
Contract & Labor | Overview | Page | loads without script errors | PASS | 784 ms
Contract & Labor | Overview | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Overview | Page | no sideways scroll of the page | PASS
Contract & Labor | Overview | Header | button "Last 90 days" | PASS | menu / action
Contract & Labor | Overview | Page | summary | INFO | 6 cards, 0 tabs, 1 header buttons, loaded in 784 ms
Contract & Labor | Contractor Onboarding | Page | loads without script errors | PASS | 777 ms
Contract & Labor | Contractor Onboarding | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Contractor Onboarding | Page | no sideways scroll of the page | PASS
Contract & Labor | Contractor Onboarding | Form | button "Onboard contractor" → "Onboard contractor" opens | PASS
Contract & Labor | Contractor Onboarding | Form | "Onboard contractor" — Submit for approval on the untouched form | PASS | Blocked: validation message shown
Contract & Labor | Contractor Onboarding | Form | "Onboard contractor" closes with Esc | PASS
Contract & Labor | Contractor Onboarding | List | list: footer count matches the rows | PASS | footer 7 contractors, rows 7
Contract & Labor | Contractor Onboarding | List | list: sort on all 2 columns | PASS
Contract & Labor | Contractor Onboarding | List | list: search "Civil" finds rows | PASS | 1 rows
Contract & Labor | Contractor Onboarding | List | list: search with no match shows "No matches" | PASS
Contract & Labor | Contractor Onboarding | Filters | list: panel opens (3 sections, 7 chips) | PASS
Contract & Labor | Contractor Onboarding | Filters | list: apply one chip | PASS | 7 → 2 rows
Contract & Labor | Contractor Onboarding | Filters | list: Reset restores all rows | PASS | 7 of 7
Contract & Labor | Contractor Onboarding | List | list: export to CSV | PASS | contractors-2026-10-03.csv · 7 rows
Contract & Labor | Contractor Onboarding | Record | list: drawer "Shree Balaji Infra Contractors" opens | PASS
Contract & Labor | Contractor Onboarding | Page | summary | INFO | 0 cards, 0 tabs, 1 header buttons, loaded in 777 ms
Contract & Labor | Contracts | Page | loads without script errors | PASS | 795 ms
Contract & Labor | Contracts | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Contracts | Page | no sideways scroll of the page | PASS
Contract & Labor | Contracts | Form | button "Create contract" → "Create contract" opens | PASS
Contract & Labor | Contracts | Form | "Create contract" — Submit for approval disabled until the form is complete | PASS | 31 fields, 3 required
Contract & Labor | Contracts | Form | "Create contract" closes with Esc | PASS
Contract & Labor | Contracts | List | list: footer count matches the rows | PASS | footer 6 contracts, rows 6
Contract & Labor | Contracts | List | list: sort on all 5 columns | PASS
Contract & Labor | Contracts | List | list: search "Civil" finds rows | PASS | 1 rows
Contract & Labor | Contracts | List | list: search with no match shows "No matches" | PASS
Contract & Labor | Contracts | Filters | list: panel opens (3 sections, 21 chips) | PASS
Contract & Labor | Contracts | Filters | list: apply one chip | PASS | 6 → 1 rows
Contract & Labor | Contracts | Filters | list: Reset restores all rows | PASS | 6 of 6
Contract & Labor | Contracts | List | list: export to CSV | PASS | contracts-2026-10-03.csv · 6 rows
Contract & Labor | Contracts | Record | list: drawer "Civil & structural works — Towers A & B" opens | PASS
Contract & Labor | Contracts | Page | summary | INFO | 0 cards, 0 tabs, 1 header buttons, loaded in 795 ms
Contract & Labor | Work Orders | Page | loads without script errors | PASS | 769 ms
Contract & Labor | Work Orders | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Work Orders | Page | no sideways scroll of the page | PASS
Contract & Labor | Work Orders | Form | button "Create work order" → "Create work order" opens | PASS
Contract & Labor | Work Orders | Form | "Create work order" — Issue work order disabled until the form is complete | PASS | 7 fields, 3 required
Contract & Labor | Work Orders | Form | "Create work order" closes with Esc | PASS
Contract & Labor | Work Orders | List | list: footer count matches the rows | PASS | footer 6 work orders, rows 6
Contract & Labor | Work Orders | List | list: sort on all 5 columns | PASS
Contract & Labor | Work Orders | List | list: search "Tower" finds rows | PASS | 4 rows
Contract & Labor | Work Orders | List | list: search with no match shows "No matches" | PASS
Contract & Labor | Work Orders | Filters | list: panel opens (3 sections, 17 chips) | PASS
Contract & Labor | Work Orders | Filters | list: apply one chip | PASS | 6 → 1 rows
Contract & Labor | Work Orders | Filters | list: Reset restores all rows | PASS | 6 of 6
Contract & Labor | Work Orders | List | list: export to CSV | PASS | work-orders-2026-10-03.csv · 6 rows
Contract & Labor | Work Orders | List | list: Customize columns opens | PASS
Contract & Labor | Work Orders | Record | list: drawer "Tower A — substructure & superstructure up to L5" opens | PASS
Contract & Labor | Work Orders | Page | summary | INFO | 0 cards, 0 tabs, 1 header buttons, loaded in 769 ms
Contract & Labor | Labour Attendance | Page | loads without script errors | PASS | 755 ms
Contract & Labor | Labour Attendance | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Labour Attendance | Page | no sideways scroll of the page | PASS
Contract & Labor | Labour Attendance | Tab | tab "Daily muster" opens | PASS
Contract & Labor | Labour Attendance | Tab | tab "Roll up to measurement book" opens | PASS
Contract & Labor | Labour Attendance | List | tab "Roll up to measurement book": footer count matches the rows | PASS | footer 3 records, rows 3
Contract & Labor | Labour Attendance | List | tab "Roll up to measurement book": sort on all 2 columns | PASS
Contract & Labor | Labour Attendance | List | tab "Roll up to measurement book": search with no match shows "No matches" | PASS
Contract & Labor | Labour Attendance | List | tab "Roll up to measurement book": export to CSV | PASS | records-2026-10-03.csv · 3 rows
Contract & Labor | Labour Attendance | Record | tab "Roll up to measurement book": row click | INFO | no drawer (row is not clickable)
Contract & Labor | Labour Attendance | Tab | tab "Workers" opens | PASS
Contract & Labor | Labour Attendance | List | tab "Workers": footer count matches the rows | PASS | footer 16 workers, rows 16
Contract & Labor | Labour Attendance | List | tab "Workers": sort on all 7 columns | PASS
Contract & Labor | Labour Attendance | List | tab "Workers": search "Suresh" finds rows | PASS | 1 rows
Contract & Labor | Labour Attendance | List | tab "Workers": search with no match shows "No matches" | PASS
Contract & Labor | Labour Attendance | Filters | tab "Workers": panel opens (4 sections, 24 chips) | PASS
Contract & Labor | Labour Attendance | Filters | tab "Workers": apply one chip | PASS | 16 → 0 rows
Contract & Labor | Labour Attendance | Filters | tab "Workers": Reset restores all rows | PASS | 16 of 16
Contract & Labor | Labour Attendance | List | tab "Workers": export to CSV | PASS | workers-2026-10-03.csv · 16 rows
Contract & Labor | Labour Attendance | Record | tab "Workers": row click | INFO | no drawer (row is not clickable)
Contract & Labor | Labour Attendance | Page | summary | INFO | 0 cards, 3 tabs, 0 header buttons, loaded in 755 ms
Contract & Labor | Measurement Book | Page | loads without script errors | PASS | 766 ms
Contract & Labor | Measurement Book | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Measurement Book | Page | no sideways scroll of the page | PASS
Contract & Labor | Measurement Book | Form | button "Record measurement" → "Record measurement" opens | PASS
Contract & Labor | Measurement Book | Form | "Record measurement" — Save to MB disabled until the form is complete | PASS | 10 fields, 3 required
Contract & Labor | Measurement Book | Form | "Record measurement" closes with Esc | PASS
Contract & Labor | Measurement Book | Tab | tab "Measurement book" opens | PASS
Contract & Labor | Measurement Book | List | tab "Measurement book": footer count matches the rows | PASS | footer 32 measurements, rows 32
Contract & Labor | Measurement Book | List | tab "Measurement book": sort on all 5 columns | PASS
Contract & Labor | Measurement Book | List | tab "Measurement book": search "Sept" finds rows | PASS | 7 rows
Contract & Labor | Measurement Book | List | tab "Measurement book": search with no match shows "No matches" | PASS
Contract & Labor | Measurement Book | Filters | tab "Measurement book": panel opens (4 sections, 14 chips) | PASS
Contract & Labor | Measurement Book | Filters | tab "Measurement book": apply one chip | PASS | 32 → 5 rows
Contract & Labor | Measurement Book | Filters | tab "Measurement book": Reset restores all rows | PASS | 32 of 32
Contract & Labor | Measurement Book | List | tab "Measurement book": export to CSV | PASS | measurements-2026-10-03.csv · 32 rows
Contract & Labor | Measurement Book | List | tab "Measurement book": Customize columns opens | PASS
Contract & Labor | Measurement Book | Record | tab "Measurement book": drawer "1.6 · Backfilling with approved excavated earth" opens | PASS
Contract & Labor | Measurement Book | Tab | tab "Joint measurement sheets" opens | PASS
Contract & Labor | Measurement Book | List | tab "Joint measurement sheets": footer count matches the rows | PASS | footer 5 pending entries, rows 5
Contract & Labor | Measurement Book | List | tab "Joint measurement sheets": sort on all 3 columns | PASS
Contract & Labor | Measurement Book | List | tab "Joint measurement sheets": search "MB-016" finds rows | PASS | 1 rows
Contract & Labor | Measurement Book | List | tab "Joint measurement sheets": search with no match shows "No matches" | PASS
Contract & Labor | Measurement Book | Filters | tab "Joint measurement sheets": panel opens (1 sections, 3 chips) | PASS
Contract & Labor | Measurement Book | Filters | tab "Joint measurement sheets": apply one chip | PASS | 5 → 4 rows
Contract & Labor | Measurement Book | Filters | tab "Joint measurement sheets": Reset restores all rows | PASS | 5 of 5
Contract & Labor | Measurement Book | List | tab "Joint measurement sheets": export to CSV | PASS | pending-entries-2026-10-03.csv · 5 rows
Contract & Labor | Measurement Book | Record | tab "Joint measurement sheets": drawer "3.4 · RCC M30 in raft, columns & slabs" opens | PASS
Contract & Labor | Measurement Book | Tab | tab "Inspections & NCRs (1)" opens | PASS
Contract & Labor | Measurement Book | List | tab "Inspections & NCRs (1)": footer count matches the rows | PASS | footer 2 NCRs, rows 2
Contract & Labor | Measurement Book | List | tab "Inspections & NCRs (1)": sort on all 5 columns | PASS
Contract & Labor | Measurement Book | List | tab "Inspections & NCRs (1)": search "WO-004" finds rows | PASS | 1 rows
Contract & Labor | Measurement Book | List | tab "Inspections & NCRs (1)": search with no match shows "No matches" | PASS
Contract & Labor | Measurement Book | Filters | tab "Inspections & NCRs (1)": panel opens (3 sections, 8 chips) | PASS
Contract & Labor | Measurement Book | Filters | tab "Inspections & NCRs (1)": apply one chip | PASS | 2 → 1 rows
Contract & Labor | Measurement Book | Filters | tab "Inspections & NCRs (1)": Reset restores all rows | PASS | 2 of 2
Contract & Labor | Measurement Book | List | tab "Inspections & NCRs (1)": export to CSV | PASS | NCRs-2026-10-03.csv · 2 rows
Contract & Labor | Measurement Book | Record | tab "Inspections & NCRs (1)": row click | INFO | no drawer (row is not clickable)
Contract & Labor | Measurement Book | Tab | tab "Abstract by item" opens | PASS
Contract & Labor | Measurement Book | Page | summary | INFO | 0 cards, 4 tabs, 1 header buttons, loaded in 766 ms
Contract & Labor | RA Bills & Certification | Page | loads without script errors | PASS | 760 ms
Contract & Labor | RA Bills & Certification | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | RA Bills & Certification | Page | no sideways scroll of the page | PASS
Contract & Labor | RA Bills & Certification | Form | button "Prepare RA bill" → "Prepare RA bill — WO-003 · RA-3" opens | PASS
Contract & Labor | RA Bills & Certification | Form | "Prepare RA bill — WO-003 · RA-3" — Submit for certification on the untouched form | PASS | Blocked: validation message shown
Contract & Labor | RA Bills & Certification | Form | "Prepare RA bill — WO-003 · RA-3" closes with Esc | PASS
Contract & Labor | RA Bills & Certification | Tab | tab "RA bills" opens | PASS
Contract & Labor | RA Bills & Certification | List | tab "RA bills": footer count matches the rows | PASS | footer 9 bills, rows 9
Contract & Labor | RA Bills & Certification | List | tab "RA bills": sort on all 4 columns | PASS
Contract & Labor | RA Bills & Certification | List | tab "RA bills": search "RA-3" finds rows | PASS | 2 rows
Contract & Labor | RA Bills & Certification | List | tab "RA bills": search with no match shows "No matches" | PASS
Contract & Labor | RA Bills & Certification | Filters | tab "RA bills": panel opens (3 sections, 15 chips) | PASS
Contract & Labor | RA Bills & Certification | Filters | tab "RA bills": apply one chip | PASS | 9 → 3 rows
Contract & Labor | RA Bills & Certification | Filters | tab "RA bills": Reset restores all rows | PASS | 9 of 9
Contract & Labor | RA Bills & Certification | List | tab "RA bills": export to CSV | PASS | bills-2026-10-03.csv · 9 rows
Contract & Labor | RA Bills & Certification | Record | tab "RA bills": drawer "RA-009 · RA-3 · Erection & stringing — Section 1 (" opens | PASS
Contract & Labor | RA Bills & Certification | Tab | tab "Contractor claims" opens | PASS
Contract & Labor | RA Bills & Certification | List | tab "Contractor claims": footer count matches the rows | PASS | footer 1 claims, rows 1
Contract & Labor | RA Bills & Certification | List | tab "Contractor claims": sort on all 3 columns | PASS
Contract & Labor | RA Bills & Certification | List | tab "Contractor claims": search "Earthmovers" finds rows | PASS | 1 rows
Contract & Labor | RA Bills & Certification | List | tab "Contractor claims": search with no match shows "No matches" | PASS
Contract & Labor | RA Bills & Certification | Filters | tab "Contractor claims": panel opens (2 sections, 10 chips) | PASS
Contract & Labor | RA Bills & Certification | Filters | tab "Contractor claims": apply one chip | PASS | 1 → 0 rows
Contract & Labor | RA Bills & Certification | Filters | tab "Contractor claims": Reset restores all rows | PASS | 1 of 1
Contract & Labor | RA Bills & Certification | List | tab "Contractor claims": export to CSV | PASS | claims-2026-10-03.csv · 1 rows
Contract & Labor | RA Bills & Certification | Record | tab "Contractor claims": drawer "Verify contractor claim CLM-001" opens | PASS
Contract & Labor | RA Bills & Certification | Page | summary | INFO | 0 cards, 2 tabs, 1 header buttons, loaded in 760 ms
Contract & Labor | Retention & Deductions | Page | loads without script errors | PASS | 777 ms
Contract & Labor | Retention & Deductions | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Retention & Deductions | Page | no sideways scroll of the page | PASS
Contract & Labor | Retention & Deductions | Form | button "Record advance" → "Record advance paid to contractor" opens | PASS
Contract & Labor | Retention & Deductions | Form | "Record advance paid to contractor" — Save disabled until the form is complete | PASS | 5 fields, 3 required
Contract & Labor | Retention & Deductions | Form | "Record advance paid to contractor" closes with Esc | PASS
Contract & Labor | Retention & Deductions | Form | button "Request retention release" → "Request retention release" opens | PASS
Contract & Labor | Retention & Deductions | Form | "Request retention release" — Raise request disabled until the form is complete | PASS | 4 fields, 0 required
Contract & Labor | Retention & Deductions | Form | "Request retention release" closes with Esc | PASS
Contract & Labor | Retention & Deductions | Tab | tab "Contract ledger" opens | PASS
Contract & Labor | Retention & Deductions | List | tab "Contract ledger": footer count matches the rows | PASS | footer 5 contracts, rows 5
Contract & Labor | Retention & Deductions | List | tab "Contract ledger": sort on all 1 columns | PASS
Contract & Labor | Retention & Deductions | List | tab "Contract ledger": search "Active" finds rows | PASS | 5 rows
Contract & Labor | Retention & Deductions | List | tab "Contract ledger": search with no match shows "No matches" | PASS
Contract & Labor | Retention & Deductions | Filters | tab "Contract ledger": panel opens (1 sections, 11 chips) | PASS
Contract & Labor | Retention & Deductions | Filters | tab "Contract ledger": apply one chip | PASS | 5 → 0 rows
Contract & Labor | Retention & Deductions | Filters | tab "Contract ledger": Reset restores all rows | PASS | 5 of 5
Contract & Labor | Retention & Deductions | List | tab "Contract ledger": export to CSV | PASS | contracts-2026-10-03.csv · 5 rows
Contract & Labor | Retention & Deductions | Record | tab "Contract ledger": drawer "Civil & structural works — Towers A & B" opens | PASS
Contract & Labor | Retention & Deductions | Tab | tab "Retention releases" opens | PASS
Contract & Labor | Retention & Deductions | List | tab "Retention releases": footer count matches the rows | PASS | footer 1 releases, rows 1
Contract & Labor | Retention & Deductions | List | tab "Retention releases": sort on all 5 columns | PASS
Contract & Labor | Retention & Deductions | List | tab "Retention releases": search "CTR-005" finds rows | PASS | 1 rows
Contract & Labor | Retention & Deductions | List | tab "Retention releases": search with no match shows "No matches" | PASS
Contract & Labor | Retention & Deductions | Filters | tab "Retention releases": panel opens (2 sections, 5 chips) | PASS
Contract & Labor | Retention & Deductions | Filters | tab "Retention releases": apply one chip | PASS | 1 → 1 rows
Contract & Labor | Retention & Deductions | Filters | tab "Retention releases": Reset restores all rows | PASS | 1 of 1
Contract & Labor | Retention & Deductions | List | tab "Retention releases": export to CSV | PASS | releases-2026-10-03.csv · 1 rows
Contract & Labor | Retention & Deductions | Record | tab "Retention releases": drawer "Scaffolding hire & erection — Tower A" opens | PASS
Contract & Labor | Retention & Deductions | Tab | tab "Deduction register" opens | PASS
Contract & Labor | Retention & Deductions | List | tab "Deduction register": footer count matches the rows | PASS | footer 8 deductions, rows 8
Contract & Labor | Retention & Deductions | List | tab "Deduction register": sort on all 2 columns | PASS
Contract & Labor | Retention & Deductions | List | tab "Deduction register": search "CTR-001" finds rows | PASS | 3 rows
Contract & Labor | Retention & Deductions | List | tab "Deduction register": search with no match shows "No matches" | PASS
Contract & Labor | Retention & Deductions | Filters | tab "Deduction register": panel opens (1 sections, 7 chips) | PASS
Contract & Labor | Retention & Deductions | Filters | tab "Deduction register": apply one chip | PASS | 8 → 2 rows
Contract & Labor | Retention & Deductions | Filters | tab "Deduction register": Reset restores all rows | PASS | 8 of 8
Contract & Labor | Retention & Deductions | List | tab "Deduction register": export to CSV | PASS | deductions-2026-10-03.csv · 8 rows
Contract & Labor | Retention & Deductions | Record | tab "Deduction register": drawer "RA-001 · RA-1 · Tower A — substructure & superstru" opens | PASS
Contract & Labor | Retention & Deductions | Page | summary | INFO | 0 cards, 3 tabs, 2 header buttons, loaded in 777 ms
Contract & Labor | Labor Rate Management | Page | loads without script errors | PASS | 783 ms
Contract & Labor | Labor Rate Management | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Labor Rate Management | Page | no sideways scroll of the page | PASS
Contract & Labor | Labor Rate Management | Form | button "New rate" → "New labour rate" opens | PASS
Contract & Labor | Labor Rate Management | Form | "New labour rate" — Submit for approval disabled until the form is complete | PASS | 9 fields, 3 required
Contract & Labor | Labor Rate Management | Form | "New labour rate" closes with Esc | PASS
Contract & Labor | Labor Rate Management | Tab | tab "Rate cards" opens | PASS
Contract & Labor | Labor Rate Management | List | tab "Rate cards": footer count matches the rows | PASS | footer 16 rate cards, rows 16
Contract & Labor | Labor Rate Management | List | tab "Rate cards": sort on all 5 columns | PASS
Contract & Labor | Labor Rate Management | List | tab "Rate cards": search "Helper" finds rows | PASS | 3 rows
Contract & Labor | Labor Rate Management | List | tab "Rate cards": search with no match shows "No matches" | PASS
Contract & Labor | Labor Rate Management | Filters | tab "Rate cards": panel opens (4 sections, 21 chips) | PASS
Contract & Labor | Labor Rate Management | Filters | tab "Rate cards": apply one chip | PASS | 16 → 1 rows
Contract & Labor | Labor Rate Management | Filters | tab "Rate cards": Reset restores all rows | PASS | 16 of 16
Contract & Labor | Labor Rate Management | List | tab "Rate cards": export to CSV | PASS | rate-cards-2026-10-03.csv · 16 rows
Contract & Labor | Labor Rate Management | List | tab "Rate cards": Customize columns opens | PASS
Contract & Labor | Labor Rate Management | Record | tab "Rate cards": drawer "Helper / Unskilled — Unskilled" opens | PASS
Contract & Labor | Labor Rate Management | Tab | tab "Pending approval" opens | PASS
Contract & Labor | Labor Rate Management | List | tab "Pending approval": footer count matches the rows | PASS | footer 2 revisions, rows 2
Contract & Labor | Labor Rate Management | List | tab "Pending approval": sort on all 5 columns | PASS
Contract & Labor | Labor Rate Management | List | tab "Pending approval": search "Helper" finds rows | PASS | 1 rows
Contract & Labor | Labor Rate Management | List | tab "Pending approval": search with no match shows "No matches" | PASS
Contract & Labor | Labor Rate Management | Filters | tab "Pending approval": panel opens (1 sections, 11 chips) | PASS
Contract & Labor | Labor Rate Management | Filters | tab "Pending approval": apply one chip | PASS | 2 → 0 rows
Contract & Labor | Labor Rate Management | Filters | tab "Pending approval": Reset restores all rows | PASS | 2 of 2
Contract & Labor | Labor Rate Management | List | tab "Pending approval": export to CSV | PASS | revisions-2026-10-03.csv · 2 rows
Contract & Labor | Labor Rate Management | List | tab "Pending approval": Customize columns opens | PASS
Contract & Labor | Labor Rate Management | Record | tab "Pending approval": drawer "Helper / Unskilled — Unskilled" opens | PASS
Contract & Labor | Labor Rate Management | Tab | tab "Work order rate check" opens | PASS
Contract & Labor | Labor Rate Management | List | tab "Work order rate check": footer count matches the rows | PASS | footer 3 items, rows 3
Contract & Labor | Labor Rate Management | List | tab "Work order rate check": sort on all 2 columns | PASS
Contract & Labor | Labor Rate Management | List | tab "Work order rate check": search "Skilled" finds rows | PASS | 3 rows
Contract & Labor | Labor Rate Management | List | tab "Work order rate check": search with no match shows "No matches" | PASS
Contract & Labor | Labor Rate Management | Filters | tab "Work order rate check": panel opens (2 sections, 10 chips) | PASS
Contract & Labor | Labor Rate Management | Filters | tab "Work order rate check": apply one chip | PASS | 3 → 0 rows
Contract & Labor | Labor Rate Management | Filters | tab "Work order rate check": Reset restores all rows | PASS | 3 of 3
Contract & Labor | Labor Rate Management | List | tab "Work order rate check": export to CSV | PASS | items-2026-10-03.csv · 3 rows
Contract & Labor | Labor Rate Management | Record | tab "Work order rate check": row click | INFO | no drawer (row is not clickable)
Contract & Labor | Labor Rate Management | Tab | tab "Revision history" opens | PASS
Contract & Labor | Labor Rate Management | List | tab "Revision history": footer count matches the rows | PASS | footer 20 versions, rows 20
Contract & Labor | Labor Rate Management | List | tab "Revision history": sort on all 5 columns | PASS
Contract & Labor | Labor Rate Management | List | tab "Revision history": search "Bender" finds rows | PASS | 1 rows
Contract & Labor | Labor Rate Management | List | tab "Revision history": search with no match shows "No matches" | PASS
Contract & Labor | Labor Rate Management | Filters | tab "Revision history": panel opens (4 sections, 21 chips) | PASS
Contract & Labor | Labor Rate Management | Filters | tab "Revision history": apply one chip | PASS | 20 → 1 rows
Contract & Labor | Labor Rate Management | Filters | tab "Revision history": Reset restores all rows | PASS | 20 of 20
Contract & Labor | Labor Rate Management | List | tab "Revision history": export to CSV | PASS | versions-2026-10-03.csv · 20 rows
Contract & Labor | Labor Rate Management | List | tab "Revision history": Customize columns opens | PASS
Contract & Labor | Labor Rate Management | Record | tab "Revision history": drawer "Bar Bender — Skilled" opens | PASS
Contract & Labor | Labor Rate Management | Page | summary | INFO | 0 cards, 4 tabs, 1 header buttons, loaded in 783 ms
Contract & Labor | Performance & Progress | Page | loads without script errors | PASS | 774 ms
Contract & Labor | Performance & Progress | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Performance & Progress | Page | no sideways scroll of the page | PASS
Contract & Labor | Performance & Progress | Form | button "Rate contractor" → "Rate contractor performance" opens | PASS
Contract & Labor | Performance & Progress | Form | "Rate contractor performance" — Save rating disabled until the form is complete | PASS | 8 fields, 0 required
Contract & Labor | Performance & Progress | Form | "Rate contractor performance" closes with Esc | PASS
Contract & Labor | Performance & Progress | Tab | tab "Work order progress" opens | PASS
Contract & Labor | Performance & Progress | List | tab "Work order progress": footer count matches the rows | PASS | footer 5 work orders, rows 5
Contract & Labor | Performance & Progress | List | tab "Work order progress": sort on all 2 columns | PASS
Contract & Labor | Performance & Progress | List | tab "Work order progress": search "Tower" finds rows | PASS | 3 rows
Contract & Labor | Performance & Progress | List | tab "Work order progress": search with no match shows "No matches" | PASS
Contract & Labor | Performance & Progress | Filters | tab "Work order progress": panel opens (2 sections, 10 chips) | PASS
Contract & Labor | Performance & Progress | Filters | tab "Work order progress": apply one chip | PASS | 5 → 1 rows
Contract & Labor | Performance & Progress | Filters | tab "Work order progress": Reset restores all rows | PASS | 5 of 5
Contract & Labor | Performance & Progress | List | tab "Work order progress": export to CSV | PASS | work-orders-2026-10-03.csv · 5 rows
Contract & Labor | Performance & Progress | Record | tab "Work order progress": drawer "Tower A — substructure & superstructure up to L5" opens | PASS
Contract & Labor | Performance & Progress | Tab | tab "Planned vs actual" opens | PASS
Contract & Labor | Performance & Progress | Tab | tab "Daily progress" opens | PASS
Contract & Labor | Performance & Progress | List | tab "Daily progress": footer count matches the rows | PASS | footer 3 daily reports, rows 3
Contract & Labor | Performance & Progress | List | tab "Daily progress": sort on all 7 columns | PASS
Contract & Labor | Performance & Progress | List | tab "Daily progress": search "WO-001" finds rows | PASS | 2 rows
Contract & Labor | Performance & Progress | List | tab "Daily progress": search with no match shows "No matches" | PASS
Contract & Labor | Performance & Progress | Filters | tab "Daily progress": panel opens (2 sections, 11 chips) | PASS
Contract & Labor | Performance & Progress | Filters | tab "Daily progress": apply one chip | PASS | 3 → 0 rows
Contract & Labor | Performance & Progress | Filters | tab "Daily progress": Reset restores all rows | PASS | 3 of 3
Contract & Labor | Performance & Progress | List | tab "Daily progress": export to CSV | PASS | daily-reports-2026-10-03.csv · 3 rows
Contract & Labor | Performance & Progress | Record | tab "Daily progress": row click | INFO | no drawer (row is not clickable)
Contract & Labor | Performance & Progress | Tab | tab "Cost by WBS" opens | PASS
Contract & Labor | Performance & Progress | List | tab "Cost by WBS": footer count matches the rows | PASS | footer 5 WBS elements, rows 5
Contract & Labor | Performance & Progress | List | tab "Cost by WBS": sort on all 8 columns | PASS
Contract & Labor | Performance & Progress | List | tab "Cost by WBS": search "Tower" finds rows | PASS | 3 rows
Contract & Labor | Performance & Progress | List | tab "Cost by WBS": search with no match shows "No matches" | PASS
Contract & Labor | Performance & Progress | Filters | tab "Cost by WBS": panel opens (1 sections, 5 chips) | PASS
Contract & Labor | Performance & Progress | Filters | tab "Cost by WBS": apply one chip | PASS | 5 → 2 rows
Contract & Labor | Performance & Progress | Filters | tab "Cost by WBS": Reset restores all rows | PASS | 5 of 5
Contract & Labor | Performance & Progress | List | tab "Cost by WBS": export to CSV | PASS | WBS-elements-2026-10-03.csv · 5 rows
Contract & Labor | Performance & Progress | Record | tab "Cost by WBS": row click | INFO | no drawer (row is not clickable)
Contract & Labor | Performance & Progress | Page | summary | INFO | 0 cards, 4 tabs, 1 header buttons, loaded in 774 ms
Contract & Labor | Close-out & Handover | Page | loads without script errors | PASS | 766 ms
Contract & Labor | Close-out & Handover | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Close-out & Handover | Page | no sideways scroll of the page | PASS
Contract & Labor | Close-out & Handover | List | list: footer count matches the rows | PASS | footer 5 contracts, rows 5
Contract & Labor | Close-out & Handover | List | list: sort on all 1 columns | PASS
Contract & Labor | Close-out & Handover | List | list: search "Civil" finds rows | PASS | 1 rows
Contract & Labor | Close-out & Handover | List | list: search with no match shows "No matches" | PASS
Contract & Labor | Close-out & Handover | Filters | list: panel opens (2 sections, 20 chips) | PASS
Contract & Labor | Close-out & Handover | Filters | list: apply one chip | PASS | 5 → 1 rows
Contract & Labor | Close-out & Handover | Filters | list: Reset restores all rows | PASS | 5 of 5
Contract & Labor | Close-out & Handover | List | list: export to CSV | PASS | contracts-2026-10-03.csv · 5 rows
Contract & Labor | Close-out & Handover | Record | list: drawer "Close-out — Civil & structural works — Towers A & " opens | PASS
Contract & Labor | Close-out & Handover | Page | summary | INFO | 0 cards, 0 tabs, 0 header buttons, loaded in 766 ms
Contract & Labor | Final Settlement | Page | loads without script errors | PASS | 757 ms
Contract & Labor | Final Settlement | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Final Settlement | Page | no sideways scroll of the page | PASS
Contract & Labor | Final Settlement | List | list: footer count matches the rows | PASS | footer 1 contracts, rows 1
Contract & Labor | Final Settlement | List | list: sort on all 4 columns | PASS
Contract & Labor | Final Settlement | List | list: search "Scaffolding" finds rows | PASS | 1 rows
Contract & Labor | Final Settlement | List | list: search with no match shows "No matches" | PASS
Contract & Labor | Final Settlement | Filters | list: panel opens (2 sections, 12 chips) | PASS
Contract & Labor | Final Settlement | Filters | list: apply one chip | PASS | 1 → 0 rows
Contract & Labor | Final Settlement | Filters | list: Reset restores all rows | PASS | 1 of 1
Contract & Labor | Final Settlement | List | list: export to CSV | PASS | contracts-2026-10-03.csv · 1 rows
Contract & Labor | Final Settlement | Record | list: drawer "Final settlement — Scaffolding hire & erection — T" opens | PASS
Contract & Labor | Final Settlement | Page | summary | INFO | 4 cards, 0 tabs, 0 header buttons, loaded in 757 ms
Contract & Labor | DLP & Warranty | Page | loads without script errors | PASS | 757 ms
Contract & Labor | DLP & Warranty | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | DLP & Warranty | Page | no sideways scroll of the page | PASS
Contract & Labor | DLP & Warranty | Tab | tab "Defect liability" opens | PASS
Contract & Labor | DLP & Warranty | List | tab "Defect liability": footer count matches the rows | PASS | footer 1 contracts, rows 1
Contract & Labor | DLP & Warranty | List | tab "Defect liability": sort on all 3 columns | PASS
Contract & Labor | DLP & Warranty | List | tab "Defect liability": search "Scaffolding" finds rows | PASS | 1 rows
Contract & Labor | DLP & Warranty | List | tab "Defect liability": search with no match shows "No matches" | PASS
Contract & Labor | DLP & Warranty | List | tab "Defect liability": export to CSV | PASS | contracts-2026-10-03.csv · 1 rows
Contract & Labor | DLP & Warranty | Record | tab "Defect liability": drawer "Close-out — Scaffolding hire & erection — Tower A" opens | PASS
Contract & Labor | DLP & Warranty | Tab | tab "Goods warranties" opens | PASS
Contract & Labor | DLP & Warranty | Page | summary | INFO | 0 cards, 2 tabs, 0 header buttons, loaded in 757 ms
Contract & Labor | Contractor Release | Page | loads without script errors | PASS | 760 ms
Contract & Labor | Contractor Release | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Contractor Release | Page | no sideways scroll of the page | PASS
Contract & Labor | Contractor Release | Page | summary | INFO | 0 cards, 0 tabs, 0 header buttons, loaded in 760 ms
Contract & Labor | Termination & Final Account | Page | loads without script errors | PASS | 754 ms
Contract & Labor | Termination & Final Account | Page | no undefined / NaN / Invalid Date on screen | PASS
Contract & Labor | Termination & Final Account | Page | no sideways scroll of the page | PASS
Contract & Labor | Termination & Final Account | Form | button "Terminate a contract" → "Terminate a contract" opens | PASS
Contract & Labor | Termination & Final Account | Form | "Terminate a contract" — Terminate contract disabled until the form is complete | PASS | 2 fields, 2 required
Contract & Labor | Termination & Final Account | Form | "Terminate a contract" closes with Esc | PASS
Contract & Labor | Termination & Final Account | Page | summary | INFO | 0 cards, 0 tabs, 1 header buttons, loaded in 754 ms
Administration | Audit Log | Page | loads without script errors | PASS | 772 ms
Administration | Audit Log | Page | no undefined / NaN / Invalid Date on screen | PASS
Administration | Audit Log | Page | no sideways scroll of the page | PASS
Administration | Audit Log | List | list: footer count matches the rows | PASS | footer 4 entries, rows 4
Administration | Audit Log | List | list: sort on all 5 columns | PASS
Administration | Audit Log | List | list: search "Joshi" finds rows | PASS | 2 rows
Administration | Audit Log | List | list: search with no match shows "No matches" | PASS
Administration | Audit Log | Filters | list: panel opens (2 sections, 6 chips) | PASS
Administration | Audit Log | Filters | list: apply one chip | PASS | 4 → 2 rows
Administration | Audit Log | Filters | list: Reset restores all rows | PASS | 4 of 4
Administration | Audit Log | List | list: export to CSV | PASS | audit-log-2026-10-03.csv · 4 rows
Administration | Audit Log | Record | list: row click | INFO | no drawer (row is not clickable)
Administration | Audit Log | Page | summary | INFO | 0 cards, 0 tabs, 0 header buttons, loaded in 772 ms
Approvals | Approval Management | Page | loads without script errors | PASS | 756 ms
Approvals | Approval Management | Page | no undefined / NaN / Invalid Date on screen | PASS
Approvals | Approval Management | Page | no sideways scroll of the page | PASS
Approvals | Approval Management | Header | button "Ask AI" | PASS | menu / action
Approvals | Approval Management | Header | button "Select project" | PASS | menu / action
Approvals | Approval Management | List | list: footer count matches the rows | PASS | footer 1 items, rows 1
Approvals | Approval Management | List | list: sort on all 7 columns | PASS
Approvals | Approval Management | List | list: search "Greenline" finds rows | PASS | 1 rows
Approvals | Approval Management | List | list: search with no match shows "No matches" | PASS
Approvals | Approval Management | Filters | list: panel opens (3 sections, 5 chips) | PASS
Approvals | Approval Management | Filters | list: apply one chip | PASS | 1 → 1 rows
Approvals | Approval Management | Filters | list: Reset restores all rows | PASS | 1 of 1
Approvals | Approval Management | List | list: export to CSV | PASS | items-2026-10-03.csv · 1 rows
Approvals | Approval Management | Record | list: drawer "Greenline Solar EPC" opens | PASS
Approvals | Approval Management | Record | list: drawer tab "Overview" | PASS
Approvals | Approval Management | Record | list: drawer tab "Status & flags" | PASS
Approvals | Approval Management | Record | list: drawer tab "Documents 8/9" | PASS
Approvals | Approval Management | Record | list: drawer tab "Bank 1" | PASS
Approvals | Approval Management | Record | list: drawer tab "Qualification" | PASS
Approvals | Approval Management | Record | list: drawer tab "Equipment" | PASS
Approvals | Approval Management | Record | list: drawer tab "Approvals" | PASS
Approvals | Approval Management | Page | summary | INFO | 0 cards, 0 tabs, 2 header buttons, loaded in 756 ms
Supplier portal | Contractor (Shree Balaji) | Portal | opens signed in | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "RFQs" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Purchase orders" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Work orders" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Work orders": first record opens | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Work orders": record tab "BOQ items" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Work orders": record tab "Measurements 2 to agree" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Work orders": record tab "NCRs" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Work orders": record tab "Daily reports 2" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Work orders": record tab "Claims 0" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Work orders": record tab "RA bills 3" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Work orders": record tab "Contract terms" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "RA claims" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Bills & payments" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Bills & payments": first record opens | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Pricelist" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Documents" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Documents": first record opens | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Queries" | PASS
Supplier portal | Contractor (Shree Balaji) | Portal | tab "Users" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | opens signed in | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "RFQs" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "RFQs": first record opens | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Purchase orders" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Purchase orders": first record opens | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Purchase orders": record tab "Items" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Purchase orders": record tab "Deliveries 2" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Purchase orders": record tab "Returns 1" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Purchase orders": record tab "Bills 2" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Purchase orders": record tab "Terms" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Purchase orders": record tab "Revisions 2" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Bills & payments" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Bills & payments": first record opens | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Pricelist" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Pricelist": first record opens | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Documents" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Documents": first record opens | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Queries" | PASS
Supplier portal | Goods supplier (Deccan Steel) | Portal | tab "Users" | PASS
Public pages | No sign-in | Public | Supplier sign-in opens | PASS
Public pages | No sign-in | Public | Vendor self-registration opens | PASS
Public pages | No sign-in | Public | Vendor quotation link opens | PASS
Public pages | No sign-in | Public | Sign-in: Send code disabled for an invalid e-mail, enabled for a valid one | PASS | invalid → disabled, valid → enabled
Layout | Laptop 1280 × 720 | Layout | Overview: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Vendor Registry: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Vendor Approvals: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Compliance Center: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Purchase Requisitions: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | RFQ & Quotations: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Blanket Orders: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Purchase Orders: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Invoices & Payments: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Requalification: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Vendor Scorecard: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Vendor Portal: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Procurement Settings: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Overview: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Contractor Onboarding: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Contracts: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Work Orders: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Labour Attendance: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Measurement Book: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | RA Bills & Certification: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Retention & Deductions: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Labor Rate Management: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Performance & Progress: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Close-out & Handover: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Final Settlement: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | DLP & Warranty: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Contractor Release: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Termination & Final Account: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Audit Log: fits 1280 px wide | PASS
Layout | Laptop 1280 × 720 | Layout | Approval Management: fits 1280 px wide | PASS

## End-to-end suites
Suite | Covers | Checks | Pass | Fail | Result
merge.js | Vendor master: bank verification, foreign vendor, formats, uploads, document versions | 19 | 19 | 0 | PASS
fix1.js | Vendor gates and approvals | 13 | 13 | 0 | PASS
fix23.js | Award → contract, contract approval, guarantees, work-order gates, change orders | 12 | 12 | 0 | PASS
fix4.js | Inspection / NCR, quantities, material, equipment, DPR, JMS, WBS | 12 | 12 | 0 | PASS
fix5.js | Close-out, final bill, retention, portal invoices | 11 | 11 | 0 | PASS
final.js | Full vendor + contractor lifecycle (33 steps) | 33 | 33 | 0 | PASS
bench.js | Benchmark fields (19) | 19 | 19 | 0 | PASS
flow.js | Requisition → RFQ → PO → GRN, holds, change orders, audit log | 6 | 6 | 0 | PASS
closure.js | Final settlement, DLP & warranty, release, termination, requalification | 7 | 7 | 0 | PASS
wire.js | Every menu page, record links, deep links, filters panel, public pages | 102 | 102 | 0 | PASS