## LILO 220kV WBS
Activity_title | Activity_Description | Task_Name | Task_Description | Sub_Task_Name
Project Initial Activity |  | Site Establishment |  | Establishment of Site Office
Project Initial Activity |  | Site Establishment |  | Establishment of Store
Project Initial Activity |  | Mobilization |  | Mobilization of Site Team
Project Initial Activity |  | Mobilization |  | Finalization of Sub-Contractor
Engineering |  | Electrical Engineering |  | Route Survey with Client
Engineering |  | Electrical Engineering |  | Detail Survey
Engineering |  | Electrical Engineering |  | Profile Approval
Engineering |  | Documentation |  | Requisition of Inputs
Engineering |  | Documentation |  | Receipt of Drawings
Tower Foundation |  | Check Survey |  | Gantry 220kV-AP-01
Tower Foundation |  | Check Survey |  | AP-01 - AP-02
Tower Foundation |  | Check Survey |  | AP-02 - AP-03
Tower Foundation |  | Check Survey |  | AP-03 - AP-04
Tower Foundation |  | Check Survey |  | AP-04 - AP-05
Tower Foundation |  | Check Survey |  | AP-05 - AP-06
Tower Foundation |  | Check Survey |  | AP006 - EXT.T0.77
Tower Foundation |  | Civil Work |  | Location No. 01/0
Tower Foundation |  | Civil Work |  | Location No. 02/0
Tower Foundation |  | Civil Work |  | Location No. 03/0
Tower Foundation |  | Civil Work |  | Location No. 04/0
Tower Foundation |  | Civil Work |  | Location No. 05/0
Tower Foundation |  | Civil Work |  | Location No. 06/0
Tower Foundation |  | Earthing |  | Location No. 01/0
Tower Foundation |  | Earthing |  | Location No. 02/0
Tower Foundation |  | Earthing |  | Location No. 03/0
Tower Foundation |  | Earthing |  | Location No. 04/0
Tower Foundation |  | Earthing |  | Location No. 05/0
Tower Foundation |  | Earthing |  | Location No. 06/0
Tower Erection |  | Location No. 01/0
Tower Erection |  | Location No. 02/0
Tower Erection |  | Location No. 03/0
Tower Erection |  | Location No. 04/0
Tower Erection |  | Location No. 05/0
Tower Erection |  | Location No. 06/0
Tack welding |  | Location No. 01/0
Tack welding |  | Location No. 02/0
Tack welding |  | Location No. 03/0
Tack welding |  | Location No. 04/0
Tack welding |  | Location No. 05/0
Tack welding |  | Location No. 06/0
Conducter Stringing |  | Payout of Conducter |  | Gantry 220kV-AP-01
Conducter Stringing |  | Payout of Conducter |  | AP-01 - AP-02
Conducter Stringing |  | Payout of Conducter |  | AP-02 - AP-03
Conducter Stringing |  | Payout of Conducter |  | AP-03 - AP-04
Conducter Stringing |  | Payout of Conducter |  | AP-04 - AP-05
Conducter Stringing |  | Payout of Conducter |  | AP-05 - AP-06
Conducter Stringing |  | Payout of Conducter |  | AP006 - EXT.T0.77
Conducter Stringing |  | Final Sag |  | Gantry 220kV-AP-01
Conducter Stringing |  | Final Sag |  | AP-01 - AP-02
Conducter Stringing |  | Final Sag |  | AP-02 - AP-03
Conducter Stringing |  | Final Sag |  | AP-03 - AP-04
Conducter Stringing |  | Final Sag |  | AP-04 - AP-05
Conducter Stringing |  | Final Sag |  | AP-05 - AP-06
Conducter Stringing |  | Final Sag |  | AP006 - EXT.T0.77
Earthing/OPGW |  | Payout of OPGW |  | Gantry 220kV-AP-01
Earthing/OPGW |  | Payout of OPGW |  | AP-01 - AP-02
Earthing/OPGW |  | Payout of OPGW |  | AP-02 - AP-03
Earthing/OPGW |  | Payout of OPGW |  | AP-03 - AP-04
Earthing/OPGW |  | Payout of OPGW |  | AP-04 - AP-05
Earthing/OPGW |  | Payout of OPGW |  | AP-05 - AP-06
Earthing/OPGW |  | Payout of OPGW |  | AP006 - EXT.T0.77
Earthing/OPGW |  | Final Sag |  | Gantry 220kV-AP-01
Earthing/OPGW |  | Final Sag |  | AP-01 - AP-02
Earthing/OPGW |  | Final Sag |  | AP-02 - AP-03
Earthing/OPGW |  | Final Sag |  | AP-03 - AP-04
Earthing/OPGW |  | Final Sag |  | AP-04 - AP-05
Earthing/OPGW |  | Final Sag |  | AP-05 - AP-06
Earthing/OPGW |  | Final Sag |  | AP006 - EXT.T0.77
Testing & Commissioning