## Universal Substation WBS
UNIVERSAL SUBSTATION WBS — General Activity Checklist (All Types & Voltages)
Covers: AIS ¦ GIS ¦ Hybrid ¦ Distribution 33/11 kV ¦ Transmission/Grid ≥132 kV ¦ Switching SS ¦ Traction (Rail/Metro) ¦ Industrial/Captive ¦ Source: File 3 – All 8 Sheets
LEGEND: ✔ = Applicable to this type ¦ Cond. = Conditional / If Applicable ¦ (blank) = Not Applicable
S.No | Activity | Task | Sub-Task | Sub Sub-Task | AIS | GIS | Hybrid | Distribution (33/11 kV) | Transmission/ Grid (≥132 kV) | Switching SS | Traction (Rail/Metro) | Industrial/ Captive
1. Project Initiation & Site Setup
1.1 Project Mobilization
1 |  | Bid cost estimation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
2 |  |  | Material cost estimation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3 |  |  | Erection / civil work cost |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4 |  |  | Manpower cost estimation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5 |  |  | Equipment & machinery cost (T&P) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
6 |  | Overhead & risk provisioning |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
7 |  |  | ROW / hindrance provisioning |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
8 |  |  | Major material finalization |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
9 |  |  | Margin finalization |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10 |  | Internal approval of bid cost / electrical safety fees |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
11 |  | Bid submission |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
12 |  | Site Possession Certificate / Land Acquisition / Land NOC (DISCOM) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
1.2 Financial & Banking
13 |  | Project budget & cost code / WBS creation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
14 |  | Opening project bank account |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15 |  | Performance Bank Guarantee (PBG) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
16 |  | Advance Bank Guarantee (ABG) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
17 |  | EMD (Earnest Money Deposit) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
18 |  | Insurance |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
19 |  |  | Contractor All Risk (CAR) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
20 |  |  | Workmen Compensation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
21 |  |  | Third Party Insurance |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
22 |  |  | Marine Transit |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
23 |  |  | OSM (Official Store Material) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
24 |  |  | Erection All Risk |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
1.3 Site Establishment
25 |  | Site office & meeting room setup |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
26 |  | Store / godown setup |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
27 |  | Material unloading platform / hard standing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
28 |  | Labour hut / security hut & main gate |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
29 |  | Worker facilities (toilet, rest shelter, safety) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
30 |  | Construction power & water arrangement |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
1.4 Mobilization of Site Team
31 |  | Engineers & supervisors deployment |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
32 |  | Skilled & unskilled workforce mobilization |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
33 |  | Safety officer & quality engineer deployment |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
1.5 Construction Equipment
34 |  | Crane / hydra mobilization |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
35 |  | Excavator & tipper mobilization |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
36 |  | Welding sets / cutting tools |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
37 |  | Survey instruments (total station / level) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
38 |  | Cable pulling equipment |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
39 |  | EOT crane readiness (GIS hall) |  |  |  | ✔ | ✔ |  | ✔
1.6 Project Controls Setup
40 |  | Safety & quality plan approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
41 |  | Baseline programme (L1 / L2 / L3 schedule) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
42 |  | Document control & filing system |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
43 |  | Drawing submission & approval register |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
44 |  | Material reconciliation register |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
2. Statutory Clearances & Approvals
2.1 Land & Site Clearances
45 |  | Site Possession Certificate |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
46 |  | Land NOC / Lease agreement |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
47 |  | ROW / Easement documentation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
48 |  | Indemnity bond signing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
2.2 Environmental Clearances
49 |  | Proposal Making |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
50 |  |  | Environment / Pollution NOC |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
51 |  |  | Tree cutting permission |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
52 |  |  | EIA report (if applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
53 |  | Proposal Submission |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
54 |  |  | Environment / Pollution NOC |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
55 |  |  | Tree cutting permission |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
56 |  |  | EIA report (if applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
57 |  | Approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
58 |  |  | Environment / Pollution NOC |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
59 |  |  | Tree cutting permission |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
60 |  |  | EIA report (if applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
2.3 Electrical Statutory Approvals
61 |  | Proposal Making |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
62 |  |  | CEIG approval application |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
63 |  |  | Work authorization from utility / DISCOM |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
64 |  |  | Fire safety approval |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
65 |  |  | Building plan / local authority approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
66 |  | Proposal Submission |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
67 |  |  | CEIG approval application |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
68 |  |  | Work authorization from utility / DISCOM |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
69 |  |  | Fire safety approval |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
70 |  |  | Building plan / local authority approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
71 |  | Approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
72 |  |  | CEIG approval application |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
73 |  |  | Work authorization from utility / DISCOM |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
74 |  |  | Fire safety approval |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
75 |  |  | Building plan / local authority approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
2.4 DISCOM / Utility Interface
76 |  | Vendor approval list from DISCOM / Utility |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
77 |  | GTP / drawings / MQP submission & approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
78 |  | Manufacturing clearance from DISCOM |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3. Survey
3.1 Topographical Survey
79 |  | Data collection / field survey |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
80 |  | Proposal submission to client |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
81 |  | Approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.2 Geotechnical / Soil Investigation
82 |  | Borehole / trial pit execution |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
83 |  | Laboratory testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
84 |  | Report submission to client |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
85 |  | Approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.3 Bay / Layout Survey
86 |  | Equipment foundation marking survey |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
87 |  | Gantry / structure alignment survey |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
88 |  | GIS bay layout & hall location marking |  |  |  | ✔ | ✔ |  | ✔
89 |  | Cable corridor marking |  |  |  | ✔ | ✔ |  | ✔
90 |  | Control room location marking |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
91 |  | Switchyard layout & GA approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
92 |  | Submission to client & approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.4 Load / Feeder Survey
93 |  | Load survey & feeder mapping | [5 empty] | ✔
94 |  | Submission to client | [5 empty] | ✔
95 |  | Approval | [5 empty] | ✔
3.5 Special Surveys
96 |  | Interface survey with OHE / third rail | [8 empty] | ✔
97 |  | Process load & harmonic / power quality study | [9 empty] | ✔
98 |  | Groundwater level assessment |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4. Engineering & Design
4.1 System Studies
99 |  | Load flow study |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
100 |  | Short circuit study |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
101 |  | Protection coordination study |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
102 |  | Insulation coordination study |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
103 |  | Earthing grid calculation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
104 |  | Lightning protection design (DSLP) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4.2 Primary Design
105 |  | Approved Single Line Diagram (SLD) from utility |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
106 |  | Switchyard GA & protection scheme approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
107 |  | Layout / plan drawing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
108 |  | Busbar & bay design |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
109 |  | Gantry & equipment support structure design |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
110 |  | GIS hall architectural & layout design |  |  |  | ✔ | ✔ |  | ✔
111 |  | Equipment quantity & BOQ finalization |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4.3 Civil Design
112 |  | Foundation design – Power Transformer |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
113 |  | Foundation design – Circuit Breaker |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
114 |  | Foundation design – CT / PT / CVT / LA / Isolator |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
115 |  | Foundation design – Gantry & structures |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
116 |  | Foundation design – Control room |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
117 |  | Control room building architectural drawings |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
118 |  | Boundary wall / gate / fencing drawings |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
119 |  | Transformer fire wall / bund wall design |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
120 |  | Cable trench layout & section drawings |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
121 |  | Approach road & drainage design |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4.4 Secondary & Protection Design
122 |  | Protection design & relay setting calculations |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
123 |  | Control & metering design |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
124 |  | DC system design (battery / charger sizing) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
125 |  | Busbar protection scheme design |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
126 |  | SCADA / RTU / telecom design |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4.5 SAS Engineering (If Applicable)
127 |  | SAS architecture finalization |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
128 |  |  | SAS SLD & network topology (Ring / Star) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
129 |  |  | Redundancy philosophy |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
130 |  | GOOSE mapping |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
131 |  | IP addressing scheme |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
132 |  | IED & BCU engineering |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
133 |  | PMU integration design |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
4.6 Ancillary Systems Design
134 |  | Firefighting system design |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
135 |  | HVAC design for control room |  |  | Cond. | ✔ | ✔ | Cond. | ✔ | Cond. | Cond. | ✔
136 |  | Yard & building lighting design |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
137 |  | Treated earth pits design |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4.7 Drawing Approvals & As-Builts
138 |  | Client / utility submission |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
139 |  | Comment incorporation & re-submission |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
140 |  | Issued for Construction (IFC) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
141 |  | As-built mark-up collection from site |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
142 |  | Preparation & submission of as-built drawings |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
143 |  | Client / utility acceptance of as-builts |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5. Procurement
5.1 Vendor Finalization
144 |  | Enquiry to approved vendors (civil & electrical) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
145 |  | RFQ from minimum 3 vendors |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
146 |  | Techno-commercial evaluation & comparison |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
147 |  | Vendor finalization & Purchase Order (PO) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
148 |  | Guarantee / warranty certificate |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
149 |  | Performance certificate from vendor |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5.2 Vendor Approval from DISCOM
150 |  | Request letter to DISCOM for vendor approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
151 |  | Vendor approval received from DISCOM |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
152 |  | Factory approval for major equipment |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
153 |  | GTP / drawings / MQP submission & request letter |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
154 |  | Manufacturing clearance to vendor with approved GTP |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5.3 Factory Inspection & Dispatch
155 |  | Inspection date finalization |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
156 |  | Inspection call from vendors to contractor |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
157 |  | Submission of inspection call to DISCOM |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
158 |  | DISCOM nomination letter & forwarding to vendors |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
159 |  | Material inspection by DISCOM at vendor works |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
160 |  | Dispatch instructions from DISCOM to contractor |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
161 |  | Dispatch of materials with balance payment |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5.4 Power Transformer
162 |  | Technical specification & BOQ |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
163 |  | Vendor evaluation & PO |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
164 |  | Factory inspection & FAT |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
165 |  | Dispatch clearance from DISCOM |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
166 |  | Transportation to site |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
5.5 Switchgear & Primary Equipment
167 |  | 33 kV VCB (Incomer / Outcomer) / RMU |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
168 |  | GIS equipment (factory-assembled bays) |  |  |  | ✔ | ✔ |  | ✔
169 |  | Control panel |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
170 |  | 11 kV indoor / outdoor VCB panels |  |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
171 |  | CTs & PTs (33 kV & 11 kV) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
172 |  | EHV circuit breakers |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
173 |  | Isolators & earth switches |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
174 |  | Gantry structure |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
175 |  | Lightning arresters |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
176 |  | Busbars & insulators |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5.6 SAS Equipment (If Applicable)
177 |  | IED procurement |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
178 |  | Bay Control Unit (BCU) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
179 |  | Station HMI & server |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
180 |  | Ethernet switches & GPS time sync system |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
181 |  | Fiber optic patch panel & FO cables |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
182 |  | Factory inspection & FAT |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
5.7 Protection & Control Equipment
183 |  | Control & relay panels |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
184 |  | Busbar protection panel |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
185 |  | Bus coupler (if applicable) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
186 |  | Metering equipment |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
187 |  | RTU / gateway |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
188 |  | SCADA system |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
189 |  | Battery & battery charger (110V DC / 48V DC) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5.8 Electrical Materials
190 |  | Power & control cables – BOQ & PO |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
191 |  | Optical fiber cables – BOQ & PO |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
192 |  | Cable trays / supports / accessories – BOQ & PO |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
193 |  | Lugs / glands / PG clamps – BOQ & PO |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
194 |  | Earthing materials (GI flat / copper / electrodes) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5.9 Civil Materials
195 |  | Cement – BOQ & PO |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
196 |  | Steel & iron – BOQ & PO |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
197 |  | Aggregates – BOQ & PO |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
198 |  | Bricks / blocks – BOQ & PO |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5.10 Material Management at Site
199 |  | Material receipt & entry into store / warehouse |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
200 |  | Storage & preservation at site |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
201 |  | Material reconciliation reports |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
202 |  | DISCOM inspection & indemnity bond signing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
203 |  | Cartage from DISCOM store (if applicable) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
6. Site Development
6.1 Site Clearing
204 |  | Vegetation & tree clearance |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
205 |  | Demolition of existing structures (if any) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
206 |  | Debris removal & disposal |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
6.2 Earthwork
207 |  | Setting out & benchmark establishment |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
208 |  | Bulk excavation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
209 |  | Excavation for AIS equipment foundations |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
210 |  | Excavation for GIS plinths & cable basement |  |  |  | ✔ | ✔ |  | ✔
211 |  | Filling & compaction |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
212 |  | Site grading & leveling |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
213 |  | Terrace formation (if sloped terrain) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
6.3 Access
214 |  | Approach road formation & surfacing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
215 |  | Temporary haul roads |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
216 |  | Barricading, fencing & safety signage |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
7. Civil Works
7.1 Perimeter & Access
217 |  | Boundary Wall |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
218 |  |  | Setting out |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
219 |  |  | Foundation – excavation & PCC / RCC |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
220 |  |  | Brickwork / masonry |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
221 |  |  | Plastering & finishing |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
222 |  | Main Gate |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
223 |  |  | Foundation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
224 |  |  | Gate fabrication & erection |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
225 |  |  | Finishing & painting |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
226 |  | Security Fence |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
227 |  |  | Post installation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
228 |  |  | Fencing wire / mesh fixing |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
7.2 Control Room Building
229 |  | Foundation – excavation & PCC / RCC |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
230 |  | RCC columns & beams |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
231 |  | Brickwork & internal / external plaster |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
232 |  | Roofing & waterproofing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
233 |  | Flooring & anti-static / false flooring (if required) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
234 |  | Doors / windows / rolling shutters |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
235 |  | Painting & finishing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
236 |  | Battery room (if required) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
237 |  | Switchyard panel room (if applicable) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
7.3 GIS Hall
238 |  | Foundation |  |  |  | ✔ | ✔ |  | ✔
239 |  | Steel structure erection |  |  |  | ✔ | ✔ |  | ✔
240 |  | Roofing & cladding |  |  |  | ✔ | ✔ |  | ✔
241 |  | Flooring |  |  |  | ✔ | ✔ |  | ✔
242 |  | Cable basement / trench interface |  |  |  | ✔ | ✔ |  | ✔
243 |  | EOT crane beam & rail |  |  |  | ✔ | ✔ |  | ✔
244 |  | Doors & windows |  |  |  | ✔ | ✔ |  | ✔
245 |  | Finishing & painting |  |  |  | ✔ | ✔ |  | ✔
7.4 Ancillary Buildings
246 |  | Relay / telecom room |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
247 |  | Store & security building |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
248 |  | Fire fighting pump house |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
249 |  | Septic tank & soak pit |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
250 |  | Water tank |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
7.5 Equipment Foundations
251 |  | Power Transformer Foundation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
252 |  |  | Setting out & excavation |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
253 |  |  | PCC & RCC casting |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
254 |  |  | Anchor bolt setting |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
255 |  |  | Curing & backfilling |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
256 |  | Circuit Breaker Foundation |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
257 |  |  | Setting out & excavation |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
258 |  |  | PCC & RCC casting |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
259 |  |  | Curing |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
260 |  | CT / PT / CVT / Surge Arrester Foundation |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
261 |  |  | Setting out & excavation |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
262 |  |  | PCC & RCC casting |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
263 |  |  | Curing |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
264 |  | Isolator / Disconnector Foundation |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
265 |  |  | Setting out & excavation |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
266 |  |  | PCC & RCC casting |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
267 |  |  | Curing |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
268 |  | Gantry Foundation |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
269 |  |  | Setting out & excavation |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
270 |  |  | PCC & RCC casting |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
271 |  |  | Anchor bolt setting |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
272 |  |  | Curing & backfilling |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
273 |  | 33 kV Equipment Foundation |  |  | ✔ |  | ✔ | ✔
274 |  |  | Setting out & excavation |  | ✔ |  | ✔ | ✔
275 |  |  | PCC & RCC casting |  | ✔ |  | ✔ | ✔
276 |  |  | Curing |  | ✔ |  | ✔ | ✔
277 |  | 11 kV Switchgear Foundation |  |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
278 |  |  | Setting out & excavation |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
279 |  |  | PCC & RCC casting |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
280 |  |  | Curing |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
281 |  | Lighting mast foundation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
282 |  | Bay marshalling box foundation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
283 |  | DG foundation (if required) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
284 |  | Control room foundation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
285 |  | LT transformer foundation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
286 |  | Traction transformer / rectifier foundation | [8 empty] | ✔
7.6 Transformer Containment
287 |  | Oil Soak Pit |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
288 |  |  | Excavation |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
289 |  |  | RCC casting |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
290 |  |  | Waterproofing |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
291 |  |  | Oil drain pipe connection |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
292 |  | Bund Wall |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
293 |  |  | Construction |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
294 |  |  | Waterproofing |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
295 |  | Fire Wall |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
296 |  |  | Construction |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
297 |  |  | Finishing |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
7.7 Cable Civil Works
298 |  | Cable Trench |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
299 |  |  | Setting out |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
300 |  |  | Excavation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
301 |  |  | RCC casting |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
302 |  |  | Trench cover placement |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
303 |  | Cable Ducts & Conduits |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
304 |  |  | Duct / conduit laying |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
305 |  |  | Sealing & backfilling |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
306 |  | Cable Pits & Manholes |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
307 |  |  | Excavation & RCC construction |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
308 |  |  | Cover slab placement |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
7.8 Drainage & Water
309 |  | Storm Water Drainage |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
310 |  |  | Drain excavation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
311 |  |  | Pipe laying & jointing |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
312 |  |  | Backfilling & compaction |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
313 |  | Sewer System |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
314 |  | Water Supply |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
315 |  | Rain Water Harvesting System |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
316 |  | Fire Water Tank |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
317 |  |  | Foundation & tank construction |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
318 |  |  | Plumbing connections |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
319 |  | Pump House |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
320 |  |  | Construction |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
321 |  |  | Pump & motor installation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
7.9 Yard & Roads
322 |  | Yard gravelling / hard standing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
323 |  | Internal roads – sub-base & surface course |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
324 |  | Kerbing & road markings |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
8. Earthing System
8.1 Earth Mat
325 |  | Excavation for earth mat grid |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
326 |  | GI flat / copper conductor laying |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
327 |  | Joints & exothermic / bolted connections |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
328 |  | Backfilling & compaction |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
8.2 Earth Electrodes & Pits
329 |  | Pipe / plate electrode installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
330 |  | Chemical / treated earth pit |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
331 |  | Earth pit testing pre-burial |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
8.3 Earth Risers
332 |  | Riser connection to equipment bases |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
333 |  | Riser connection to structures & gantries |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
334 |  | Riser connection to building / control room |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
8.4 Equipment Earthing
335 |  | Primary equipment body earthing (double earthing) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
336 |  | Secondary panel & control room earthing (clean earth) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
337 |  | GIS enclosure earthing |  |  |  | ✔ | ✔ |  | ✔
8.5 Lightning Protection
338 |  | Lightning mast / air terminal installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
339 |  | Down conductor installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
340 |  | Bonding to earth mat |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
341 |  | Anti-climbing device (ACD) installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
8.6 Earthing Testing & Acceptance
342 |  | Earth resistance measurement (all pits) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
343 |  | Earth mat continuity check |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
344 |  | Step & touch potential verification |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
345 |  | Utility / client acceptance |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
9. Structural Steel & Gantries
9.1 Gantry Structures
346 |  | Gantry fabrication & trial assembly |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
347 |  | Foundation bolt setting check |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
348 |  | Gantry erection & alignment |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
349 |  | Grouting & fixing |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
350 |  | Painting & finishing |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
9.2 Equipment Support Structures
351 |  | LA structure erection |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
352 |  | CT / PT / CVT structure erection |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
353 |  | Circuit breaker support structure erection |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
354 |  | Isolator / disconnector structure erection |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
355 |  | 33 kV VCB / RMU structure (Distribution) |  |  | ✔ |  | ✔ | ✔
356 |  | Cable support structure erection |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
9.3 Bus Support Structures
357 |  | Post insulator structure erection |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
358 |  | Bus clamps & fittings installation |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
9.4 Platforms, Ladders & Safety
359 |  | Steel platform erection |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
360 |  | Handrail & ladder installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
361 |  | Fire fighting pipe supports |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10. Primary Equipment Installation
10.1 Power Transformer
362 |  | Unloading & shifting to foundation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
363 |  | Placement & alignment on foundation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
364 |  | Oil filtration & filling |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
365 |  | Radiator & cooling equipment mounting |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
366 |  | Buchholz relay & PRD piping |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
367 |  | Conservator & breather installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
368 |  | Marshalling box mounting & wiring |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
369 |  | OLTC drive mechanism installation |  |  | Cond. | Cond. | Cond. | Cond. | Cond. |  | Cond. | Cond.
370 |  | Transformer fencing & gravel spreading |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
371 |  | Fire fighting system integration |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
372 |  | HV / LV terminal connections |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
373 |  | Earthing (neutral / body / phase) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
10.2 Circuit Breakers (AIS / HYB)
374 |  | Unloading & positioning |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
375 |  | Erection & alignment on foundation |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
376 |  | SF6 / vacuum filling |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
377 |  | Operating mechanism adjustment |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
378 |  | Local control panel wiring |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10.3 Disconnectors / Isolators (AIS / HYB)
379 |  | Structure & base erection |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
380 |  | Isolator head mounting |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
381 |  | Blade alignment & adjustment |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
382 |  | Motor / manual mechanism installation |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
383 |  | Interlock mechanism adjustment |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
384 |  | Control wiring |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10.4 Earth Switches (AIS / HYB)
385 |  | Erection & alignment |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
386 |  | Interlock mechanism installation |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
387 |  | Control wiring |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10.5 Current Transformers (AIS / HYB)
388 |  | Unloading & erection on structure |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
389 |  | Primary terminal connection |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
390 |  | Secondary terminal box wiring |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
391 |  | Oil / SF6 filling (if applicable) |  |  | Cond. |  | C | Cond. | Cond. | Cond. | Cond. | Cond.
10.6 CVTs / PTs (AIS / HYB)
392 |  | Unloading & erection on structure |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
393 |  | Primary terminal connection |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
394 |  | Secondary terminal box wiring |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10.7 Surge Arresters (AIS / HYB)
395 |  | Erection on structure |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
396 |  | Primary terminal connection |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
397 |  | Counter / monitor installation |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
398 |  | Earthing of counter |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10.8 GIS Installation
399 |  | GIS hall cleanliness & environment verification |  |  |  | ✔ | ✔ |  | ✔
400 |  | GIS bay module shifting & positioning |  |  |  | ✔ | ✔ |  | ✔
401 |  | Mechanical assembly of GIS modules |  |  |  | ✔ | ✔ |  | ✔
402 |  | Torque control |  |  |  | ✔ | ✔ |  | ✔
403 |  | SF6 compartment sealing |  |  |  | ✔ | ✔ |  | ✔
404 |  | Bus duct connections |  |  |  | ✔ | ✔ |  | ✔
405 |  | Transformer-GIS bus duct connection |  |  |  | ✔ | ✔ |  | ✔
406 |  | Cable sealing end installation |  |  |  | ✔ | ✔ |  | ✔
407 |  | GIS CT / PT / LA integration |  |  |  | ✔ | ✔ |  | ✔
408 |  | GIS earth switch installation |  |  |  | ✔ | ✔ |  | ✔
409 |  | Local control cubicle (LCC) installation |  |  |  | ✔ | ✔ |  | ✔
410 |  | EOT crane commissioning |  |  |  | ✔ | ✔ |  | ✔
10.9 33 kV Yard Equipment (Distribution)
411 |  | 33 kV VCB / RMU erection & alignment |  |  | ✔ |  | ✔ | ✔
412 |  | CT & PT installation |  |  | ✔ |  | ✔ | ✔
413 |  | Lightning arrester installation |  |  | ✔ |  | ✔ | ✔
414 |  | Bus & jumper connections |  |  | ✔ |  | ✔ | ✔
10.10 11 kV Switchgear (Distribution)
415 |  | Panel unloading & placement |  |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
416 |  | Bus coupler installation (if two incomers) |  |  | Cond. | Cond. | Cond. | Cond. |  |  |  | Cond.
417 |  | Busbar installation & connections |  |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
418 |  | Inter-panel connections |  |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
10.11 Busbar & Conductors (AIS / HYB)
419 |  | Rigid / twin / quad bus / ACSR stringing |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
420 |  | Jumper fabrication & fixing |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
421 |  | Strain clamp & hardware fittings |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
422 |  | Tightening & torque check |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
423 |  | BPI insulator (if required) |  |  | Cond. |  | C | Cond. | Cond. | Cond. | Cond. | Cond.
10.12 Special Equipment
424 |  | Capacitor banks / reactors (Industrial SS) | [9 empty] | ✔
425 |  | HT switchgear erection (Industrial SS) | [9 empty] | ✔
426 |  | Traction transformer / rectifier / converter | [8 empty] | ✔
11. Secondary System Installation
11.1 Control & Relay Panels
427 |  | Panel unloading & shifting to control room |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
428 |  | Panel layout marking on floor |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
429 |  | Panel erection / alignment / grouting / fixing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
430 |  | Configure protection relays |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
431 |  |  | Relay setting calculation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
432 |  |  | Parameter configuration |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
433 |  |  | Logic testing |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
434 |  | Busbar protection panel installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
435 |  | Inter-panel wiring |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
436 |  | Internal wiring checks |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
437 |  |  | Continuity check |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
438 |  |  | Megger test |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
439 |  |  | Ferrule verification |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
11.2 SAS / IEC 61850 System (If Applicable)
440 |  | SAS network installation & IED configuration upload |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
441 |  |  | LAN setup & switch configuration |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
442 |  |  | IED IP mapping & configuration upload |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
443 |  | SAS server & HMI installation |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
444 |  |  | Server rack mounting & software installation |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
445 |  |  | HMI screen installation & configuration |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
446 |  | FO patch cord connections |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
11.3 RTU / Gateway & SCADA
447 |  | RTU installation & configuration |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
448 |  |  | RTU rack mounting & I/O mapping |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
449 |  |  | Protocol configuration (IEC 60870-5-104 / 101) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
450 |  | SCADA server & HMI installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
451 |  |  | Server rack mounting |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
452 |  |  | Software installation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
453 |  |  | HMI screen installation & wiring |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
454 |  | PMU panel installation (if applicable) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
455 |  |  | PMU mounting & GPS time sync setup |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
11.4 Telecom & Communication Equipment
456 |  | Telecom rack installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
457 |  | OFC equipment (SDH / MPLS) installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
458 |  | Patch panel installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
459 |  | Telecom wiring & patching |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
460 |  | Rack mounting – DPLC / FOTE |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
461 |  |  | SDH equipment |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
462 |  |  | OLTE / Ethernet switch / media converter |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
463 |  |  | Teleprotection terminal / FO modem / FODP |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
464 |  | PLCC / VOIP / PABX integration (if required) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
465 |  | NMS integration |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
466 |  | PDC integration (if applicable) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
11.5 Automation & Metering
467 |  | Energy meters installation & CT/PT integration |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
468 |  | GIS asset mapping & asset tagging (GPS) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
469 |  | PLC / DCS interfacing (Industrial SS) | [9 empty] | ✔
470 |  |  | Signal mapping & logic integration | [8 empty] | ✔
12. Auxiliary System Installation
12.1 Station Service Transformer
471 |  | SST / substation DT erection |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
472 |  | HV & LV terminations |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
473 |  | Earthing connections |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
12.2 AC Distribution
474 |  | ACDB installation & wiring |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
475 |  | Station AC supply cabling |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
476 |  | LT cable connections to loads |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
12.3 DC Distribution
477 |  | DCDB installation & wiring |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
478 |  | DC loop wiring |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
479 |  | Fuse / MCB installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
12.4 Battery Bank & Charger
480 |  | Battery rack installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
481 |  | Battery cell placement & interconnection |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
482 |  | Battery charger installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
483 |  | Terminal connections |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
484 |  | Electrolyte filling (VRLA / flooded if applicable) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
12.5 UPS System
485 |  | UPS installation & wiring |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
486 |  | Bypass switch connection |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
12.6 DG Set (If Required)
487 |  | DG installation & fuel system |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
488 |  | Synchronization setup |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
12.7 Lighting System
489 |  | Yard lighting – high mast erection, cabling, focusing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
490 |  | Control room / building lighting |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
491 |  | Emergency lighting |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
492 |  | Lighting distribution board (LDB) installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
12.8 HVAC & Ventilation
493 |  | AC unit installation (control room) |  |  | Cond. | ✔ | ✔ | Cond. | ✔ | Cond. | Cond. | ✔
494 |  | AHU installation |  |  |  | ✔ | ✔ |  | ✔ |  |  | ✔
495 |  | Ducting & insulation |  |  |  | ✔ | ✔ |  | ✔ |  |  | ✔
496 |  | Temperature balancing |  |  |  | ✔ | ✔ |  | ✔ |  |  | ✔
497 |  | Ventilation fan & ductwork |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
498 |  | Thermostat & controls |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
12.9 Fire Protection & Detection
499 |  | Fire detection sensor installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
500 |  | Fire alarm panel installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
501 |  | Fire alarm cabling |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
502 |  | Fire suppression system (FM200 / CO2 / HVWS / NIFPES) |  |  | Cond. | ✔ | ✔ | Cond. | ✔ | Cond. | Cond. | Cond.
503 |  | Fire hydrant & hose reel |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
504 |  | Fire fighting pipe work |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
505 |  | SF6 gas detector installation (GIS) |  |  |  | ✔ | ✔ |  | ✔
506 |  | Smoke detection / extraction system |  |  |  | ✔ | ✔ |  | ✔
507 |  | Fire extinguisher provision |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
12.10 Electronic Security
508 |  | CCTV camera installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
509 |  | DVR / NVR installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
510 |  | Access control system |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
511 |  | Intrusion alarm system |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
512 |  | VMS installation (if required) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
13. Cable Works
13.1 Cable Tray & Support Installation
513 |  | Cable tray erection |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
514 |  | Cable tray support brackets |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
515 |  | Conduit / rigid pipe installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
516 |  | GI pipe / GI elbow installation for cable protection |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
13.2 Power Cable Laying
517 |  | Cable route marking |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
518 |  | Power cable pulling & laying |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
519 |  | Cable identification & numbering |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
13.3 Control Cable Laying
520 |  | Control & protection cable laying |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
521 |  | Cable tray routing & clamping |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
522 |  | AIS to GIS control cabling |  |  |  |  | ✔
523 |  | Transformer–GIS interface cabling |  |  |  | ✔ | ✔ |  | ✔
524 |  | OLTE / FOA / SCADA communication cabling |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
13.4 Optical Fiber Cable Laying
525 |  | FO cable pulling & laying |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
526 |  | FO splicing & termination |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
527 |  | FODP installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
528 |  | OTDR testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
13.5 Cable Dressing & Tagging
529 |  | Cable dressing & cleating |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
530 |  | Ferruling & tagging |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
531 |  | Cable schedule preparation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
13.6 Glanding & Termination
532 |  | Cable glanding |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
533 |  | Cable termination at panels |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
534 |  | Cable termination at field equipment |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
535 |  | HV / MV cable jointing (if applicable) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
13.7 Panel & Marshalling Wiring
536 |  | Marshalling kiosk wiring |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
537 |  | Panel internal wiring |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
538 |  | Terminal block connections |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
539 |  | Wiring continuity check |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
14. Protection, Control & SCADA
14.1 Relay Setting & Configuration
540 |  | Relay setting calculation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
541 |  | Setting upload to relay / IED |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
542 |  | Setting verification & sign-off |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
14.2 Logic & Scheme Configuration
543 |  | Protection logic programming |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
544 |  | Auto-reclose / AVR logic |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
545 |  | Alarm & event configuration |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
14.3 Interlocking Checks
546 |  | Mechanical interlock verification |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
547 |  | Electrical interlock testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
548 |  | Scheme interlock testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
549 |  | Emergency stop testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
550 |  | Trip circuit supervision testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
14.4 RTU & SCADA Configuration
551 |  | RTU point mapping & configuration |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
552 |  | SCADA database build |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
553 |  | Signal list verification |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
554 |  | Point-to-point signal testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
555 |  | End-to-end communication test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
556 |  | Alarm & event testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
557 |  | Remote SCADA integration testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
14.5 IEC 61850 & SAS Configuration (If Applicable)
558 |  | IED GOOSE configuration & binding |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
559 |  | SAS network configuration |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
560 |  | Time synchronization (GPS / PTP) setup |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
561 |  | MMS communication test |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
562 |  | Site Acceptance Test (SAT) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
563 |  | Integration test – SAS + SCADA + RTU validation |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
14.6 Telecom Integration
564 |  | Telecom system integration |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
565 |  | Voice communication (VOIP / PABX) setup |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
566 |  | PLCC channel testing (132 kV+) | [6 empty] | ✔ | ✔
567 |  | Teleprotection testing (132 kV+) | [6 empty] | ✔ | ✔
14.7 Cybersecurity / OT Hardening
568 |  | OT network segmentation & VLAN configuration |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
569 |  | Firewall rules configuration |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
570 |  | User access management & passwords |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
571 |  | OT security audit & sign-off |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15. Testing & Commissioning
15.1 Transformer Pre-Commissioning Tests
572 |  | Turns ratio test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
573 |  | Insulation resistance (IR) test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
574 |  | Oil sampling & dissolved gas analysis (DGA) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
575 |  | Tan-delta test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
576 |  | Magnetizing current test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
577 |  | DC resistance test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
578 |  | Buchholz & PRD functional check |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
15.2 Circuit Breaker Tests
579 |  | Contact resistance test |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
580 |  | Timing test (open / close / O-C) |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
581 |  | Insulation resistance test |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
582 |  | SF6 pressure & quality check |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
583 |  | Mechanism functional test |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15.3 CT Tests
584 |  | Ratio & polarity test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
585 |  | Magnetization / knee point curve |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
586 |  | Insulation resistance test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
587 |  | Burden measurement |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15.4 CVT / PT Tests
588 |  | Ratio & polarity test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
589 |  | Insulation resistance test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
590 |  | Tan-delta test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15.5 Isolator / Disconnector Tests
591 |  | Contact resistance test |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
592 |  | Alignment & operation check |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
593 |  | Motor mechanism functional test |  |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15.6 GIS Tests
594 |  | SF6 gas quality & purity test |  |  |  | ✔ | ✔ |  | ✔
595 |  | SF6 leak test (ppm / year) |  |  |  | ✔ | ✔ |  | ✔
596 |  | HV withstand / partial discharge (PD) test |  |  |  | ✔ | ✔ |  | ✔
597 |  | GIS interlock & logic test |  |  |  | ✔ | ✔ |  | ✔
15.7 Cable Tests
598 |  | Insulation resistance (IR) test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
599 |  | Hi-pot / VLF withstand test |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
600 |  | Continuity test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
601 |  | Sheath test |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
602 |  | OTDR test (fiber) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15.8 Battery & Charger Tests
603 |  | Battery capacity discharge test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
604 |  | Charger output & regulation test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
605 |  | DC system endurance test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
606 |  | UPS changeover test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15.9 Protection Secondary Injection Tests
607 |  | Overcurrent & earth fault relay testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
608 |  | Differential relay testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
609 |  | Distance relay testing | [6 empty] | ✔ | ✔
610 |  | Busbar protection testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
611 |  | Auto-reclose relay testing |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
612 |  | Trip circuit supervision testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
613 |  | Lockout relay testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
614 |  | Line protection testing (Switching SS) | [7 empty] | ✔
15.10 Metering Verification
615 |  | Meter accuracy check |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
616 |  | CT / PT ratio verification |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
617 |  | Energy meter testing & sealing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15.11 Auxiliary & Ancillary Systems Testing
618 |  | AC / DC auxiliary supply verification |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
619 |  | Lighting & small power test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
620 |  | HVAC functional test |  |  | Cond. | ✔ | ✔ | Cond. | ✔ | Cond. | Cond. | ✔
621 |  | Fire detection & alarm test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
622 |  | Fire suppression system test |  |  | Cond. | ✔ | ✔ | Cond. | ✔ | Cond. | Cond. | Cond.
623 |  | CCTV & access control test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
624 |  | DG load test (if applicable) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
625 |  | Protocol testing – IEC 61850 / Modbus |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
15.12 System Integration Testing
626 |  | Bay functional test (local & remote) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
627 |  | Inter-bay interlock testing |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
628 |  | SCADA point-to-point & end-to-end test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
629 |  | IEC 61850 GOOSE message test (if applicable) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
630 |  | Teleprotection end-to-end test (132 kV+) | [6 empty] | ✔ | ✔
631 |  | Control room simulation test |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15.13 Pre-Commissioning Review
632 |  | Protection coordination final check |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
633 |  | Trial run (no-load operation) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
634 |  | Client / utility inspection & punch list |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
635 |  | Punch list closure |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
16. Energization & Handover
16.1 Outage Coordination & Safety
636 |  | Outage request & SLDC / DISCOM coordination |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
637 |  | Safety clearance & permit to work (PTW) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
638 |  | Isolation & earthing verification |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
639 |  | Safety audit before energization |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
16.2 Energization
640 |  | 33 kV bus / HV line charging |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
641 |  | Transformer energization (no-load) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
642 |  | Bus voltage & phase verification |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
643 |  | 11 kV feeder energization & load transfer |  |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
644 |  | Line energization – charging test (Switching SS) | [7 empty] | ✔
645 |  | Grid synchronization (Transmission >132 kV) | [6 empty] | ✔
646 |  | Synchronization with plant load (Industrial SS) | [9 empty] | ✔
647 |  | Continuous traction load test (Traction SS) | [8 empty] | ✔
648 |  | Reliability run (72-hour continuous) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
16.3 Post-Energization Checks
649 |  | Protection stability check under load |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
650 |  | Metering verification under load |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
651 |  | SCADA readings verification under load |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
652 |  | Power quality validation (Industrial SS) | [9 empty] | ✔
16.4 Documentation & Handover
653 |  | As-built drawings final submission |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
654 |  | Test reports compilation & submission |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
655 |  | O&M manuals handover |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
656 |  | Spare parts list & handover |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
657 |  | Warranty documents compilation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
658 |  | Final commissioning dossier |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
659 |  | OEM supervision records & gas handling logs (GIS) |  |  |  | ✔ | ✔ |  | ✔
16.5 Training
660 |  | Operations training to utility / client staff |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
661 |  | Maintenance training |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
662 |  | Emergency response training |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
16.6 Acceptance
663 |  | PAC (Provisional Acceptance Certificate) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
664 |  | Site reinstatement / rehabilitation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
665 |  | Defects liability period monitoring |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
666 |  | FAC (Final Acceptance Certificate) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
17. HSE & Quality (Ongoing)
17.1 Health & Safety Management
667 |  | Safety plan preparation & approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
668 |  | Toolbox talks (daily) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
669 |  | PPE compliance monitoring |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
670 |  | Permit to work (PTW) system |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
671 |  | Safety audits & inspections |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
672 |  | Incident reporting & investigation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
673 |  | Emergency response drill |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
674 |  | Working at height safety |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
675 |  | Electrical safety (LV / HV awareness) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
676 |  | Anti-climbing device (ACD) installation |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
677 |  | Panel room safety items (sand bucket, extinguisher, mats) |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
678 |  | VMS installation (if required) |  |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
17.2 Quality Management
679 |  | ITP (Inspection & Test Plan) preparation & approval |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
680 |  | Stage-wise quality checks & sign-off |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
681 |  | NCR (Non-Conformance Report) issuance & closure |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
682 |  | Calibration records management |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
683 |  | Third-party inspection coordination |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
684 |  | Material test certificates (MTC) verification |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
685 |  | OEM stage approvals (GIS / special equipment) |  |  | Cond. | ✔ | ✔ | Cond. | ✔ | Cond. | Cond. | Cond.
686 |  | Cleanliness & torque records |  |  | Cond. | ✔ | ✔ | Cond. | ✔ | Cond. | Cond. | Cond.
17.3 Environmental Controls
687 |  | Waste management plan |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
688 |  | Oil spill prevention & containment |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
689 |  | Noise & dust control |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
690 |  | Hazardous material handling |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
691 |  | Environmental monitoring reports |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
692 |  | SF6 gas handling & leak prevention |  |  |  | ✔ | ✔ |  | ✔