## Universal Substation WBS
UNIVERSAL SUBSTATION WBS — GENERAL ACTIVITY CHECKLIST
Applicable to: AIS ¦ GIS ¦ Hybrid ¦ Distribution (33/11 kV) ¦ Transmission/Grid (132–400 kV) ¦ Switching ¦ Traction (Rail/Metro) ¦ Industrial/Captive ¦ Source: File 3 – All Sheets
S.No | Activity | Task | Sub-Task / Activity Description | Notes / Remarks | AIS (Air Insulated) | GIS (Gas Insulated) | Hybrid (AIS+GIS) | Distribution (33/11 kV) | Transmission/ Grid (≥132 kV) | Switching SS | Traction (Rail/Metro) | Industrial/ Captive | Legend
| 1. Project Initiation & Site Setup | [11 empty] | ✔ = Applicable to this type
|  | 1.1 Project Mobilization | [10 empty] | Cond. = Conditional / If Applicable
1 |  |  | Bid cost estimation (material, erection, civil) | Material+erection+civil cost | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | (blank) = Not Applicable
2 |  |  | Manpower cost estimation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Source: File 3 – All 8 Sheets
3 |  |  | Equipment & machinery cost (T&P) | Tools and plant | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4 |  |  | Overhead & risk provisioning (ROW / Hindrance / Major material) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5 |  |  | Margin finalization |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
6 |  |  | Internal approval of bid cost / Electrical safety fees approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
7 |  |  | Bid submission |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
8 |  |  | Site Possession Certificate / Land Acquisition / Land NOC (DISCOM) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
1.2 Financial & Banking
9 |  |  | Project budget creation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10 |  |  | Cost code / WBS creation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
11 |  |  | Opening project bank account |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
12 |  |  | Performance Bank Guarantee (PBG) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
13 |  |  | Advance Bank Guarantee (ABG) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
14 |  |  | EMD (Earnest Money Deposit) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
15 |  |  | Insurance (CAR / Workmen Compensation / Third Party / Marine / OSM / Erection All Risk) | CAR, WC, TP, Marine, OSM, EAR | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
2. Statutory Clearances & Mobilization
2.1 Statutory Approvals
16 |  |  | Local authority permissions |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
17 |  |  | Electrical Inspector approval (CEIG) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
18 |  |  | Fire safety approval (where applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
19 |  |  | Environment / Pollution NOC |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
20 |  |  | Work authorization from utility / DISCOM |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
2.2 Mobilization
21 |  |  | Mobilization of engineers, supervisors & workmen |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
22 |  |  | Safety & Quality plan approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
23 |  |  | Site office & meeting room setup |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
24 |  |  | Construction power & water arrangement | Borewell or water tanker | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
25 |  |  | Material storage & godown setup |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
26 |  |  | Worker facilities (toilet, rest shelter, safety) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
27 |  |  | Site barricading, fencing & safety signage |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
28 |  |  | Material unloading platforms / hard standings |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
29 |  |  | Labour hut / security hut & main gate |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3. Procurement
3.1 Vendor Finalization
30 |  |  | Enquiry to approved vendors (civil & electrical) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
31 |  |  | Vendor-to-item mapping for procurement |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
32 |  |  | RFQ from minimum 3 vendors |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
33 |  |  | Comparison of rates / quality evaluation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
34 |  |  | Finalization of vendors & Purchase Order (PO) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
35 |  |  | Guarantee / Warranty certificate from vendor |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
36 |  |  | Performance certificate from vendor |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.2 Vendor Approval from DISCOM / Utility
37 |  |  | Request letter to DISCOM for vendor approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
38 |  |  | Vendor approval received from DISCOM |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
39 |  |  | Factory approval (for major equipment) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
40 |  |  | GTP / drawings / MQP submission to DISCOM | Manufacturing Quality Plan | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
41 |  |  | Manufacturing clearance to vendor with approved GTP |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.3 Factory Inspection & Dispatch
42 |  |  | Inspection date finalization | Mfg clearance + supply dates | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
43 |  |  | Inspection call from all vendors to contractor |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
44 |  |  | Submission of inspection call to DISCOM |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
45 |  |  | DISCOM nomination letter issuance & forwarding to vendors |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
46 |  |  | Material inspection by DISCOM at vendor works |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
47 |  |  | Dispatch instructions by DISCOM to contractor |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
48 |  |  | Dispatch of materials with balance payment |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.4 Material Receipt & Store
49 |  |  | Entry of material into warehouse / central store |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
50 |  |  | Storage & preservation at store |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
51 |  |  | Material reconciliation reports |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
52 |  |  | Cartage of material from DISCOM (if applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
53 |  |  | DISCOM inspection & signing of indemnity bond at store |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.5 Power Transformer
54 |  |  | Technical specification & BOQ | 33/11 kV or higher rating | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
55 |  |  | Vendor evaluation & PO |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
56 |  |  | Factory inspection & FAT |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
57 |  |  | Dispatch clearance from DISCOM |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
58 |  |  | Transportation to site |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.6 Switchgear & Primary Equipment
59 |  |  | 33 kV VCB (Incomer/Outcomer) / RMU |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
60 |  |  | GIS equipment procurement | Factory assembled bays |  | ✔ | ✔ |  | ✔
61 |  |  | Control panel |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
62 |  |  | 11 kV indoor / outdoor VCB panels (Incomer & Outgoing) |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
63 |  |  | CTs & PTs (33 kV & 11 kV) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
64 |  |  | Gantry structure |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
65 |  |  | Lightning arresters |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
66 |  |  | Busbars & insulators |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
67 |  |  | Circuit breakers (EHV) |  | ✔ |  | ✔ |  | ✔ | ✔ | ✔
68 |  |  | Isolators & earth switches |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.7 SAS Equipment (If Applicable)
69 |  |  | IED procurement |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
70 |  |  | Bay Control Unit (BCU) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
71 |  |  | Station HMI & server |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
72 |  |  | Ethernet switches & GPS time sync system |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
73 |  |  | Fiber optic patch panel & FO cables |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
74 |  |  | Factory inspection & FAT |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
3.8 Protection & Control Equipment
75 |  |  | Control & relay panels |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
76 |  |  | Bus coupler (if applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
77 |  |  | Metering equipment |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
78 |  |  | Battery & battery charger (110V DC / 48V DC) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.9 Electrical Materials
79 |  |  | Power & control cables |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
80 |  |  | Cable trays, supports & cable termination accessories |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
81 |  |  | Earthing materials (GI flat / copper / electrodes) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
82 |  |  | Lugs, glands, PG clamps & consumables |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
3.10 Civil Materials
83 |  |  | Cement |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
84 |  |  | Steel & iron |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
85 |  |  | Aggregates |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
86 |  |  | Bricks & blocks |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4. Engineering & Approvals
4.1 Site Surveys
87 |  |  | Preliminary route / topographical survey |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
88 |  |  | Detailed route survey (DRS) – contour, DGPS profiling |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
89 |  |  | Bay survey / bay approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
90 |  |  | Load survey & feeder mapping | Distribution SS |  |  |  | ✔
91 |  |  | Soil investigation (heavy foundation locations) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
92 |  |  | Groundwater level assessment |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
93 |  |  | Incoming & outgoing line terminal survey |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
94 |  |  | AIS yard equipment marking |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
95 |  |  | Transformer–GIS / AIS–GIS interface alignment |  |  | ✔ | ✔ |  | ✔
96 |  |  | Gantry alignment survey |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
97 |  |  | Control room location marking / drawing approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
98 |  |  | GIS hall location marking |  |  | ✔ | ✔ |  | ✔
99 |  |  | Cable corridor marking |  |  | ✔ | ✔ |  | ✔
100 |  |  | GIS bay layout approval |  |  | ✔ | ✔ |  | ✔
101 |  |  | Switchyard layout & GA approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
102 |  |  | Interface survey with OHE / third rail | Traction SS only | [6 empty] | ✔
103 |  |  | Process load & harmonic / power quality study | Industrial SS | [7 empty] | ✔
4.2 Electrical Engineering
104 |  |  | Approved Single Line Diagram (SLD) from utility |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
105 |  |  | Indoor / outdoor earthing design approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
106 |  |  | Earthing design calculations |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
107 |  |  | Protection philosophy & busbar protection scheme design | Relay setting calc, insulation coordination, DSLP, earthing grid, short circuit | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
108 |  |  | Equipment quantity & BOQ finalization |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4.3 Civil Engineering
109 |  |  | Switchyard layout approval |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
110 |  |  | Control room architectural drawings |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
111 |  |  | Boundary wall, gate & fencing drawings |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
112 |  |  | Foundation design – Power Transformer |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
113 |  |  | Foundation design – CT / PT / LA / Gantries |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
114 |  |  | Foundation design – Circuit breakers |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
115 |  |  | Tower & equipment support structure design |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
116 |  |  | Transformer fire wall / bund wall design |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
117 |  |  | Cable trench layout & section drawings |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
118 |  |  | Approach road design |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4.4 SAS Engineering (If Required)
119 |  |  | SAS architecture finalization (SLD, network topology, redundancy) | Ring/Star topology | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
120 |  |  | GOOSE mapping |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
121 |  |  | IP addressing scheme |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
122 |  |  | IED & BCU engineering |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
123 |  |  | PMU integration design |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
4.5 Auxiliary System Design
124 |  |  | Firefighting system design |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
125 |  |  | HVAC design for control room |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
126 |  |  | Treated earth pits design |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
4.6 Drawing Approvals
127 |  |  | Client / utility submission |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
128 |  |  | Comment incorporation & re-submission |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
129 |  |  | Issued for Construction (IFC) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5. Civil & Structural Works
5.1 Pre-Construction Site Setup
130 |  |  | Site leveling & grading |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
131 |  |  | Boundary wall construction (if required) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
132 |  |  | Excavation for AIS equipment foundations |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
133 |  |  | Excavation for GIS plinths & cable basement |  |  | ✔ | ✔ |  | ✔
5.2 Control Room / GIS Hall Construction
134 |  |  | Control room building construction | RCC/brick, plaster, flooring, finishing | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
135 |  |  | Switchyard panel room (if applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
136 |  |  | Battery room (if required) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
137 |  |  | Fire fighting pump house |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
138 |  |  | Septic tank & soak pit |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
139 |  |  | False / anti-static flooring (if required) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
140 |  |  | RCC foundations, columns & beams |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
141 |  |  | Cable basement / trench interface |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
142 |  |  | Brickwork & plaster |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
143 |  |  | Roofing & waterproofing |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
144 |  |  | Flooring & finishing |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
145 |  |  | Door, window & rolling shutter installation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
146 |  |  | Water tank |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
147 |  |  | GIS hall construction (steel structure / RCC) |  |  | ✔ | ✔ |  | ✔
5.3 Cable Trenches & Drainage
148 |  |  | Trench excavation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
149 |  |  | RCC trench casting |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
150 |  |  | Trench covers placement |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
151 |  |  | Drainage construction | Excavation→PCC/RCC base→walls→plaster→covers→slope | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
152 |  |  | Rain water harvesting system |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5.4 Foundations
153 |  |  | Power transformer foundation with oil sump | Excluding switching SS | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
154 |  |  | Autotransformer / reactor foundation (if applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
155 |  |  | Common oil pit (if required) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
156 |  |  | Traction transformer foundation | Traction SS | [6 empty] | ✔
157 |  |  | Rectifier / converter foundation | Traction SS | [6 empty] | ✔
158 |  |  | Circuit breaker foundations |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
159 |  |  | LT transformer foundation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
160 |  |  | CT / PT foundations |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
161 |  |  | Isolator & LA foundations |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
162 |  |  | 33 kV equipment foundations | Distribution SS |  |  |  | ✔
163 |  |  | 11 kV switchgear foundation | Distribution SS |  |  |  | ✔
164 |  |  | Fire protection walls (if required) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
165 |  |  | Noise & vibration control works | Industrial SS | [7 empty] | ✔
166 |  |  | Control room foundation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
167 |  |  | DG foundation (if required) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
168 |  |  | Lighting mast foundation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
169 |  |  | Bay marshalling box foundation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
170 |  |  | Gantry foundations (dead-end & suspension) |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
5.5 Structural Erection
171 |  |  | Gantry structure erection |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
172 |  |  | Bus support structures |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
173 |  |  | LA / CT / PT / Isolator / CB / 33 kV VCB / cable support structures |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
174 |  |  | Control panel foundation / base frame |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
175 |  |  | Platforms & ladders |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
176 |  |  | Fire fighting pipe supports |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
177 |  |  | Earth mat laying (outdoor earthing) |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
6. Electrical Erection – Primary Equipment
6.1 Power Transformer / Reactor
178 |  |  | Transformer unloading & placement | Excluding switching SS | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
179 |  |  | Alignment & leveling |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
180 |  |  | Oil filtration & filling |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
181 |  |  | Radiator & accessories erection |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
182 |  |  | Oil soak pit & oil drain connection |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
183 |  |  | Breather installation |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
184 |  |  | Marshalling box wiring |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
185 |  |  | Buchholz relay & PRD piping |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
186 |  |  | Transformer fencing & gravel spreading |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
187 |  |  | Fire fighting system integration |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
188 |  |  | HV / LV connection |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
189 |  |  | Earthing (neutral / body / phase) |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
190 |  |  | BUS / Line reactor installation |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
191 |  |  | Traction transformer installation | Traction SS | [6 empty] | ✔
192 |  |  | Rectifier / converter installation | Traction SS | [6 empty] | ✔
6.2 AIS / HYB Yard Equipment
193 |  |  | Circuit breaker erection | Skip if full GIS | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
194 |  |  | Isolator & earth switch installation |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
195 |  |  | CT & PT installation |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
196 |  |  | Lightning arrester installation |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
197 |  |  | NGR installation (if applicable) |  | Cond. |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
6.3 11 kV Switchgear (Distribution)
198 |  |  | Panel unloading & placement |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
199 |  |  | Bus coupler (if two incomers) |  | Cond. | Cond. | Cond. | Cond. |  |  |  | Cond.
200 |  |  | Busbar installation |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
201 |  |  | Inter-panel connections |  | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
6.4 GIS Equipment Erection & Assembly
202 |  |  | GIS module shifting & positioning |  |  | ✔ | ✔ |  | ✔
203 |  |  | Mechanical assembly of GIS modules |  |  | ✔ | ✔ |  | ✔
204 |  |  | Torque control & SF₆ compartment sealing |  |  | ✔ | ✔ |  | ✔
205 |  |  | Transformer-GIS bus duct connection |  |  | ✔ | ✔ |  | ✔
206 |  |  | Cable sealing end installation |  |  | ✔ | ✔ |  | ✔
6.5 Busbar & Jumpers
207 |  |  | Rigid / twin / quad bus erection |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
208 |  |  | Jumper fabrication & fixing |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
209 |  |  | Torque tightening & clearance checking |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
210 |  |  | BPI insulator (if required) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
6.6 Industrial / Captive Equipment
211 |  |  | Capacitor banks / reactors | Industrial SS | [7 empty] | ✔
212 |  |  | HT switchgear erection | Industrial SS | [7 empty] | ✔
7. Electrical Erection – Secondary Systems
7.1 Control & Relay Panels & SAS
213 |  |  | Panel unloading & positioning | Material unloading, shifting to control room, layout marking | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
214 |  |  | Panel erection, alignment, grouting & fixing |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
215 |  |  | Configure protection relays | Relay setting calc, parameter config, logic testing | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
216 |  |  | SAS network installation & IED configuration upload | LAN setup, switch config, IED IP mapping | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
217 |  |  | SAS server & HMI installation | Server mounting, software install, HMI config | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
218 |  |  | RTU installation & configuration | I/O mapping, protocol config IEC 60870-5-104/101 | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
219 |  |  | PMU panel installation | PMU mounting, GPS time sync, communication setup | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
220 |  |  | Inter-panel wiring | Cable laying between panels, termination | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
221 |  |  | Internal wiring checks | Continuity check, megger test, ferrule verification | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
222 |  |  | Busbar protection panel installation | Panel erection, scheme wiring, configuration | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
7.2 Cable Laying & Termination
223 |  |  | Power cable laying | Route marking, trench, laying, backfilling | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
224 |  |  | Control & protection cable laying | Cable tray laying, routing, clamping | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
225 |  |  | Dressing, tagging & ferruling | Cable dressing, ferrule numbering, tagging | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
226 |  |  | FODP installation | Cable glanding, lugging, termination | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
227 |  |  | Cable termination at panels & equipment |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
228 |  |  | GI pipe / GI elbow installation for cable protection |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
229 |  |  | AIS to GIS control cabling | Interface cabling between AIS & GIS |  |  | ✔
230 |  |  | Transformer–GIS interface cabling | Marshalling box to GIS termination |  | ✔ | ✔ |  | ✔
231 |  |  | OLTE / FOA / SCADA communication cabling | Fiber laying, splicing, testing | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
7.3 Earthing System
232 |  |  | Earth pit installation | Excavation, electrode, backfilling | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
233 |  |  | Main earth mat laying | GI strip laying, welding, grid formation | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
234 |  |  | Equipment earthing (pipe earthing / GI flat) | Equipment bonding, double earthing | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
235 |  |  | Control room earthing | Panel earthing, clean earth system | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
236 |  |  | GIS enclosure earthing |  |  | ✔ | ✔ |  | ✔
7.4 Auxiliaries
237 |  |  | Substation DT (LT transformer) install | Installation, oil filling, testing | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
238 |  |  | Station AC supply | LT panel installation, cabling | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
239 |  |  | Yard lighting | High mast erection, cabling, focusing | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
240 |  |  | Control room lighting | Wiring, fixture installation | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
241 |  |  | DG setup (if required) | DG install, fuel system, synchronization | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
242 |  |  | DC system (battery & charger) | Rack mounting, battery install, charger wiring | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
7.5 Automation & Communication
243 |  |  | SCADA panels installation & configuration | Panel install, wiring, FO termination | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
244 |  |  | Energy meters installation | Meter install, CT/PT integration, testing | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
245 |  |  | PLC / DCS interfacing | Signal mapping, logic integration | [7 empty] | ✔
246 |  |  | PLCC / VOIP / PABX integration (if required) | Communication setup, testing | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
247 |  |  | NMS integration | Network monitoring setup | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
248 |  |  | PDC integration (if applicable) | PMU data aggregation setup | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
249 |  |  | Rack mounting – DPLC / FOTE | SDH, OLTE, switch, media converter, teleprotection terminal | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
250 |  |  | GIS asset mapping & asset tagging | GPS survey, GPS capture, data upload, consumer mapping | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
8. Testing & Commissioning
8.1 Equipment Testing
251 |  |  | Transformer / reactor tests | IR, ratio, DGA, tan-delta, magnetizing current | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
252 |  |  | Breaker timing & operation tests | Contact resistance, timing open/close/O-C | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
253 |  |  | CT / PT ratio & polarity tests | Magnetization, knee point, burden, IR | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
254 |  |  | Protection relay testing | Secondary injection, scheme check | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
255 |  |  | Insulation resistance (IR) tests |  | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
256 |  |  | SF₆ gas handling – vacuuming, filling, density setting |  |  | ✔ | ✔ |  | ✔
257 |  |  | SF₆ gas leakage testing (ppm check) |  |  | ✔ | ✔ |  | ✔
258 |  |  | GIS electrical testing – PD / interlock / logic |  |  | ✔ | ✔ |  | ✔
259 |  |  | CCTV functional test (if applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
8.2 System Testing
260 |  |  | Continuity checks |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
261 |  |  | Line protection testing | Switching SS | [5 empty] | ✔
262 |  |  | Functional & interlock tests |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
263 |  |  | SCADA testing | Point-to-point check, signal verification | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
264 |  |  | Cable testing – IR / Hi-pot / continuity |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
265 |  |  | Earth resistance testing & earth grid continuity |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
266 |  |  | Battery capacity discharge test |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
267 |  |  | DG load test (if applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
268 |  |  | Protocol testing – IEC 61850 / Modbus (if applicable) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
269 |  |  | HV cable testing – VLF / Hi-pot |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
270 |  |  | Fiber OTDR testing |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
8.3 SAS Testing (If Applicable)
271 |  |  | Site Acceptance Test (SAT) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
272 |  |  | Interlocking & trip circuit testing |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
273 |  |  | Remote SCADA integration testing |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
274 |  |  | Time synchronization testing (GPS / PTP) |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
275 |  |  | Integration testing – SAS + SCADA + RTU validation |  | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
8.4 Pre-Commissioning
276 |  |  | Protection coordination check |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
277 |  |  | Trial run | Load trial, system stability | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
278 |  |  | Client inspection & punch list |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
8.5 Energization
279 |  |  | Bay-wise charging |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
280 |  |  | Transformer energization |  | ✔ | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔
281 |  |  | 33 kV bus charging |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
282 |  |  | 11 kV bus / feeder charging | Distribution SS | ✔ | ✔ | ✔ | ✔ |  |  |  | ✔
283 |  |  | Line energization (charging test) | Switching SS | [5 empty] | ✔
284 |  |  | Grid synchronization | Transmission >132 kV |  |  |  |  | ✔
285 |  |  | Synchronization with plant load | Industrial SS | [7 empty] | ✔
286 |  |  | Power quality validation | Industrial SS | [7 empty] | ✔
287 |  |  | Continuous traction load test | Traction SS | [6 empty] | ✔
288 |  |  | Load trials & reliability run |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
9. Safety & Quality (Ongoing)
9.1 Safety Management
289 |  |  | Toolbox talks (daily) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
290 |  |  | PPE compliance monitoring |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
291 |  |  | Anti-climbing device (ACD) installation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
292 |  |  | Permit to work (PTW) system |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
293 |  |  | Safety audits & inspections |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
294 |  |  | Panel room safety items (sand bucket, extinguisher, mats) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
295 |  |  | VMS installation (if required) | Visitor management system | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond. | Cond.
9.2 HVAC, Fire & Ventilation
296 |  |  | AHU installation | Excluding up to 33 kV SS |  | ✔ | ✔ |  | ✔ |  |  | ✔
297 |  |  | Ducting & insulation |  |  | ✔ | ✔ |  | ✔ |  |  | ✔
298 |  |  | Temperature balancing | Excluding up to 33 kV SS |  | ✔ | ✔ |  | ✔ |  |  | ✔
9.3 Fire & Gas Safety
299 |  |  | Fire alarm cabling |  | Cond. | ✔ | ✔ | Cond. | ✔ | Cond. | Cond. | Cond.
300 |  |  | Fire protection integration (HVWS / NIFPES) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
301 |  |  | SF₆ gas detector installation |  |  | ✔ | ✔ |  | ✔
302 |  |  | Smoke detection system |  |  | ✔ | ✔ |  | ✔
303 |  |  | Fire extinguisher provision (mandatory transformer yard & GIS) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
304 |  |  | OEM supervision & stage approvals | GIS |  | ✔ | ✔ |  | ✔
305 |  |  | Cleanliness & torque records | GIS |  | ✔ | ✔ |  | ✔
306 |  |  | Gas handling logs | GIS |  | ✔ | ✔ |  | ✔
9.4 Quality Management
307 |  |  | ITP (Inspection & Test Plan) inspections |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
308 |  |  | Stage-wise quality checks & sign-off |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
309 |  |  | NCR (Non-Conformance Report) issuance & closure |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10. Handover & Closeout
10.1 Documentation
310 |  |  | As-built drawings compilation & submission |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
311 |  |  | Test reports compilation & submission |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
312 |  |  | O&M manuals handover |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
313 |  |  | Spare parts list & handover |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
314 |  |  | Warranty documents compilation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
315 |  |  | Final commissioning dossier |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10.2 Training
316 |  |  | Operations training to utility / client staff |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
317 |  |  | Maintenance training |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
318 |  |  | Emergency response training |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
10.3 Acceptance
319 |  |  | PAC (Provisional Acceptance Certificate) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
320 |  |  | Site reinstatement / rehabilitation |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
321 |  |  | Defects liability period monitoring |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔
322 |  |  | FAC (Final Acceptance Certificate) |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔